## Dashboard (hidden)
SuperMarty project - Project overview
Roadmap deficit prognose | Apr 2025 | Mei 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Okt 2025 | Nov 2025 | Dec 2025 | Jan 2026 | Feb 2026 | Mrt 2026
Project manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Backend development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Frontend development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UI/UX design | 0 | 14.5762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 03:46 | #VALUE!
#ERROR! | 45748 | 45778 | 45809 | 45839 | 45870 | 45901
#N/A | 2025-05-01 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30
45777
| #ERROR! | [8 empty] | 0
-89021
| #REF! | #NAME? | -45777
| #REF! | #REF!
| #REF! | #REF!
#REF!

## Dashboard Template (hidden)
PROJECT MANAGEMENT PLAN DASHBOARD TEMPLATE | [6 empty] | https://www.smartsheet.com/try-it?trp=11440&utm_source=integrated+content&utm_campaign=/content/google-sheets-project-management-templates&utm_medium=Project+Management+Plan+Dashboard+google+sheets+11440&lpa=Project+Management+Plan+Dashboard+google+sheets+11440&lx=PFpZZjisDNTS-Ddigi3MyABAgeTPLDIL8TQRu558b7w
CAMPAIGN NAME |  |  |  | DATE | PROJECT STATUS | % COMPLETE
|  |  |  | 00/00/00 | ON TRACK | 72%
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
Set Kick-Off Meeting | Alex B. | 2024-01-02 | 2024-01-08 | 6 | Complete | High
Agree on Objectives | Frank C. | 2024-01-04 | 2024-01-11 | 7 | Complete | Medium
Detailed Requests | Jacob S. | 2024-01-07 | 2024-01-11 | 4 | Complete | Low
Hardware Requests | Jacob S. | 2024-01-10 | 2024-01-15 | 5 | Complete | Low
Final Resource Plan | Jacob S. | 2024-01-13 | 2024-01-20 | 7 | Complete | Low
Staffing | Alex B. | 2024-01-16 | 2024-01-29 | 13 | Overdue | High
Technical Requests | Frank C. | 2024-01-19 | 2024-02-01 | 13 | In Progress | High
Testing | Kennedy K. | 2024-01-22 | 2024-02-09 | 18 | In Progress | High
Dev. Complete | Jacob S. | 2024-01-25 | 2024-02-05 | 11 | In Progress | High
Hardware Configuration | Alex B. | 2024-01-28 | 2024-02-06 | 9 | On Hold | High
System Testing | Kennedy K. | 2024-01-31 | 2024-02-02 | 2 | Not Started | Medium
LAUNCH |  | 2024-02-03 | 2024-02-04 | 1 | Not Started | Medium
TASK STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PLANNED | 80000
Not Started | 2 | 16.67% |  | ACTUAL | 50000
In Progress | 3 | 25%
Complete | 5 | 41.67%
Overdue | 1 | 8.333%
On Hold | 1 | 8.333%
TOTAL | 12 | 100%
TASK PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 5
High | 6 | 50% |  | Actions | 2
Medium | 3 | 25% |  | Change Requests | 4
Low | 3 | 25%
| 0 | 0%
TOTAL | 12 | 100%

## Roadmap
SuperMarty project - Roadmap MVP
User story / task |  | User story description | Project manager | Backend development | Frontend development | UI/UX design | Backend auto. testing | Frontend auto. testing | Technical (code) review | Performance testing | Security testing | Technical documentation | Total time | MVP | Backend auto. testing | Frontend auto. testing | Technical (code) review | Performance testing | Security testing | Technical documentation | Total Time | MMP | Backend auto. testing | Frontend auto. testing | Technical (code) review | Performance testing | Security testing | Technical documentation | Total Time | MLP | Backend auto. testing | Frontend auto. testing | Technical (code) review | Performance testing | Security testing | Technical documentation | Total Time | MAP | Estimated duriation | Backend req. delivery | Frontend req. delivery | Backend est. delivery | Frontend est. delivery | Estimated delivery date | Actual duration | Actual delivered date | Comment
Team communication & management activities
|  | Daily Stand Up - Scrum Poker - Retrospective - Sprint Demos, Other meetings 20% | [10 empty] | 243.245 | [7 empty] | 18.56 | [7 empty] | 19.04 | [7 empty] | 19.52 |  | 243.245 | [5 empty] | 360.31
Epic 0: Analysis and basic setups
Analysis and Environment Setup
Chore |  | Onboarding the team members on the project | 10 | 20 | 20 | 0 | 0 | 0 | 4.8 | 0.4 | 0 | 0.8 | 56 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 56 | 2025-05-02 11:41 | 2025-05-04 02:42 | 2025-05-05 02:21 | 2025-05-06 21:37 | 2025-05-06 21:37 | 41.91 | 2024-12-26
Chore |  | Review AlbertHeijn API scraper functions and APIs | 0 | 12 | 0 | 0 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 13.8 | TRUE |  |  | 0.39 |  |  | 0.52 | 15.21 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 13.8 | 2025-05-03 23:29 | 2025-05-04 02:42 | 2025-05-08 03:46 | 2025-05-06 21:37 | 2025-05-08 03:46 | 5 | 2024-12-26
Chore |  | Review Picnic API scraper and it's API end points | 0 | 12 | 0 | 0 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 13.8 | TRUE |  |  | 0.36 |  |  | 0.48 | 14.04 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 13.8 | 2025-05-05 11:17 | 2025-05-04 02:42 | 2025-05-11 05:10 | 2025-05-06 21:37 | 2025-05-11 05:10 | 5 | 2024-12-26
Chore |  | Review Jumbo web scraper and it's available APIs | 0 | 12 | 0 | 0 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 13.8 | TRUE |  |  | 0.36 |  |  | 0.48 | 14.04 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 13.8 | 2025-05-06 23:06 | 2025-05-04 02:42 | 2025-05-14 06:35 | 2025-05-06 21:37 | 2025-05-14 06:35 | 4.33 | 2024-12-26
Chore |  | Review plus web scraper and API end points | 0 | 12 | 0 | 0 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 13.8 | TRUE |  |  | 0.36 |  |  | 0.48 | 14.04 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 13.8 | 2025-05-08 10:54 | 2025-05-04 02:42 | 2025-05-17 08:00 | 2025-05-06 21:37 | 2025-05-17 08:00 | 4 | 2024-12-26
Chore |  | Technical budgeting strategy R&D to maintain the initial budget | 2 | 20 | 20 | 0 | 0 | 0 | 4.8 | 0.4 | 0 | 0.8 | 48 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 48 | 2025-05-10 22:35 | 2025-05-08 05:24 | 2025-05-22 10:21 | 2025-05-13 19:13 | 2025-05-22 10:21 | 32.56 | 2024-12-26
Chore |  | Prepare backend development repository | 0 | 2 | 0 | 0 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 2.3 | TRUE |  |  | 0.06 |  |  | 0.08 | 2.34 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 2.3 | 2378-12-09 05:34 | 1916-04-27 20:30 | 336575.9848 | 1948-12-21 13:30 | 336575.9848 | 0
Chore |  | Basic setup of backend repository and its API doc structure | 0 | 4 | 0 | 0 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 4.6 | TRUE | 0.4 | 0 | 0.12 | 0.08 | 0.04 | 0.16 | 5.2 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 4.6 | 2378-12-12 04:01 | 1916-04-27 20:30 | 336582.3595 | 1948-12-21 13:30 | 336582.3595 | 0
Chore |  | Basic setup of Android and IOS applications using Capacitor | 0 | 0 | 8 | 0 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 9.2 | TRUE | 0 | 0.8 | 0.24 | 0.16 | 0.08 | 0.32 | 10.4 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 9.2 | 2378-12-12 04:01 | 1916-04-29 11:59 | 336582.3595 | 1948-12-24 07:45 | 336582.3595 | 0
Chore |  | Prepare UI/UX design system | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8.6 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 8.6 | 2378-12-10 23:20 | 1916-04-29 11:59 | 336579.5534 | 1948-12-24 07:45 | 336579.5534 | 0
Chore |  | Setting up project management infrastructure | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 5.6 | 2378-12-10 23:20 | 1916-04-29 11:59 | 336579.5534 | 1948-12-24 07:45 | 336579.5534 | 0 | 2024-12-19
December 29 to January 23 |  | Epic 1 : Build the core system infrastructure, product aggregation, and admin panel basics.
Sprint 1 - 29 Dec to Jan 9
Chore | Must | As a developer, I want to design the database structure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE |  |  | 0.72 |  |  | 0.96 | 28.08 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 0 | 2025-05-08 10:54 | 2025-05-04 02:42 | 2025-05-17 08:00 | 2025-05-06 21:37 | 2025-05-17 08:00 | 6.85 | 2025-01-09
Chore | Must | Deploy project on development server | 0 | 8 | 0 | 0 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 8.45 | TRUE |  |  | 0.48 |  |  | 0.64 | 18.72 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 8.45 | 2378-12-13 03:53 | 1916-04-29 11:59 | 336584.3987 | 1948-12-24 07:45 | 336584.3987 | 1.01 | 2025-01-09
Chore | Must | As a DevOps engineer I want to set up project's infrastructure | 0 | 8 | 0 | 0 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 9.2 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 9.2 | 2378-12-11 23:12 | 1916-04-29 11:59 | 336581.5925 | 1948-12-24 07:45 | 336581.5925 | 6.01 | 2025-01-09
Chore | Must | As [developer] I have to setup & dockerize a aggregator codebase | 0 | 2 | 0 | 0 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 2.3 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 2.3 | 2378-12-11 05:18 | 1916-04-29 11:59 | 336580.0632 | 1948-12-24 07:45 | 336580.0632 | 3 | 2025-01-09
Feature | Must | As an admin, I want to log in to the portal so that I can access and manage the system securely | 1.4 | 7 | 0 | 0 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 9.45 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 9.45 | 2378-12-12 20:05 | 1916-04-29 11:59 | 336583.3768 | 1948-12-24 07:45 | 336583.3768 | 2.71 | 2025-01-09
Feature | Must | As an admin, I want to set a password during my first login or after a reset so that I can securely access my account | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2378-12-12 20:05 | 1916-04-29 11:59 | 336583.3768 | 1948-12-24 07:45 | 336583.3768 | 2.71 | 2025-01-09
Feature | Should | As an admin, I want to use the "Forgot Password" feature so that I can recover access to my account if I forget my credentials | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2378-12-12 20:05 | 1916-04-29 11:59 | 336583.3768 | 1948-12-24 07:45 | 336583.3768 | 2.71 | 2025-01-09
Feature | Must | As an admin, I want to receive welcome and reset password emails so that I am guided through account setup or recovery | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2378-12-12 20:05 | 1916-04-29 11:59 | 336583.3768 | 1948-12-24 07:45 | 336583.3768 | 2.71 | 2025-01-09
Feature | Should | As an admin, I want to log out of the portal so that I can ensure my account's security when leaving the session | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2378-12-12 20:05 | 1916-04-29 11:59 | 336583.3768 | 1948-12-24 07:45 | 336583.3768 | 2.94 | 2025-01-09
Chore | Must | As a developer, I want to retrieve product data from supermarket APIs so that I can maintain an up-to-date product catalog. | 0 | 24 | 0 | 0 | 0 | 0 | 2.88 | 0.24 | 0 | 0.48 | 27.6 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 27.6 | 2378-12-11 05:18 | 1916-04-27 20:30 | 336580.0632 | 1948-12-21 13:30 | 336580.0632 | 49.92 | 2025-01-09
Chore | Should | As a system administrator, I want periodic data fetches to occur every 24 hours so that the database remains current without manual intervention. | 0 | 8 | 0 | 0 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 9.2 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 9.2 | 2378-12-09 05:34 | 1916-04-27 20:30 | 336575.9848 | 1948-12-21 13:30 | 336575.9848 | 1.01 | 2025-01-09
Chore | Should | As a developer, I want the system to respect API rate limits so that we comply with supermarket policies and avoid service interruptions. | 0 | 4 | 0 | 0 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 4.6 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.6 | 2378-12-08 17:37 | 1916-04-27 20:30 | 336574.9652 | 1948-12-21 13:30 | 336574.9652 | 1.01 | 2025-01-09
Feature | Must | As an admin, I want to create a new category so that I can organize items effectively | 1 | 5 | 0 | 0 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 6.75 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6.75 | 2378-12-09 14:31 | 1916-04-27 20:30 | 336576.7495 | 1948-12-21 13:30 | 336576.7495 | 3.71 | 2025-01-09
Feature | Must | As an admin, I want to view all categories in a list or grid so that I can understand the current structure | 0.6 | 3 | 0 | 0 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.05 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.05 | 2378-12-09 08:33 | 1916-04-27 20:30 | 336576.2397 | 1948-12-21 13:30 | 336576.2397 | 3.71 | 2025-01-09
Feature | Must | As an admin, I want to create a new label so that I can tag and identify items more effectively. | 0.6 | 3 | 0 | 0 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.05 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.05 | 2378-12-13 05:03 | 1916-04-29 11:59 | 336584.1415 | 1948-12-24 07:45 | 336584.1415 | 2.49 | 2025-01-09
Feature | Must | As an admin, I want to view all labels in a list or grid so that I can see which labels are available. | 1 | 5 | 0 | 0 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 6.75 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6.75 | 2378-12-13 19:58 | 1916-04-29 11:59 | 336585.416 | 1948-12-24 07:45 | 336585.416 | 1.71 | 2025-01-09
Feature | Should | As an admin, I want to edit existing labels so that I can correct errors or update their attributes. | 0.4 | 2 | 0 | 0 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 2.7 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 2.7 | 2378-12-14 01:56 | 1916-04-29 11:59 | 336585.9258 | 1948-12-24 07:45 | 336585.9258 | 1.71 | 2025-01-09
Feature | Could | As an admin, I want to delete a label so that I can remove outdated or unused labels from the system | 0.6 | 3 | 0 | 0 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.05 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.05 | 2378-12-14 10:53 | 1916-04-29 11:59 | 336586.6905 | 1948-12-24 07:45 | 336586.6905 | 1.71 | 2025-01-09
Feature | Could | As an admin, I want to search for specific labels by name or keyword so that I can locate them efficiently | 0.6 | 3 | 0 | 0 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.05 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.05 | 2378-12-14 19:50 | 1916-04-29 11:59 | 336587.4552 | 1948-12-24 07:45 | 336587.4552 | 1.71 | 2025-01-09
Feature | Should | As an admin, I want to edit existing categories so that I can update their names or attributes as needed | 0.8 | 4 | 0 | 0 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 5.4 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 5.4 | 2378-12-14 03:46 | 1916-04-29 11:59 | 336586.4379 | 1948-12-24 07:45 | 336586.4379 | 3.71 | 2025-01-09
Feature | Could | As an admin, I want to search for specific categories by name or keyword so that I can find them quickly | 0.4 | 2 | 0 | 0 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 2.7 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 2.7 | 2378-12-07 19:35 | 1916-04-27 20:30 | 336573.4381 | 1948-12-21 13:30 | 336573.4381 | 2.24 | 2025-01-09
Feature | Could | As an admin, I want to delete a category so that I can remove unused or irrelevant ones from the system | 0.8 | 4 | 0 | 0 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 5.4 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 5.4 | 2378-12-09 11:32 | 1916-04-27 20:30 | 336576.4946 | 1948-12-21 13:30 | 336576.4946 | 4.71 | 2025-01-09
Chore | Must | As a developer I want to prepare the development environment |  | 1 | [9 empty] | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [6 empty] | 1
Sprint 2 - 12 Jan to 23 Jan
Chore | Must | Implement cron jobs to fetch and update data in develop environment | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE |  |  | 0.36 |  |  | 0.48 | 14.04 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 0 | 2025-05-10 22:35 | 2025-05-08 05:24 | 2025-05-22 10:21 | 2025-05-13 19:13 | 2025-05-22 10:21 | 1.91 | 2025-01-23
Chore | Must | We need to map and sync captured data from aggregators to supermarty | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE |  |  | 0.36 |  |  | 0.48 | 14.04 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 0 | 2378-12-09 05:34 | 1916-04-27 20:30 | 336575.9848 | 1948-12-21 13:30 | 336575.9848 | 6.66 | 2025-01-23
Chore | Must | As a developer, I want an automated process to relate the market products in different supermarkets to the corresponding system products in the system | 0 | 12 | 0 | 0 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 13.8 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 13.8 | 2378-12-11 04:09 | 1916-04-27 20:30 | 336580.3203 | 1948-12-21 13:30 | 336580.3203 | 5.94 | 2025-01-23
Feature | Must | As an admin, I want to create a new system product so that I can add new products to the system. | 1 | 5 | 0 | 0 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 6.75 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6.75 | 2378-12-08 20:37 | 1916-04-27 20:30 | 336575.2201 | 1948-12-21 13:30 | 336575.2201 | 2.61 | 2025-01-23
Feature | Must | As an admin, I want to publish or unpublish system products so that I can control what is visible to end users. | 0.4 | 2 | 0 | 0 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 2.7 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 2.7 | 2378-12-07 07:39 | 1916-04-27 20:30 | 336572.4185 | 1948-12-21 13:30 | 336572.4185 | 3.13 | 2025-01-09
Feature | Should | As an admin, I want to search for products by name or tags so that I can quickly find specific items in the system. | 0.2 | 1 | 0 | 0 | 0 | 0 | 0.12 | 0.01 | 0 | 0.02 | 1.35 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 1.35 | 2378-12-07 19:35 | 1916-04-27 20:30 | 336573.4381 | 1948-12-21 13:30 | 336573.4381 | 2.61 | 2025-01-09
Feature | Must | As an admin, I want to view a list of system products so that I can monitor and manage product data efficiently. | 0.4 | 2 | 0 | 0 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 2.7 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 2.7 | 2378-12-08 08:40 | 1916-04-27 20:30 | 336574.2005 | 1948-12-21 13:30 | 336574.2005 | 5.52 | 2025-01-09
Feature | Could | As an admin, I want to filter categories based on certain criteria (e.g., status, type) so that I can narrow down the results | 0.2 | 1 | 0 | 0 | 0 | 0 | 0.12 | 0.01 | 0 | 0.02 | 1.35 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 1.35 | 2378-12-08 23:36 | 1916-04-27 20:30 | 336575.475 | 1948-12-21 13:30 | 336575.475 | 2.61 | 2025-01-23
Feature | Should | As a user, I want to see similar products grouped together so that I can choose the best option easily. | 1 | 5 | 0 | 0 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 6.75 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6.75 | 2378-12-10 07:16 | 1916-04-27 20:30 | 336578.5361 | 1948-12-21 13:30 | 336578.5361 | 2.61 | 2025-01-23
Feature | Could | As an admin, I want to filter products by various attributes so that I can refine the product list for specific management tasks. | 0.2 | 1 | 0 | 0 | 0 | 0 | 0.12 | 0.01 | 0 | 0.02 | 1.35 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 1.35 | 2378-12-10 10:15 | 1916-04-27 20:30 | 336578.791 | 1948-12-21 13:30 | 336578.791 | 2.61 | 2025-01-23
Feature | Should | As a user, I want prices to be displayed in a standard format (e.g., price per kg and total price) so that I can compare products easily. | 2.4 | 12 | 0 | 0 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 16.2 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 16.2 | 2378-12-10 11:24 | 1916-04-27 20:30 | 336578.5338 | 1948-12-21 13:30 | 336578.5338 | 6.44 | 2025-01-23
Feature | Should | As a user, I want product weights to be standardized (e.g., grams, liters) so that I can easily understand and compare the quantities of different items. | 0.8 | 4 | 0 | 0 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 5.4 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 5.4 | 2378-12-10 23:20 | 1916-04-27 20:30 | 336579.5534 | 1948-12-21 13:30 | 336579.5534 | 8.56 | 2025-01-23
Feature | Could | As an admin, I want to filter labels based on certain criteria (e.g., type, associated categories) so that I can refine the results | 0.2 | 1 | 0 | 0 | 0 | 0 | 0.12 | 0.01 | 0 | 0.02 | 1.35 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 1.35 | 2378-12-14 22:49 | 1916-04-29 11:59 | 336587.7101 | 1948-12-24 07:45 | 336587.7101 | 2.61 | 2025-01-23
Chore | Must | Jumbo ¦ As a developer, I want to retrieve product data from supermarket APIs so that I can maintain an up-to-date product catalog. | 0 | 8 | 0 | 0 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 9.2 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 9.2 | 2378-12-15 03:38 | 1916-04-29 11:59 | 336588.4771 | 1948-12-24 07:45 | 336588.4771 | 14.93 | 2025-01-23
Chore | Must | As a user, I want nutritional information to be standardized so that I can make informed choices about my purchases. | 0 | 12 | 0 | 0 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 13.8 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 13.8 | 2378-12-09 07:24 | 1916-04-27 20:30 | 336576.4969 | 1948-12-21 13:30 | 336576.4969 | 7.83 | 2025-01-23
Chore | Should | As [developer] I have to refactor aggregation services & make them more safe in which times that might be error happened | 0 | 12 | 0 | 0 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 13.8 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 13.8 | 2378-12-10 23:20 | 1916-04-27 20:30 | 336579.5534 | 1948-12-21 13:30 | 336579.5534 | 3.61 | 2025-01-23
January 26 to February 20 |  | Epic 2: Meal management, Bag management, Categories page for users, Product list for users, Product single page for users, Authentication, Bags for users, meals for users
Sprint 3 - Jan 26 to Feb 6 | [44 empty] | 255.44
Feature | Must | As a team member, I want to implement feedback from the previous epic so that the product aligns with stakeholder expectations and enhances user satisfaction. | 3.2 | 16 | 0 | 0 | 0 | 0 | 1.92 | 0.16 | 0 | 0.32 | 21.6 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 21.6 | 2378-12-12 23:05 | 1916-04-27 20:30 | 336583.6317 | 1948-12-21 13:30 | 336583.6317 |  | 2025-02-17
Chore | Must | As a DevOps, I want to set up the frontend infrastructure so that the project has a scalable and maintainable foundation | 0 | 4 | 0 | 0 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 4.6 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.6 | 2378-12-13 11:01 | 1916-04-27 20:30 | 336584.6513 | 1948-12-21 13:30 | 336584.6513 |  | 2025-02-17
Feature | Must | As an admin, I want to have an overview of all bags so that I can monitor and manage their contents effectively. | 0.6 | 3 | 0 | 0 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.05 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.05 | 2378-12-13 19:58 | 1916-04-27 20:30 | 336585.416 | 1948-12-21 13:30 | 336585.416 |  | 2025-02-17
Feature | Must | As an admin, I want to add new bags so that I can include additional inventory into the system. | 1.6 | 8 | 0 | 0 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 10.8 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 10.8 | 2378-12-14 19:50 | 1916-04-27 20:30 | 336587.4552 | 1948-12-21 13:30 | 336587.4552 |  | 2025-02-17
Feature | Should | As an admin, I want to edit bag details so that I can update information accurately when needed. | 0.4 | 2 | 0 | 0 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 2.7 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 2.7 | 2378-12-15 01:48 | 1916-04-27 20:30 | 336587.965 | 1948-12-21 13:30 | 336587.965 |  | 2025-02-17
Feature | Should | As an admin, I want to delete bags so that I can remove outdated or irrelevant items from the system. | 0.2 | 1 | 0 | 0 | 0 | 0 | 0.12 | 0.01 | 0 | 0.02 | 1.35 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 1.35 | 2378-12-15 04:47 | 1916-04-27 20:30 | 336588.2199 | 1948-12-21 13:30 | 336588.2199 |  | 2025-02-17
Feature | Could | As an admin, I want to filter bags so that I can quickly locate specific items or groups for review. | 0.4 | 2 | 0 | 0 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 2.7 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 2.7 | 2378-12-15 10:45 | 1916-04-27 20:30 | 336588.7297 | 1948-12-21 13:30 | 336588.7297 |  | 2025-02-17
Feature | Must | As an admin, I want to have an overview of all meals so that I can manage and monitor meal plans comprehensively. | 0.6 | 3 | 0 | 0 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.05 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.05 | 2378-12-15 19:42 | 1916-04-27 20:30 | 336589.4944 | 1948-12-21 13:30 | 336589.4944 |  | 2025-02-17
Feature | Must | As an admin, I want to add new meals so that I can expand and update the available meal options. | 1.6 | 8 | 0 | 0 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 10.8 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 10.8 | 2378-12-16 19:34 | 1916-04-27 20:30 | 336591.5335 | 1948-12-21 13:30 | 336591.5335 |  | 2025-02-17
Feature | Should | As an admin, I want to edit meal details so that I can update ingredients, recipes, or other relevant information as needed. | 0.4 | 2 | 0 | 0 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 2.7 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 2.7 | 2378-12-17 01:32 | 1916-04-27 20:30 | 336592.0433 | 1948-12-21 13:30 | 336592.0433 |  | 2025-02-17
Feature | Could | As an admin, I want to delete meals so that I can remove obsolete or undesired options from the system. | 0.2 | 1 | 0 | 0 | 0 | 0 | 0.12 | 0.01 | 0 | 0.02 | 1.35 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 1.35 | 2378-12-17 04:32 | 1916-04-27 20:30 | 336592.2982 | 1948-12-21 13:30 | 336592.2982 |  | 2025-02-17
Feature | Could | As an admin, I want to search and filter meals so that I can quickly locate specific meals or categories for efficient management. | 0.4 | 2 | 0 | 0 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 2.7 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 2.7 | 2378-12-17 10:30 | 1916-04-27 20:30 | 336592.808 | 1948-12-21 13:30 | 336592.808 |  | 2025-02-17
Feature | Must | As an admin, I want to view an overview of users, including their name, and other details, so that I can quickly understand user profiles and manage them efficiently. | 0.4 | 2 | 0 | 0 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 2.7 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 2.7 | 2378-12-17 16:28 | 1916-04-27 20:30 | 336593.3178 | 1948-12-21 13:30 | 336593.3178 |  | 2025-02-17
Feature | Could | As an admin, I want to edit a user's information and change their role so that I can update their permissions or account details as necessary. | 0.2 | 1 | 0 | 0 | 0 | 0 | 0.12 | 0.01 | 0 | 0.02 | 1.35 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 1.35 | 2378-12-17 19:27 | 1916-04-27 20:30 | 336593.5727 | 1948-12-21 13:30 | 336593.5727 |  | 2025-02-17
Feature | Must | As a user, I want to prepare the page structure | 0.8 | 0 | 4 | 0.6 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 6 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6 | 2378-12-17 19:27 | 1916-04-28 16:14 | 336593.5727 | 1948-12-22 22:38 | 336593.5727 |  | 2025-02-17
Feature | Should | As a user, I want to view a product's header so that I can quickly identify the product. | 1 | 4 | 1 | 0.15 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 6.9 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6.9 | 2378-12-18 07:23 | 1916-04-28 01:26 | 336594.5923 | 1948-12-21 21:47 | 336594.5923 |  | 2025-02-17
Feature | Must | As a user, I want to see the title, description, and price of a product so that I can understand what it is and how much it costs. | 0.2 |  | 1 | 0.15 | 0 | 0 | 0.12 | 0.01 | 0 | 0.02 | 1.5 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 1.5 | 2378-12-18 07:23 | 1916-04-28 06:22 | 336594.5923 | 1948-12-22 06:04 | 336594.5923 |  | 2025-02-17
Feature | Must | As a user, I want to view the Nutri-score and labels of a product so that I can make informed choices about its nutritional value. | 0.2 |  | 1 | 0.15 | 0 | 0 | 0.12 | 0.01 | 0 | 0.02 | 1.5 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 1.5 | 2378-12-18 07:23 | 1916-04-28 11:18 | 336594.5923 | 1948-12-22 14:21 | 336594.5923 |  | 2025-02-17
Feature | Must | As a user, I want to compare supermarket prices for a product so that I can choose the most affordable option. | 0.4 |  | 2 | 0.3 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 3 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 3 | 2378-12-18 07:23 | 1916-04-28 21:11 | 336594.5923 | 1948-12-23 06:54 | 336594.5923 |  | 2025-02-17
Feature | Must | As a user, I want to add a product to my cart directly from the price comparison list so that I can shop conveniently. | 0.6 |  | 3 | 0.45 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.5 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.5 | 2378-12-18 07:23 | 1916-04-29 11:59 | 336594.5923 | 1948-12-24 07:45 | 336594.5923 |  | 2025-02-17
Feature | Must | As a user, I want to access the detailed nutritional information of a product so that I can assess if it meets my dietary needs. | 0.8 |  | 4 | 0.6 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 6 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6 | 2378-12-18 07:23 | 1916-04-30 07:43 | 336594.5923 | 1948-12-25 16:52 | 336594.5923 |  | 2025-02-17
Feature | Should | As a user, I want to see a list of similar products so that I can explore alternatives. | 0.6 |  | 3 | 0.45 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.5 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.5 | 2378-12-18 07:23 | 1916-04-30 22:31 | 336594.5923 | 1948-12-26 17:43 | 336594.5923 |  | 2025-02-17
Feature | Should | As a user, I want to discover meals that include the product so that I can find ideas for using it. | 0.8 |  | 4 | 0.6 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 6 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6 | 2378-12-18 07:23 | 1916-05-01 18:16 | 336594.5923 | 1948-12-28 02:50 | 336594.5923 |  | 2025-02-17
Feature | Should | As a user, I want to view the category header and title so that I know which type of products I am browsing. | 1.4 | 5 | 2 | 0.3 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 9.75 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 9.75 | 2378-12-18 22:18 | 1916-05-02 04:08 | 336595.8668 | 1948-12-28 19:24 | 336595.8668 |  | 2025-02-17
Feature | Could | As a user, I want to see a list of sub-categories so that I can narrow down my search to specific types of products. | 2 |  | 10 | 1.5 | 0 | 0 | 1.2 | 0.1 | 0 | 0.2 | 15 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 15 | 2378-12-18 07:23 | 1916-05-03 19:37 | 336594.5923 | 1948-12-31 13:38 | 336594.5923 |  | 2025-02-17
Feature | Could | As a user, I want to see a list of categories and so that I can narrow down my search to specific types of products. | 0.6 |  | 3 | 0.45 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.5 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.5 | 2378-12-18 22:18 | 1916-05-02 18:56 | 336595.8668 | 1948-12-29 20:14 | 336595.8668 |  | 2025-02-17
Feature | Should | As a user, I want to view related recipes in a selected category so that I can find cooking inspiration. | 0.2 |  | 1 | 0.15 | 0 | 0 | 0.12 | 0.01 | 0 | 0.02 | 1.5 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 1.5 | 2378-12-18 22:18 | 1916-05-02 23:52 | 336595.8668 | 1948-12-30 04:31 | 336595.8668 |  | 2025-02-17
Feature | Must | As a user, I want to see the products in a selected category with lazy loading so that I can browse efficiently without waiting for all items to load at once. | 1.6 | 3 | 5 | 0.75 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.55 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 11.55 | 2378-12-19 07:15 | 1916-05-04 00:33 | 336596.6315 | 1948-12-31 21:55 | 336596.6315 |  | 2025-02-17
Feature | Could | As a user, I want to filter products based on labels and food types so that I can easily find what suits my preferences or needs. | 0.6 |  | 3 | 0.45 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.5 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.5 | 2378-12-19 07:15 | 1916-05-04 15:21 | 336596.6315 | 1949-01-01 22:46 | 336596.6315 |  | 2025-02-17
Sprint 4 - Feb 9 to Feb 21
Feature | Could | As a user, I want to see a list of similar bags so that I can explore alternatives. | 0.9 | 3 | 1.5 | 0.225 | 0 | 0 | 0.54 | 0.045 | 0 | 0.09 | 6.3 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6.3 | 2025-05-05 11:17 | 2025-05-05 15:42 | 2025-05-11 05:10 | 2025-05-09 11:43 | 2025-05-11 05:10
Bag category and meal category management in admin panel
Feature | Must | As an admin, I want to create meal category so I can categorize my meals in meaningful groups | 1 | 5 | 0 | 0 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 6.75 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6.75 | 2025-05-06 02:12 | 2025-05-05 15:42 | 2025-05-12 11:46 | 2025-05-09 11:43 | 2025-05-12 11:46 |  | 2025-02-20
Feature | Must | As an admin, I want to have an overview of the meal categories so that I can see the meal categories at 1 glance | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 02:12 | 2025-05-05 15:42 | 2025-05-12 11:46 | 2025-05-09 11:43 | 2025-05-12 11:46 |  | 2025-02-20
Feature | Should | As an admin, I want to have the ability to delete the meal categories so that I can get rid of the unwanted meal categories | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 02:12 | 2025-05-05 15:42 | 2025-05-12 11:46 | 2025-05-09 11:43 | 2025-05-12 11:46 |  | 2025-02-20
Feature | Should | As an admin, I want to have the ability to edit the meal categories so that I can adjust the needed info in meal categories | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 02:12 | 2025-05-05 15:42 | 2025-05-12 11:46 | 2025-05-09 11:43 | 2025-05-12 11:46 |  | 2025-02-20
Feature | Must | As an admin, I want to create bag category so I can categorize my bags in meaningful groups | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 02:12 | 2025-05-05 15:42 | 2025-05-12 11:46 | 2025-05-09 11:43 | 2025-05-12 11:46 |  | 2025-02-20
Feature | Must | As an admin, I want to have an overview of the bags categories so that I can see the bag categories at 1 glance | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 02:12 | 2025-05-05 15:42 | 2025-05-12 11:46 | 2025-05-09 11:43 | 2025-05-12 11:46 |  | 2025-02-20
Feature | Should | As an admin, I want to have the ability to delete the bag categories so that I can get rid of the unwanted bag categories | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 02:12 | 2025-05-05 15:42 | 2025-05-12 11:46 | 2025-05-09 11:43 | 2025-05-12 11:46 |  | 2025-02-20
Feature | Should | As an admin, I want to have the ability to edit the bag categories so that I can adjust the needed info in bag categories | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 02:12 | 2025-05-05 15:42 | 2025-05-12 11:46 | 2025-05-09 11:43 | 2025-05-12 11:46 |  | 2025-02-20
Authentication
Feature | Must | As a user, I want to sign up so that I can create an account and access the platform. | 1.2 | 3 | 3 | 0.45 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.55 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 8.55 | 2025-05-06 11:10 | 2025-05-06 06:31 | 2025-05-13 06:07 | 2025-05-10 12:33 | 2025-05-13 06:07 |  | 2025-02-20
Feature | Must | As a user, I want to log in so that I can access my account securely. | 1 | 2 | 3 | 0.45 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 7.2 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 7.2 | 2025-05-06 17:08 | 2025-05-06 21:19 | 2025-05-13 18:21 | 2025-05-11 13:24 | 2025-05-13 18:21 | 13 | 2025-02-20
Feature | Must | As a user, I want to set a password during my first login or reset process so that I can secure my account. | 1.6 | 4 | 4 | 0.6 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.4 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 11.4 | 2025-05-07 05:04 | 2025-05-07 17:03 | 2025-05-14 18:49 | 2025-05-12 22:31 | 2025-05-14 18:49 | 7.07 | 2025-02-20
Chore | Must | As a user, I want to have my session automatically refreshed so that I don't have to log in repeatedly. | 0 | 2 | 2 | 0 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 4.6 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.6 | 2025-05-07 11:02 | 2025-05-08 02:56 | 2025-05-15 07:03 | 2025-05-13 15:05 | 2025-05-15 07:03 | 21.57 | 2025-02-20
Feature | Must | As a user, I want to log out so that I can secure my account after using the platform. | 0.4 | 1 | 1 | 0.15 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 2.85 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 2.85 | 2025-05-04 11:25 | 2025-05-06 04:03 | 2025-05-09 04:14 | 2025-05-10 08:25 | 2025-05-10 08:25 | 25.75 | 2025-02-20
February 23 to March 18 |  | Epic 3: Discover, Shoping cart and check out pages in user portal, meal and bag categories
Sprint 5 - Feb 23 to March 6 | [44 empty] | 98.55
Meal categories and details in user panel
Feature | Must | As a user, I want to see the meal categories so that I can find relevent meals easily via navigating within the meal categories | 0.7 | 2 | 1.5 | 0.225 | 0 | 0 | 0.42 | 0.035 | 0 | 0.07 | 4.95 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.95 | 2025-05-04 17:23 | 2025-05-06 11:27 | 2025-05-09 16:28 | 2025-05-10 20:50 | 2025-05-10 20:50
Feature | Could | As a user, I want to see the Popular meal recipes block in meal category so that I can see the most intresting recipes | 0.7 | 2 | 1.5 | 0.225 | 0 | 0 | 0.42 | 0.035 | 0 | 0.07 | 4.95 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.95 | 2025-05-04 23:21 | 2025-05-06 18:51 | 2025-05-10 04:42 | 2025-05-11 09:15 | 2025-05-11 09:15
Feature | Must | As a user, I want to see the meal list connected to a meal category so that I can find the recipe that I like | 1.2 | 4 | 2 | 0.3 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.4 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 8.4 | 2025-05-05 11:17 | 2025-05-07 04:43 | 2025-05-11 05:10 | 2025-05-12 01:49 | 2025-05-12 01:49
Feature | Should | As a user, I want to see the header, title, and total price of a meal so that I can understand what it is and how much it costs. | 0.6 | 1.5 | 1.5 | 0.225 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.275 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.275 | 2025-05-05 15:46 | 2025-05-07 12:07 | 2025-05-11 14:21 | 2025-05-12 14:14 | 2025-05-12 14:14
Feature | Must | As a user, I want to see the meal's recipe as a plain text so that I can learn how to cook it | 0.4 | 0.5 | 1.5 | 0.225 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 2.925 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 2.925 | 2025-05-05 17:15 | 2025-05-07 19:31 | 2025-05-11 17:24 | 2025-05-13 02:40 | 2025-05-13 02:40
Feature | Should | As a user, I want to view the Nutri-score of a meal so that I can make informed choices about its nutritional value. | 0.9 | 3 | 1.5 | 0.225 | 0 | 0 | 0.54 | 0.045 | 0 | 0.09 | 6.3 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6.3 | 2025-05-06 02:12 | 2025-05-08 02:56 | 2025-05-12 11:46 | 2025-05-13 15:05 | 2025-05-13 15:05
Feature | Must | As a user, I want to compare supermarket prices for a meal so that I can choose the most affordable option. | 2 | 8 | 2 | 0.3 | 0 | 0 | 1.2 | 0.1 | 0 | 0.2 | 13.8 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 13.8 | 2025-05-07 02:05 | 2025-05-08 12:48 | 2025-05-14 12:42 | 2025-05-14 07:38 | 2025-05-14 12:42
Feature | Must | As a user, I want to see the list of the grocery items in the meal and add a product to my cart directly from the price comparison list so that I can shop conveniently. | 0.4 |  | 2 | 0.3 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 3 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 3 | 2025-05-07 02:05 | 2025-05-08 22:40 | 2025-05-14 12:42 | 2025-05-15 00:12 | 2025-05-15 00:12
Bags categories and details in user panel
Feature | Must | As a user, I want to see the bag categories so that I can find relevent bagls easily via navigating within the bag categories | 0.8 | 2 | 2 | 0.3 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 5.7 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 5.7 | 2025-05-07 08:03 | 2025-05-09 08:32 | 2025-05-15 00:56 | 2025-05-15 16:46 | 2025-05-15 16:46
Feature | Could | As a user, I want to see the Popular bags block in meal category so that I can see the most intresting bags | 0.8 | 2 | 2 | 0.3 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 5.7 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 5.7 | 2025-05-07 14:01 | 2025-05-09 18:24 | 2025-05-15 13:10 | 2025-05-16 09:19 | 2025-05-16 09:19
Feature | Must | As a user, I want to see the bag list connected to a bag category so that I can find the bag that I like | 1.2 | 4 | 2 | 0.3 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.4 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 8.4 | 2025-05-08 01:57 | 2025-05-10 04:16 | 2025-05-16 13:38 | 2025-05-17 01:53 | 2025-05-17 01:53
Feature | Should | As a user, I want to see the header, title, description, and total price of a bag so that I can understand what it is and how much it costs. | 0.7 | 1.5 | 2 | 0.3 | 0 | 0 | 0.42 | 0.035 | 0 | 0.07 | 5.025 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 5.025 | 2025-05-08 06:26 | 2025-05-10 14:09 | 2025-05-16 22:49 | 2025-05-17 18:27 | 2025-05-17 18:27
Feature | Should | As a user, I want to view the Nutri-score of a bag so that I can make informed choices about its nutritional value. | 1 | 3 | 2 | 0.3 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 7.05 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 7.05 | 2025-05-08 15:23 | 2025-05-11 00:01 | 2025-05-17 17:10 | 2025-05-18 11:00 | 2025-05-18 11:00
Feature | Must | As a user, I want to compare supermarket prices for a bag so that I can choose the most affordable option. | 2 | 8 | 2 | 0.3 | 0 | 0 | 1.2 | 0.1 | 0 | 0.2 | 13.8 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 13.8 | 2025-05-05 02:20 | 2025-05-04 22:26 | 2025-05-10 10:49 | 2025-05-08 06:44 | 2025-05-10 10:49
Feature | Must | As a user, I want to see the list of the grocery items in the bag and add a product to my cart directly from the price comparison list so that I can shop conveniently. | 0.4 |  | 2 | 0.3 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 3 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 3 | 2025-05-05 02:20 | 2025-05-05 08:18 | 2025-05-10 10:49 | 2025-05-08 23:18 | 2025-05-10 10:49
Sprint 6 - March 9 to March 18 | [44 empty] | 120
Feature | Must | As a team member, I want to implement feedback from the previous epic so that the product aligns with stakeholder expectations and enhances user satisfaction. | 6.4 | 16 | 16 | 2.4 | 0 | 0 | 3.84 | 0.32 | 0 | 0.64 | 45.6 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 45.6 | 2025-05-01 23:44 | 2025-05-03 06:57 | 2025-05-04 01:53 | 2025-05-05 12:29 | 2025-05-05 12:29
Discover, Bags, and Meal pages
Feature | Must | As a user, I want to view my shopping list so that I can keep track of items to purchase. | 2.6 | 5 | 8 | 1.2 | 0 | 0 | 1.56 | 0.13 | 0 | 0.26 | 18.75 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 18.75 | 2025-05-04 17:23 | 2025-05-06 04:03 | 2025-05-09 16:28 | 2025-05-10 08:25 | 2025-05-10 08:25
Feature | Could | As a user, I want to see a list of similar meals so that I can explore alternatives. | 0.9 | 3 | 1.5 | 0.225 | 0 | 0 | 0.54 | 0.045 | 0 | 0.09 | 6.3 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6.3 | 2025-05-07 11:02 | 2025-05-09 06:04 | 2025-05-15 07:03 | 2025-05-15 12:37 | 2025-05-15 12:37
Feature | Must | As a user, I want to explore the discover page so that I can browse different products, meals, and bags. | 3.2 | 12 | 4 | 0.6 | 0 | 0 | 1.92 | 0.16 | 0 | 0.32 | 22.2 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 22.2 | 2025-05-03 11:33 | 2025-05-04 02:42 | 2025-05-07 03:17 | 2025-05-06 21:37 | 2025-05-07 03:17
Feature | Should | As a user, I want to be able to switch between tabs in the discover page so that I can filter the data | 0.4 |  | 2 | 0.3 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 3 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 3 | 2025-05-03 11:33 | 2025-05-04 12:34 | 2025-05-07 03:17 | 2025-05-07 14:10 | 2025-05-07 14:10
Feature | Must | As an admin, I want to be able to upload vertical rectangle thumbnail to be shown | 1 | 5 | 0 | 0 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 6.75 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6.75 | 2025-05-04 02:28 | 2025-05-04 12:34 | 2025-05-08 09:53 | 2025-05-07 14:10 | 2025-05-08 09:53
Shopping cart and Check out
Feature | Could | As a user, I want to view the Nutri-Scores and labels for my shopping list so that I can make healthy choices. | 0.6 | 1 | 2 | 0.3 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.35 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.35 | 2025-05-04 05:27 | 2025-05-04 22:26 | 2025-05-08 16:00 | 2025-05-08 06:44 | 2025-05-08 16:00
Feature | Could | As a user, I want to see a nutritional information table for my shopping list so that I can evaluate my diet. | 0.6 | 1 | 2 | 0.3 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.35 | TRUE | [7 empty] | FALSE | [7 empty] | TRUE | [7 empty] | FALSE | 4.35 | 2025-05-04 08:26 | 2025-05-05 08:18 | 2025-05-08 22:07 | 2025-05-08 23:18 | 2025-05-08 23:18
Nutritional values and charactristic of meals and bags
Feature | Must | As a user, I want to access the detailed nutritional information of a meal so that I can assess if it meets my dietary needs. | 1.5 | 6 | 1.5 | 0.225 | 0 | 0 | 0.9 | 0.075 | 0 | 0.15 | 10.35 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 10.35 | 2025-05-05 05:19 | 2025-05-06 11:27 | 2025-05-10 16:56 | 2025-05-10 20:50 | 2025-05-10 20:50
Feature | Should | As a user, I want know the charactristic of a meal to beware if it is having specific features such as halal, gluten-free, ... | 1.9 | 8 | 1.5 | 0.225 | 0 | 0 | 1.14 | 0.095 | 0 | 0.19 | 13.05 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 13.05 | 2025-05-06 05:12 | 2025-05-06 18:51 | 2025-05-12 17:53 | 2025-05-11 09:15 | 2025-05-12 17:53
Feature | Must | As a user, I want to access the detailed nutritional information of a bag so that I can assess if it meets my dietary needs. | 0.9 | 3 | 1.5 | 0.225 | 0 | 0 | 0.54 | 0.045 | 0 | 0.09 | 6.3 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6.3 | 2025-05-06 14:09 | 2025-05-07 02:15 | 2025-05-13 12:14 | 2025-05-11 21:41 | 2025-05-13 12:14
Feature | Should | As a user, I want know the charactristic of a bag to beware if it is having specific features such as halal, gluten-free, ... | 1.1 | 4 | 1.5 | 0.225 | 0 | 0 | 0.66 | 0.055 | 0 | 0.11 | 7.65 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 7.65 | 2025-05-07 02:05 | 2025-05-07 09:39 | 2025-05-14 12:42 | 2025-05-12 10:06 | 2025-05-14 12:42
April 6 to May 1 |  | Epic 4: miscellaneous
Sprint 7 - April 6 to April 17 | [44 empty] | 103.29
Feedback on the admin panel
Feedback | Must | Make the market product list selectable via select boxes | 0 | 24 | 0 | 0 | 0 | 0 | 2.88 | 0.24 | 0 | 0.48 | 27.6 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 27.6 |  |  |  |  | 0
Feedback | Must | As an admin, I want to create/edit labels directly in bag/meal/product pages | 0 | 6 | 0 | 0 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 6.9 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6.9 |  |  |  |  | 0
Feedback | Must | As an admin, I want to see the categories based on their parent on the category overview page | 0 | 8 | 0 | 0 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 9.2 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 9.2 |  |  |  |  | 0
Feedback | Must | Nutritional value visibility in meal creation for admins. | 0 | 20 | 0 | 0 | 0 | 0 | 2.4 | 0.2 | 0 | 0.4 | 23 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 23 |  |  |  |  | 0
Feedback | Must | The navigation menu should be organized based on hierarchy | 0 | 4 | 0 | 0 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 4.6 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.6 |  |  |  |  | 0
Sprint 8 - April 21 to May 5 | [44 empty] | 45
Chore | Must | As a user, I want to redirect my shopping list to the AlbertHeijn web store so that I can complete my purchase. | 0 | 0 | 1 | 0 | 0 | 0 | 0.12 | 0.01 | 0 | 0.02 | 1.15 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 1.15 | 2025-05-04 08:26 | 2025-05-05 13:14 | 2025-05-08 22:07 | 2025-05-09 07:34 | 2025-05-09 07:34
Chore | Must | As a user, I want to redirect my shopping list to the Plus web store so that I can complete my purchase. | 0 | 0 | 1 | 0 | 0 | 0 | 0.12 | 0.01 | 0 | 0.02 | 1.15 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 1.15 | 2025-05-04 08:26 | 2025-05-05 18:11 | 2025-05-08 22:07 | 2025-05-09 15:51 | 2025-05-09 15:51
Chore | Must | As a user, I want to redirect my shopping list to the Jumbo web store so that I can complete my purchase. | 0 | 0 | 1 | 0 | 0 | 0 | 0.12 | 0.01 | 0 | 0.02 | 1.15 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 1.15 | 2025-05-04 08:26 | 2025-05-05 23:07 | 2025-05-08 22:07 | 2025-05-10 00:08 | 2025-05-10 00:08
Feature | Must | As a user, I want to have single market product pages so that I can see see the real data of each market product | 5.8 | 24 | 5 | 0.75 | 0 | 0 | 3.48 | 0.29 | 0 | 0.58 | 39.9 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 39.9 |  |  |  |  | 0
Feature | Must | As a user, I want to see the application in Dutch | 0.8 | 1 | 3 | 0.45 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 5.85 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 5.85 |  |  |  |  | 0
Feature | Must | As a user, I want to add meals and bags to my shopping cart and complete the flow of shopping | 3.6 | 16 | 2 | 0.3 | 0 | 0 | 2.16 | 0.18 | 0 | 0.36 | 24.6 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 24.6 |  |  |  |  | 0
Feature | Must | As a user, I want to be able to delete my account so that if I decide not to continue on the app I can remove my data | 1 | 3 | 2 | 0.3 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 7.05 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 7.05 |  |  |  |  | 0
Feature | Must | As a user/admin, I want to receive emails in neat template with Super Marty's color pallate | 1.6 | 6 | 2 | 0.3 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.1 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 11.1 |  |  |  |  | 0
Feature | Must | Adding tags/labels to products | 2.2 | 8 | 3 | 0.45 | 0 | 0 | 1.32 | 0.11 | 0 | 0.22 | 15.3 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 15.3 |  |  |  |  | 0
Feature | Must | As a user, I want to filter products/ meals, and bags with the labels attached to them | 3.4 | 3 | 14 | 2.1 | 0 | 0 | 2.04 | 0.17 | 0 | 0.34 | 25.05 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 25.05 |  |  |  |  | 0
Feature | Must | As an admin, I want to be able to skip the markets while creating product groups | 0.4 | 2 | 0 | 0 | 0 | 0 | 0.24 | 0.02 | 0 | 0.04 | 2.7 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 2.7 |  |  |  |  | 0
Feature | Must | As a user, I want to be able to start the check out process for Plus | 2.8 | 6 | 8 | 1.2 | 0 | 0 | 1.68 | 0.14 | 0 | 0.28 | 20.1 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 20.1 |  |  |  |  | 0
Feature | Should | As an admin, I want to define the order of appearance for product/bag/ meal categories | 1.6 | 3 | 5 | 0.75 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.55 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 11.55 |  |  |  |  | 0
Feature | Could | As a user, I want to have a profile page, in which I can manage my account details | 2 | 6 | 4 | 0.6 | 0 | 0 | 1.2 | 0.1 | 0 | 0.2 | 14.1 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 14.1 |  |  |  |  | 0
Feature | Could | Filters for product overview in the admin panel | 1 | 5 | 0 | 0 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 6.75 | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 6.75 |  |  |  |  | 0
Feature | Could | Separating minerals from fat, and energy, etc | 0.6 | 0 | 3 | 0.45 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.5 | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.5 |  |  |  |  | 0
Miscellaneous
Feature | Should | As a user, I want to provide information about my intolerances so that the platform can personalize my experience. | 0.6 |  | 3 | 0.45 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.5 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 4.5 | 2025-05-06 11:10 | 2025-05-06 21:19 | 2025-05-13 06:07 | 2025-05-11 13:24 | 2025-05-13 06:07
Feature | Should | As a user, I want to have a search bar so that I can find the products that I am looking for | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 11:10 | 2025-05-06 21:19 | 2025-05-13 06:07 | 2025-05-11 13:24 | 2025-05-13 06:07
Chore | Must | As a user, I want to see the application in Dutch | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 11:10 | 2025-05-06 21:19 | 2025-05-13 06:07 | 2025-05-11 13:24 | 2025-05-13 06:07
Feature | Must | As a user, I want to create a custom bag so that I can personalize my shopping experience with my preferred items. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 11:10 | 2025-05-06 21:19 | 2025-05-13 06:07 | 2025-05-11 13:24 | 2025-05-13 06:07
Feature | Should | As a user, I want to share my bag with others so that they can see and collaborate on my selected items. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 11:10 | 2025-05-06 21:19 | 2025-05-13 06:07 | 2025-05-11 13:24 | 2025-05-13 06:07
Feature | Must | As a user, I want to filter products based on the market so that I can see only the items available in my preferred store. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 11:10 | 2025-05-06 21:19 | 2025-05-13 06:07 | 2025-05-11 13:24 | 2025-05-13 06:07
Feature | Should | As a user, I want to receive personalized suggestions so that I can quickly find relevant products based on my preferences and shopping history. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 11:10 | 2025-05-06 21:19 | 2025-05-13 06:07 | 2025-05-11 13:24 | 2025-05-13 06:07
Feature | Must | As a user, I want to add items to my favorites so that I can easily access and purchase them later. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 11:10 | 2025-05-06 21:19 | 2025-05-13 06:07 | 2025-05-11 13:24 | 2025-05-13 06:07
Feature | Must | As a user, I want to save my custom bags so that I can reuse them for future shopping sessions. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 11:10 | 2025-05-06 21:19 | 2025-05-13 06:07 | 2025-05-11 13:24 | 2025-05-13 06:07
Feature | Should | As a user, I want to share a bag or meal in other apps and social media so that I can recommend products to friends and family. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 11:10 | 2025-05-06 21:19 | 2025-05-13 06:07 | 2025-05-11 13:24 | 2025-05-13 06:07
Feature | Should | As a user, I want to set minimum and maximum price ranges so that I can find products that fit within my budget. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 11:10 | 2025-05-06 21:19 | 2025-05-13 06:07 | 2025-05-11 13:24 | 2025-05-13 06:07
Feature | Must | As a user, I want to find the nearest market so that I can shop conveniently and reduce travel time. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 11:10 | 2025-05-06 21:19 | 2025-05-13 06:07 | 2025-05-11 13:24 | 2025-05-13 06:07
Feature | Should | As a user, I want to like, dislike, or rate bags/meals so that I can improve recommendations and help other users make better choices. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 11:10 | 2025-05-06 21:19 | 2025-05-13 06:07 | 2025-05-11 13:24 | 2025-05-13 06:07
Feature | Could | As a user, I want to filter products based on various criteria such as so that I can quickly find what I am looking for. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-06 11:10 | 2025-05-06 21:19 | 2025-05-13 06:07 | 2025-05-11 13:24 | 2025-05-13 06:07
Feedback | Must | As an admin, I want a section where I can create and manage non-food product packages, so that I can organize and sell non-food items separately from food-related products. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-07 02:05 | 2025-05-07 09:39 | 2025-05-14 12:42 | 2025-05-12 10:06 | 2025-05-14 12:42
Feedback | Must | As an admin, I want to input data for creating bags, including the number of days, number of people, and meal types, so that I can generate meal bags with the appropriate quantities for customers. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | 0 | 2025-05-07 02:05 | 2025-05-07 09:39 | 2025-05-14 12:42 | 2025-05-12 10:06 | 2025-05-14 12:42
Release of the Platform
Chore |  | Setup and configure live server | 0 | 12 | 12 | 0 | 0 | 0 | 2.88 | 0.24 | 0 | 0.48 | 27.6 | TRUE |  |  | 0.72 | 0.48 | 0.24 |  | 27.84 | TRUE |  |  | 0.96 | 0.72 | 0.48 |  | 28.56 | TRUE |  |  | 1.2 | 0.96 | 0.72 |  | 29.28 | TRUE | 27.6 | 2025-05-08 13:53 | 2025-05-09 20:52 | 2025-05-17 14:07 | 2025-05-16 13:28 | 2025-05-17 14:07 | 0
Chore |  | Setup application | 0 | 32 | 0 | 0 | 0 | 0 | 3.84 | 0.32 | 0 | 0.64 | 36.8 | TRUE |  |  | 0.96 | 0.64 | 0.32 |  | 37.12 | TRUE |  |  | 1.28 | 0.96 | 0.64 |  | 38.08 | TRUE |  |  | 1.6 | 1.28 | 0.96 |  | 39.04 | TRUE | 36.8 | 2025-05-12 13:22 | 2025-05-09 20:52 | 2025-05-25 17:52 | 2025-05-16 13:28 | 2025-05-25 17:52 | 0
Chore |  | Insert the base data | 0 | 12 | 0 | 0 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 13.8 | TRUE |  |  | 0.36 | 0.24 | 0.12 |  | 13.92 | TRUE |  |  | 0.48 | 0.36 | 0.24 |  | 14.28 | TRUE |  |  | 0.6 | 0.48 | 0.36 |  | 14.64 | TRUE | 13.8 | 2025-05-14 01:10 | 2025-05-09 20:52 | 2025-05-28 19:17 | 2025-05-16 13:28 | 2025-05-28 19:17 | 0
Chore |  | configure the monitoring and backup | 0 | 12 | 0 | 0 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 13.8 | TRUE |  |  | 0.36 | 0.24 | 0.12 |  | 13.92 | TRUE |  |  | 0.48 | 0.36 | 0.24 |  | 14.28 | TRUE |  |  | 0.6 | 0.48 | 0.36 |  | 14.64 | TRUE | 13.8 | 2025-05-15 12:59 | 2025-05-09 20:52 | 2025-05-31 20:42 | 2025-05-16 13:28 | 2025-05-31 20:42 | 0
| Must 58% Should 26% Could 16% | Total estimated time + risk margin of 15% | 140.76 | 774.525 | 284.625 | 40.6812 | 0 | 0 | 126.96 | 10.58 | 0 | 21.16 | 1398.6588 | 0 | 0.46 | 0.92 | 7.1415 | 2.116 | 1.058 | 5.842 | 279.3925 | 0 | 0 | 0 | 10.258 | 2.76 | 1.84 | 9.867 | 306.82 | 0 | 0 | 0 | 12.8225 | 3.68 | 2.76 | 13.156 | 314.5135 | 0 | 1398.6588 | 2432-01-04 10:11 | 2041-09-17 18:32 | 380218.8115 | 2036-11-02 11:50 | 336596.6315 | 1333.97
|  | Total remaining time | 72.68 | 377.775 | 169.625 | 30.6762 | 0 | 0 | 65.55 | 5.4625 | 0 | 10.925 | 732.2337 | 0 | 0.46 | 0.92 | 3.243 | 2.116 | 1.058 | 0.644 | 127.351 | 0 | 0 | 0 | 5.474 | 2.76 | 1.84 | 2.691 | 163.3 | 0 | 0 | 0 | 6.8425 | 3.68 | 2.76 | 3.588 | 167.4055 | 0 | 732.2337 |  |  |  |  | 334442
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE
[14 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE | [7 empty] | FALSE

## Test case scenarios
Super Marty ¦ Test Case Scenarios
Module | Scenario Description | Preconditions | Test Steps | Expected Result | Type
Authentication | User Registration – Successful Sign-Up | User is not logged in; no account exists. | 1. Navigate to Sign-Up page 2. Enter a valid email and password 3. Click 'Sign Up/Register' | Account is created and user is registered. | Positive
Authentication | User Registration – Email Already Registered | Email already exists in system. | 1. Navigate to Sign-Up page 2. Enter existing email and password 3. Submit form | Error: Email already in use | Negative
Authentication | User Registration – Invalid Email Format | None | 1. Enter 'user@@domain' as email 2. Submit | Validation error: Invalid email format | Validation
Authentication | User Registration – Weak Password | None | 1. Enter valid email and weak password 2. Submit | Validation error: Password too weak | Validation
Authentication | User Registration – Missing Required Fields | None | 1. Leave email or password blank 2. Submit | Validation errors shown | Validation
Authentication | User Login – Successful | User account exists | 1. Enter valid credentials 2. Submit | Login successful | Positive
Authentication | User Login – Incorrect Password | User exists | 1. Enter wrong password 2. Submit | Login denied with error | Negative
Authentication | User Login – Unregistered Email | Email not registered | 1. Enter unregistered email 2. Submit | Login denied with error | Negative
Authentication | Forgot Password – Registered Email | Email exists | 1. Submit password reset request | Password reset link sent | Positive
Authentication | Forgot Password – Unregistered Email | Email does not exist | 1. Submit password reset request | No reset sent or generic message | Negative
Authentication | Password Reset – Successful | Valid reset link | 1. Enter new password 2. Submit | Password updated | Positive
Authentication | Password Reset – Expired Link | Reset link expired | 1. Open expired link | Error shown, prompt to request again | Negative
Authentication | Account Deletion – User Initiated | User logged in | 1. Click delete account 2. Confirm | Account and data removed | Positive
Authentication | Post-Deletion Access | Account deleted | 1. Attempt login | Access denied | Edge
Product management | Daily Product Data Sync – All Markets | Scheduled sync time; APIs available | 1. Trigger sync 2. Monitor completion | Products updated from all 3 markets | Positive
Product management | Daily Sync – Partial Failure | One API unavailable | 1. Trigger sync with one failed API | Other markets update, one fails with log | Edge
Product management | Create Product Category (Top-Level) | Admin logged in | 1. Add category name 2. Save | Top-level category created | Positive
Product management | Create Nested Product Category | At least one category exists | 1. Choose parent 2. Add sub-category 3. Save | Sub-category created | Positive
Product management | Category Creation – Validation Errors | Admin on create form | 1. Leave name blank or duplicate 2. Save | Error shown for required or duplicate name | Validation
Product management | Navigate Category Hierarchy | Nested categories exist | 1. Click to expand parent category | Sub-categories shown | Positive
Product management | Product Grouping & Normalization | Equivalent products exist | 1. Run aggregation 2. View group result | Products grouped and normalized | Positive
Product management | Upload Product Image | Product group exists | 1. Upload valid image 2. Save | Image added to group | Positive
Product management | Upload Invalid Product Image | Admin editing product group | 1. Upload unsupported format 2. Save | Validation error shown | Validation
Product management | View Product Details (User) | Product group available | 1. Open product page | See NutriScore, nutrition, and comparisons | Positive
Product management | Add Product to Cart | User on product detail | 1. Choose store 2. Click add to cart | Product added under selected store | Positive
Product management | View Market-Specific Product Page | Multiple store listings available | 1. Click on specific market link | Market product page shown | Positive
Product management | Shopping Cart Grouping | Cart contains items from different stores | 1. View cart | Items grouped by store | Positive
Product management | Plus Market Checkout Flow | Cart has Plus items | 1. Checkout | Plus items checked out individually | Edge
Product management | Cart Persistence – Keep | Previous cart saved | 1. Relaunch app 2. Select keep cart | Cart restored | Edge
Product management | Cart Persistence – Discard | Previous cart saved | 1. Relaunch app 2. Select discard cart | Cart cleared | Edge
Bag management | Create Bag Category (Admin) | Admin logged in | 1. Open bag category panel 2. Enter name 3. Save | Category created | Positive
Bag management | Bag Category Creation – Validation | Admin on create form | 1. Leave name blank or duplicate 2. Save | Error shown for invalid name | Validation
Bag management | Create Bag (Admin) | Product groups and category exist | 1. Enter name 2. Add products 3. Assign category/label 4. Save | Bag created | Positive
Bag management | Create Bag – Missing Fields | Admin on create form | 1. Leave required fields empty 2. Save | Validation errors shown | Validation
Bag management | Assign Label to Bag | Labels exist | 1. Edit bag 2. Select label 3. Save | Label assigned to bag | Positive
Bag management | Attach Meal to Bag | Meals exist | 1. Edit bag 2. Attach meal 3. Save | Meal linked to bag | Positive
Bag management | Remove Attached Meal | Bag has a linked meal | 1. Edit bag 2. Remove meal 3. Save | Meal removed from bag | Edge
Bag management | View Bag Nutritional Info (Admin) | Bag has products with nutrition | 1. Open bag detail | Nutritional chart shown | Positive
Bag management | View Bag Details (User) | Published bag exists | 1. Open bag on user side | Contents, labels, nutrition, related meals shown | Positive
Bag management | Add Bag to Cart – Single Store | Bag and store data available | 1. Choose store 2. Add all items | All items added from that store | Positive
Bag management | Add Bag to Cart – Best Price | Bag has products | 1. Add with 'best price' option | Cheapest items per product added | Positive
Bag management | Partial Bag Add – Remove Item | Bag open in user view | 1. Deselect product 2. Add to cart | All except removed item added | Edge
Bag management | Related Meal Link (User) | Bag has related meal | 1. Click related meal | Navigates to meal page | Positive
Meal management | Create Meal (Admin) | Product items exist | 1. Enter name, recipe, ingredients 2. Save | Meal created | Positive
Meal management | Meal Creation – Missing Fields | Admin on create form | 1. Leave name or ingredients blank 2. Save | Validation errors shown | Validation
Meal management | Attach Label to Meal | Labels exist | 1. Assign label during meal creation 2. Save | Label added to meal | Positive
Meal management | Attach Bag to Meal | Bags exist | 1. Link bag to meal 2. Save | Bag associated with meal | Positive
Meal management | View Meal Nutritional Info (Admin) | Meal has ingredients with nutrition | 1. Open meal detail | Nutritional summary displayed | Positive
Meal management | View Meal Details (User) | Meal published | 1. Open meal on user side | Ingredients, steps, labels, nutrition shown | Positive
Meal management | Add Meal to Cart – All Ingredients | User on meal page | 1. Click 'Add All to Cart' | All ingredients added to cart | Positive
Meal management | Partial Meal Add – Remove Ingredient | Meal has optional ingredients | 1. Deselect one item 2. Add to cart | Selected ingredients added | Edge
Meal management | Related Bag Link (User) | Meal linked to bag | 1. Click on related bag | Navigates to bag page | Positive
Label management | Create New Label | Admin logged in | 1. Enter label name 2. Save | Label is created | Positive
Label management | Create Label – Empty Name | Admin on label creation page | 1. Leave name blank 2. Submit | Validation error: name required | Validation
Label management | Create Label – Duplicate Name | Label with same name exists | 1. Enter existing label name 2. Submit | Error shown for duplicate | Negative
Label management | Inline Label Creation | Admin creating product, bag or meal | 1. Type new label in label field 2. Create inline | Label added to list and assigned | Positive
Label management | Assign Label to Product | Label and product exist | 1. Edit product 2. Select label 3. Save | Product tagged with label | Positive
Label management | Assign Label to Meal/Bag | Label exists | 1. Edit meal or bag 2. Select label 3. Save | Label shown in item details | Positive
Label management | Filter Content by Label (User Side) | Items tagged with label | 1. Apply filter on user interface | Only tagged items shown | Positive
User anagement | Invite New Admin | Admin logged in | 1. Enter email 2. Send invite | Invitation sent | Positive
User anagement | Invite Admin – Invalid Email | On invite form | 1. Enter malformed email 2. Send | Validation error for email | Validation
User anagement | Invite Admin – Email Already in Use | Admin email exists | 1. Enter existing admin email 2. Send | Error: Already an admin | Negative
User anagement | Accept Invitation – Set Password | Valid invite link | 1. Open invite link 2. Set password | Admin account created | Positive
User anagement | Accept Invite – Weak Password | Valid invite link | 1. Set weak password 2. Submit | Validation error for password | Validation
User anagement | Accept Invite – Expired Link | Link expired or used | 1. Open link | Error: Link invalid/expired | Negative
User anagement | New Admin Login & Access | Password set via invite | 1. Login as new admin | Admin panel accessible | Positive
User anagement | Equal Permissions for Admins | Multiple admins exist | 1. Log in as any admin 2. Access admin features | All admins have same permissions | Positive
User anagement | Normal User Access to Admin | Non-admin user logged in | 1. Try to open admin panel | Access denied or redirected | Edge

## Epic management
SuperMarty project - Epics Management Checklist
✓ | Scope | Action | Type | Due Date | Assignee | Remark | Progress
| Epic 0 - Implementation |  |  | E0 - SP2 |  | E= Epic, SP= Sprint, Each SP= 2 weeks | 100%
TRUE |  | Define Owners and Contributors: Assign specific owners (e.g., PM, HM) for each item in the checklist for better management.
TRUE |  | Allocate the resources and roles for the project
TRUE |  | Define the project monthly budget and resources weekly budget and update it in the roadmap related tabs (Budgeting and resources)
TRUE |  | Send an email and inform the stakeholder about planned resources and budget of reserved hours of month
TRUE |  | Ask financial team to send the pre-invoice of the reserved resources of month before start
TRUE |  | Prepare project management tools (Jira, Bitrix workgroup), and drives (Google drive, and Bitrix drive), scrum online etc.
TRUE |  | Defining the decision maker stakeholdet, Introduce representatives
TRUE |  | Recieve stakeholder's final approval on contract, NL digital terms, etc
TRUE |  | Recieve stakeholder's final approval on the workflows and wireframes from project discovery
TRUE |  | Recieve stakeholder's final approval on the roadmap (feature list) of chosen plan and being aware any change request other than this list is a new feature and affects deadline and scope
TRUE |  | Assign the Agile coach for the stakholders to train
TRUE |  | Set a meeting to explain the Agile practices and resposibiltie to the stakeholder
TRUE |  | Explain Agile practices and responsibilities to the stakeholders; prepare email and video materials for more clarity.
TRUE |  | Prepare Agile Flow Agreement file: Including how we work, agile, stakeholders responsibility, the consequences of not participating and all other onboarding items that explained in the kickoff meeting and have a written agreement afterwards via Email.
TRUE |  | Recieve stakeholder's final approval on Agile method's details, their responsibilities and how we work
TRUE |  | Recieve stakeholder's final approval on knowing our support system: Importance of SLA and 3 months free support after launch. After that even the bugfixing will be under paid SLA
TRUE |  | Include design review sessions with stakeholders before the final approval of wireframes. Ensures that design aligns with business goals and stakeholder expectations before committing to development.
TRUE |  | Update the roadmap with onboarding and R&D time if it's missed
TRUE |  | Prepare/ update project roadmap file with the latest version of its template, make sure including the pre-development time, and onboarding to the file (Epic 0),Enter the due dates for epic 0 implementation and epi 1 prepration and implementation.
TRUE |  | Add project files list with their links in a message and pin it in the workgroup chat so it will be accesible easier for team
TRUE |  | Set a meeting with project discovery team to get introduced to project concept and the document structure to be onboarded, invite platform/enabling team
TRUE |  | All team to read the documents, check the designs and master the project
TRUE |  | Set a meeting with team and explain the epics and their goal, and define time budget, add design team for more collaboration
TRUE |  | Add task for the designer to prepare Design system (UI/UX)
TRUE |  | Design/update the user flow
TRUE |  | Setup project meetings and ceremonies such as Daily, Epic planning, Groomings and design reviews, Scrum pokers, Retrospectives and Budget review with finance
TRUE |  | Ask the enabling team to prepare infrastructure suggestions (server, storage, etc) and share with DevOps and team
TRUE |  | Email stakeholder with the needed server, storage, and other needed services with thier links to purchase
TRUE |  | Request DevOps team to set the Development environment and related configurations
TRUE |  | Define the technical infrastructure for the DevOps team: Needed services to be imstalled
TRUE |  | Prepare Servers and Tools: Provide server configurations, domains, and certificates (e.g., SSL) as needed for the project.
TRUE |  | Prepare GIT and repositories
TRUE |  | Gather the required standard in develop and structure and CI/CDs
TRUE |  | Prepare development environment and share with team
TRUE |  | Break roadmap features into epics with specific goals and values to deliver Suggestion: Instead of numbers, name the epics with their goals. i.e. Payment Epic
TRUE |  | Rewrite the roadmap items' titles as user stories
TRUE |  | Prioritize the features based on MoSCoW
TRUE |  | Present new roadmap to the platform/enabling team and revise based on their feedback
TRUE |  | Gather the required 3rd parties, requested subscription plan and pricing, from enabling team and email stakeholder to provide them
TRUE |  | Stakeholder to create account on the required third parties for us and enter their payment information then (e.g Mailer, Payment gateways, API providers)
TRUE |  | Define the contact point and responsible person in communication with 3rd parties
TRUE |  | Request DevOps team to set the staging environment
TRUE |  | Prepare staging environment and share with team
TRUE |  | Share staging server information with Stakeholder
TRUE |  | Update Epics Management Steps: Mark the items that are done, review and in case of need update the assignees, due date and write the remark
| Epic 3 - Preparation | [5 empty] | 45.45%
| Phase 1: Strategic Alignment (Initial Planning) | [5 empty] | 100%
TRUE |  | Define Epic Objectives: Clearly outline what the epic aims to achieve within the one-month timeline.
TRUE |  | Feature Prioritization: List features for the epic and prioritize them using the MoSCoW method.
TRUE |  | Stakeholder Alignment: Confirm that all stakeholders agree on the epic’s scope and deliverable feature list. |  | 2025-02-27
TRUE |  | Revise Feature List: Update the epic feature list based on stakeholder feedback if necessary. |  | 2025-02-27
TRUE |  | Dependencies Assessment: Identify any dependencies within or outside the epic to prevent blockers during execution. |  | 2025-02-27
FALSE
Phase 2: Requirement Gathering (Preparation)
FALSE |  | Stakeholder Discussions: Conduct concise sessions to gather detailed requirements specific to the epic. |  | 2025-03-05
TRUE |  | Review Documents: Read existing project documents, check designs, and master the project details.
TRUE |  | Define User Stories: Break down requirements into clear and actionable user stories with specific goals. |  | 2025-02-26
TRUE |  | Acceptance Criteria: Define testable acceptance criteria for each user story to ensure delivery readiness. |  | 2025-02-26
TRUE |  | Review User Stories: Review the userstories abd their ACs then comment your questions and suggested ACs to be reviewed and added. |  | 2025-02-27
FALSE |  | Create PRD: Draft a detailed Product Requirements Document (PRD) for stakeholder approval.
TRUE |  | Add Design Task: Assign design tasks for the design team based on the approved epic feature list.
FALSE |  | Compliance Review: Ensure any compliance (e.g., data security, accessibility) required for this epic is addressed.
FALSE
FALSE
FALSE
FALSE
Phase 3: Risk Management and Compliance (Early Assessment)
FALSE |  | Risk Identification: Highlight risks directly affecting the one-month delivery goal.
FALSE |  | Mitigation Plans: Prepare quick-win solutions for critical risks (e.g., resource availability, technical bottlenecks).
FALSE |  | Compliance Review: Ensure any compliance (e.g., data security, accessibility) required for this epic is addressed.
FALSE
FALSE
FALSE
FALSE
Phase 4: Technical Preparations (Pre-Execution)
FALSE |  | Feasibility Study: Conduct a quick assessment of technical feasibility for the planned deliverables.
FALSE |  | Architecture Review: Ensure the epic fits into the existing architecture with minimal adjustments.
FALSE |  | Infrastructure Definition: Involve Enabling team in case of need to prepare infrastructure suggestions or review team suggestions to make the final choice.
FALSE |  | Epic Discovery: Conduct required meetings review ACs, tech solutions to reach userstories goals, content and designs and define if any other requirment is still remained inorder to estimate the features.
TRUE |  | Announce Resource Needs: Inform the finance team about resource allocation, billable hours, and epic details.
FALSE
FALSE
Phase 5: Design and UX (Concurrent with Technical Preparations)
FALSE |  | Design System: Add a task for the designer to prepare the design system (UI/UX) for upcoming epic.
TRUE |  | Reserve Designer Time: Submit designer resource request.
TRUE |  | Wireframes or Mockups: Create lightweight designs for features (if applicable).
TRUE |  | Review Design: Provide feedback, finalize, and share designs with stakeholders, clearly communicating deadlines.
TRUE |  | Design Approval: Ask the technical team for approval on designs to ensure feasibility.
TRUE |  | Present Designs: Share the designs with stakeholders, ensuring clarity on deadlines and objectives.
TRUE |  | Stakeholder Approval: Ensuring that designes are meeting stakeholders requirments and objectives.
FALSE
FALSE
Phase 6: Epic Planning (Detailed Execution Planning)
FALSE
TRUE |  | Team alignment: Share the epic objective and prioritized features with the team and get their approval that they are inline to commit the Must Haves and Should haves |  | 2025-02-27
TRUE |  | Estimation: Estimate effort (story points or time) for all user stories to ensure they fit within the one-month timeframe
TRUE |  | Compare Velocity: Compare epics’ estimated points with the team’s velocity, removing low-priority tasks that don’t fit in the epic.
TRUE |  | Update Backlog: Update the backlog and draft your suggested sprints scopes for the sprint planning meetings. |  | 2025-02-27
TRUE |  | First Sprint Planning: Schedule and conduct the first sprint planning meeting for the epic, the plan of each member based on their velocity and time capacity should be finalized and comitted by the end of this meeting.
TRUE |  | Second Sprint Planning: Plan subsequent sprints within the epic to address remaining tasks, the plan of each member based on their velocity and time capacity should be finalized and comitted by the end of this meeting. |  | 2025-03-05
FALSE
FALSE
FALSE
Phase 7: Communication and Documentation (Ongoing Throughout)
TRUE |  | Kickoff Meeting: Align the team on the goals, scope, and timeline of the epic.
FALSE |  | Documentation: Keep requirements, user stories, and scope clearly documented for reference.
TRUE |  | Update Epics Management Steps: Mark the items that are done, review and in case of need update the assignees, due date and write the remark
FALSE
Epic 3 - Implementation
TRUE |  | Stakeholder Updates: Send emails informing stakeholders about planning progress, resources, and timelines.
TRUE |  | Update Epics Management Steps: Mark the items that are done, review and in case of need update the assignees, due date and write the remark
FALSE | Phase 8: Execution and Delivery
FALSE |  | Delivered Feature List: After the epic is complete, send the delivered feature list to stakeholders for approval or feedback. |  | 2025-03-16
FALSE |  | Feedback Deadline: If stakeholders do not provide feedback by the deadline, send an email clarifying that delayed feedback will not be addressed in the current scope. |  | 2025-04-06
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
| Epic 4 - Preparation |  |  | E0 - SP1 |  |  | 0%
| Phase 1: Strategic Alignment (Initial Planning) | [5 empty] | 0%
FALSE |  | Define Epic Objectives: Clearly outline what the epic aims to achieve within the one-month timeline. |  | 2025-03-16
FALSE |  | Feature Prioritization: List features for the epic and prioritize them using the MoSCoW method. |  | 2025-03-16
FALSE |  | Stakeholder Alignment: Confirm that all stakeholders agree on the epic’s scope and deliverable feature list. |  | 2025-03-17
FALSE |  | Revise Feature List: Update the epic feature list based on stakeholder feedback if necessary. |  | 2025-03-17
FALSE |  | Dependencies Assessment: Identify any dependencies within or outside the epic to prevent blockers during execution.
FALSE
Phase 2: Requirement Gathering (Preparation)
FALSE |  | Stakeholder Discussions: Conduct concise sessions to gather detailed requirements specific to the epic.
FALSE |  | Review Documents: Read existing project documents, check designs, and master the project details.
FALSE |  | Define User Stories: Break down requirements into clear and actionable user stories with specific goals.
FALSE |  | Acceptance Criteria: Define testable acceptance criteria for each user story to ensure delivery readiness.
FALSE |  | Review User Stories: Review the userstories abd their ACs then comment your questions and suggested ACs to be reviewed and added.
FALSE |  | Create PRD: Draft a detailed Product Requirements Document (PRD) for stakeholder approval.
FALSE |  | Add Design Task: Assign design tasks for the design team based on the approved epic feature list.
FALSE |  | Compliance Review: Ensure any compliance (e.g., data security, accessibility) required for this epic is addressed.
FALSE
FALSE
FALSE
FALSE
Phase 3: Risk Management and Compliance (Early Assessment)
FALSE |  | Risk Identification: Highlight risks directly affecting the one-month delivery goal.
FALSE |  | Mitigation Plans: Prepare quick-win solutions for critical risks (e.g., resource availability, technical bottlenecks).
FALSE |  | Compliance Review: Ensure any compliance (e.g., data security, accessibility) required for this epic is addressed.
FALSE
FALSE
FALSE
FALSE
Phase 4: Technical Preparations (Pre-Execution)
FALSE |  | Feasibility Study: Conduct a quick assessment of technical feasibility for the planned deliverables.
FALSE |  | Architecture Review: Ensure the epic fits into the existing architecture with minimal adjustments.
FALSE |  | Infrastructure Definition: Involve Enabling team in case of need to prepare infrastructure suggestions or review team suggestions to make the final choice.
FALSE |  | Epic Discovery: Conduct required meetings review ACs, tech solutions to reach userstories goals, content and designs and define if any other requirment is still remained inorder to estimate the features.
FALSE |  | Announce Resource Needs: Inform the finance team about resource allocation, billable hours, and epic details.
FALSE
FALSE
Phase 5: Design and UX (Concurrent with Technical Preparations)
FALSE |  | Design System: Add a task for the designer to prepare the design system (UI/UX) for upcoming epic.
FALSE |  | Reserve Designer Time: Submit designer resource request.
FALSE |  | Wireframes or Mockups: Create lightweight designs for features (if applicable).
FALSE |  | Review Design: Provide feedback, finalize, and share designs with stakeholders, clearly communicating deadlines.
FALSE |  | Design Approval: Ask the technical team for approval on designs to ensure feasibility.
FALSE |  | Present Designs: Share the designs with stakeholders, ensuring clarity on deadlines and objectives.
FALSE |  | Stakeholder Approval: Ensuring that designes are meeting stakeholders requirments and objectives.
FALSE
FALSE
Phase 6: Epic Planning (Detailed Execution Planning)
FALSE |  | Make sure epic consist of 40% Must haves, 40% should haves, 20% could haves
FALSE
FALSE |  | Team alignment: Share the epic objective and prioritized features with the team and get their approval that they are inline to commit the Must Haves and Should haves
FALSE |  | Estimation: Estimate effort (story points or time) for all user stories to ensure they fit within the one-month timeframe
FALSE |  | Compare Velocity: Compare epics’ estimated points with the team’s velocity, removing low-priority tasks that don’t fit in the epic.
FALSE |  | Update Backlog: Update the backlog and draft your suggested sprints scopes for the sprint planning meetings.
FALSE |  | First Sprint Planning: Schedule and conduct the first sprint planning meeting for the epic, the plan of each member based on their velocity and time capacity should be finalized and comitted by the end of this meeting.
FALSE |  | Second Sprint Planning: Plan subsequent sprints within the epic to address remaining tasks, the plan of each member based on their velocity and time capacity should be finalized and comitted by the end of this meeting.
FALSE
FALSE
FALSE
Phase 7: Communication and Documentation (Ongoing Throughout)
FALSE |  | Kickoff Meeting: Align the team on the goals, scope, and timeline of the epic.
FALSE |  | Documentation: Keep requirements, user stories, and scope clearly documented for reference.
FALSE |  | Update Epics Management Steps: Mark the items that are done, review and in case of need update the assignees, due date and write the remark
FALSE
| Epic 4 - Implementation |  |  | E1 - SP1, SP2
FALSE |  | Stakeholder Updates: Send emails informing stakeholders about planning progress, resources, and timelines.
FALSE |  | Update Epics Management Steps: Mark the items that are done, review and in case of need update the assignees, due date and write the remark
FALSE |  | Test Implemented Stories: Continuously test user stories during development to ensure quality.
FALSE |  | Sprint Report Meetings: Review progress and deliverables with the finance team during sprint reporting sessions.
| Epic 4 - Finalization |  |  | E1 - SP2, E2 - SP1
| Epic 5 - Preparation |  |  | E0 - SP1 |  |  | 35.71%
| Phase 1: Strategic Alignment (Initial Planning) | [5 empty] | 80%
TRUE |  | Define Epic Objectives: Clearly outline what the epic aims to achieve within the one-month timeline. | Meeting | 2025-04-10 | Product Manager
TRUE |  | Feature Prioritization: List features for the epic and prioritize them using the MoSCoW method. | Task | 2025-04-15 | Product Manager
TRUE |  | Stakeholder Alignment: Confirm that all stakeholders agree on the epic’s scope and deliverable feature list. | Meeting | 2025-04-15 | Product Manager
TRUE |  | Revise Feature List: Update the epic feature list based on stakeholder feedback if necessary. | Task | 2025-04-15 | Product Manager
FALSE |  | Dependencies Assessment: Identify any dependencies within or outside the epic to prevent blockers during execution.
FALSE
Phase 2: Requirement Gathering (Preparation)
TRUE |  | Stakeholder Discussions: Conduct concise sessions to gather detailed requirements specific to the epic. | Task | 2025-04-15 | Team
TRUE |  | Review Documents: Read existing project documents, check designs, and master the project details.
TRUE |  | Define User Stories: Break down requirements into clear and actionable user stories with specific goals. | Task | 2025-04-16 | Product Manager
TRUE |  | Acceptance Criteria: Define testable acceptance criteria for each user story to ensure delivery readiness. | Task | 2025-04-16 | Product Manager
TRUE |  | Review User Stories: Review the userstories abd their ACs then comment your questions and suggested ACs to be reviewed and added. | Task | 2025-04-17 | Team
FALSE |  | Create PRD: Draft a detailed Product Requirements Document (PRD) for stakeholder approval.
TRUE |  | Add Design Task: Assign design tasks for the design team based on the approved epic feature list. | Task | 2025-04-15 | Product Manager
FALSE |  | Compliance Review: Ensure any compliance (e.g., data security, accessibility) required for this epic is addressed.
FALSE
FALSE
FALSE
FALSE
Phase 3: Risk Management and Compliance (Early Assessment)
FALSE |  | Risk Identification: Highlight risks directly affecting the one-month delivery goal.
FALSE |  | Mitigation Plans: Prepare quick-win solutions for critical risks (e.g., resource availability, technical bottlenecks).
FALSE |  | Compliance Review: Ensure any compliance (e.g., data security, accessibility) required for this epic is addressed.
FALSE
FALSE
FALSE
FALSE
Phase 4: Technical Preparations (Pre-Execution)
FALSE |  | Feasibility Study: Conduct a quick assessment of technical feasibility for the planned deliverables.
FALSE |  | Architecture Review: Ensure the epic fits into the existing architecture with minimal adjustments.
FALSE |  | Infrastructure Definition: Involve Enabling team in case of need to prepare infrastructure suggestions or review team suggestions to make the final choice.
FALSE |  | Epic Discovery: Conduct required meetings review ACs, tech solutions to reach userstories goals, content and designs and define if any other requirment is still remained inorder to estimate the features.
TRUE |  | Announce Resource Needs: Inform the finance team about resource allocation, billable hours, and epic details. | Meeting | 2025-04-15 | Product Manager
FALSE
FALSE
Phase 5: Design and UX (Concurrent with Technical Preparations)
FALSE |  | Design System: Add a task for the designer to prepare the design system (UI/UX) for upcoming epic.
TRUE |  | Reserve Designer Time: Submit designer resource request. | Task | 2025-04-16 | Product Manager
FALSE |  | Wireframes or Mockups: Create lightweight designs for features (if applicable). | Task | 2025-04-24 | Design team
FALSE |  | Review Design: Provide feedback, finalize, and share designs with stakeholders, clearly communicating deadlines. | Task | 2025-04-24 | Product Manager
FALSE |  | Design Approval: Ask the technical team for approval on designs to ensure feasibility. | Task | 2025-04-24 | Product Manager
FALSE |  | Present Designs: Share the designs with stakeholders, ensuring clarity on deadlines and objectives. | Task | 2025-04-24 | Product Manager
FALSE |  | Stakeholder Approval: Ensuring that designes are meeting stakeholders requirments and objectives. | Task | 2025-04-24 | Product Manager
FALSE
FALSE
Phase 6: Epic Planning (Detailed Execution Planning)
FALSE |  | Make sure epic consist of 40% Must haves, 40% should haves, 20% could haves |  |  |  | Not applicable for epic 4 which is the sum up phase
FALSE
TRUE |  | Team alignment: Share the epic objective and prioritized features with the team and get their approval that they are inline to commit the Must Haves and Should haves | Task | 2025-04-16 | Product Manager
TRUE |  | Estimation: Estimate effort (story points or time) for all user stories to ensure they fit within the one-month timeframe | Task | 2025-04-20 | Product Manager
TRUE |  | Compare Velocity: Compare epics’ estimated points with the team’s velocity, removing low-priority tasks that don’t fit in the epic. | Task | 2025-04-20 | Product Manager
TRUE |  | Update Backlog: Update the backlog and draft your suggested sprints scopes for the sprint planning meetings. | Task | 2025-04-16 | Product Manager
TRUE |  | First Sprint Planning: Schedule and conduct the first sprint planning meeting for the epic, the plan of each member based on their velocity and time capacity should be finalized and comitted by the end of this meeting. | Meeting | 2025-04-20 | Product Manager, Team, Finance team , Design team
TRUE |  | Second Sprint Planning: Plan subsequent sprints within the epic to address remaining tasks, the plan of each member based on their velocity and time capacity should be finalized and comitted by the end of this meeting. | Meeting | 2025-04-20 | Product Manager, Team
FALSE
FALSE
FALSE
Phase 7: Communication and Documentation (Ongoing Throughout)
TRUE |  | Kickoff Meeting: Align the team on the goals, scope, and timeline of the epic. | Meeting | 2025-04-17 | Product Manager
FALSE |  | Documentation: Keep requirements, user stories, and scope clearly documented for reference.
TRUE |  | Update Epics Management Steps: Mark the items that are done, review and in case of need update the assignees, due date and write the remark | Task | 2025-04-23 | Product Manager
FALSE
| Epic 5 - Implementation |  |  | E1 - SP1, SP2
FALSE |  | Stakeholder Updates: Send emails informing stakeholders about planning progress, resources, and timelines. | Email | 2025-04-17 | Product Manager
TRUE |  | Update Epics Management Steps: Mark the items that are done, review and in case of need update the assignees, due date and write the remark | Task | 2025-04-16 | Product Manager
FALSE |  | Test Implemented Stories: Continuously test user stories during development to ensure quality. | Task | 2025-04-17 | Product Manager
FALSE |  | Sprint Report Meetings: Review progress and deliverables with the finance team during sprint reporting sessions. | Meeting | 2025-04-15 | Product Manager, Finance team
TRUE |  | Sprint Demo Meetings: Conduct sprint demos to showcase completed features and gather feedback. | Meeting | 2025-04-15 | Product Manager
FALSE |  | Delivered Feature List: After the epic is complete, send the delivered feature list to stakeholders for approval or feedback and set a deadline with them. | Email | 2025-05-08 | Product Manager
FALSE |  | Feedback Deadline: If stakeholders do not provide feedback by the deadline, send an email clarifying that delayed feedback will not be addressed in the current scope.
FALSE
FALSE |  | Actual tracked time: Fill up the all the tracked time on the roadmap, compare it with estimations, then share the reasults in your team retro
FALSE |  | Epic Report Meeting: Schedule a meeting with the finance team to review the entire epic’s deliverables, time, and cost.
FALSE |  | Financial Report: Prepare the financial report for the completed epic and share it with stakeholders and the finance team.
FALSE
Epic X - Launching Prepration
Stakholders Approval
FALSE |  | Recieve the emai from stakeholders that they reviewed and approve the project go live |  |  |  | Should be done before the official launch
Coming soon page
FALSE |  | Set a cooming soon page on the live URL |  |  |  | At least a week before launch
New Host
FALSE |  | Server configure |  |  |  | Time zone,service needed configuration(Docker-swarm-nginx-trafik-php-mysq-ansible-private networkl)
FALSE |  | Firewall setting |  |  |  | Port access+ limitation access
Migration
FALSE |  | Run migrations |  |  |  | It can be migration from another app, default values like country and time zone list etc.
Domain
FALSE |  | Move |  |  |  | Cloudflare
FALSE |  | TransIP
FALSE |  | Change record |  |  |  | Change records if the domain has been used on another app or website to the new one
Back up
FALSE |  | Back up storage |  |  |  | Configure and linked
FALSE |  | VM Back up size and duration |  |  |  | VM -1 month -latest keep
FALSE |  | DB Back up size and duration |  |  |  | DB (every hour+ very day- keep 1month hourly- 6month daily)
FALSE |  | Uploadfile (1 week keep)
Monitoring tools
FALSE |  | Sentry |  |  |  | Structure for checking the logs and prioritizing the bugs to be resolved
FALSE |  | Uptime robot |  |  |  | To monitor app up or down
FALSE |  | Grafana |  |  |  | Structure for checking the logs and prioritizing the bugs to be resolved
FALSE |  | Opserve |  |  |  | To monitor the app and server
Pipeline
FALSE |  | Deployment
FALSE |  | Revert to previous version
FALSE |  | Prod mode
Mail Servers
FALSE |  | Email Provider |  |  |  | Configure the correct mail sending application (Server, or external application)
FALSE |  | SMTP address |  |  |  | Ask stakeholder to Share their SMTP address to us
FALSE |  | Set it for each Sender |  |  |  | Set the shared SMTP address for sender email address
Browser support APP
FALSE |  | In which browsers should the application be supported
Performance test
FALSE |  | Test the performance of the live server |  |  |  | Check if there are unneeded Query's
Clean dammy data
FALSE |  | Remove all dummy data from the live server application
FALSE |  | All live server logs should be erased before going live
Cronjobs
FALSE |  | Check and test that cronjobs are up and running
Browsers
FALSE |  | Fav. icon and page title for browsers tab to be implemented
FALSE |  | Check the supported browsers
Third Party User
FALSE |  | Add Bugloos Account |  |  |  | Add an account on each third party that has been used for Bugloos and not use stakeholder admin account.
FALSE |  | Store credentials in VaultWarden
Project Bugloos Email
FALSE |  | Add new Bugloos email group |  |  |  | A new email address with the format project@bugloos.nl should be added as group and accessed project managers
Documentation
FALSE |  | Record instruction videos of the application
FALSE |  | Write a Technical document for help instructions on code explanation
FALSE |  | Write a Technical document for help instructions on devops tools
Service
FALSE |  | Docker |  |  |  | Service Install, Configure and Security
FALSE |  | Ansible |  |  |  | Service Install, Configure and Security
FALSE |  | PHP |  |  |  | Service Install, Configure and Security
FALSE |  | Trafik |  |  |  | Service Install, Configure and Security
FALSE |  | Nginx |  |  |  | Service Install, Configure and Security
FALSE |  | Mysql -MariDB |  |  |  | Service Install, Configure and Security
FALSE |  | Private Network |  |  |  | Service Install, Configure and Security
FALSE |  | Public network |  |  |  | Service Install, Configure and Security
FALSE |  | Firewall |  |  |  | Service Install, Configure and Security
FALSE |  | Update Epics Management Steps: Mark the items that are done, review and in case of need update the assignees, due date and write the remark
FALSE
FALSE
FALSE
FALSE |  | Budget review with finance
FALSE |  | Epic consist of 40% Must haves, 40% should haves, 20% could haves
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Team performance
SuperMarty project - Team performance
Team member | Performance |  | User story output per sprint in hours |  |  | Technical performance |  |  |  |  | Soft skill |  |  |  |  | Agile scrum performance |  |  |  | Comment
| Output | Quality | Estimated | Promised | Delivered | Work quality | Documentation | Testing | Teamwork | Being a leader | Communication | Core values | Work reports | Knowledge sharing | Conflict management | Daily standup | Retrospective | Sprint Demo | Scrum poker |  | Sonarqube issues
All sprint performance | 69.48% | 107.7% | 21.5 | 41.3333 | 40.75 | 91.67% | 100% | 90% | 118.8% | 103.6% | 110.4% | 107.1% | 97.22% | 103.6% | 109.4% | 100% | 100% | 116.7% | 102.4%
Mahsa Amiri |  | 102.4% | 19 |  |  | 75% | 100% | 100% | 100% | 100% | 133.3% | 100% | 100% | 100% | 125% | 100% | 100% | 100% | 100%
Javad Zaki |  | 100% | 7 |  |  |  | 100% |  | 100% | 100% | 100% | 100% |  | 100% | 100% |  |  |  | 100%
Komeyl Mohebbian | 20.21% | 150% | 47 | 28.25 | 28.25 |  |  |  | 150% |  | 150% |  |  |  | 150% |  |  | 150%
Alireza Ebrahimzadeh | 67.68% | 99.04% | 12 | 43.8333 | 36.75 | 100% | 100% | 50% | 137.5% | 125% | 75% | 100% | 83.33% | 100% | 100% | 100% | 100% |  | 116.7%
Maziar Gholami |  | 100% | 19 |  |  | 75% | 100% | 100% | 125% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Farzaneh Sadeghi |  | 100% | 12 |  |  | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100%
Vahid Sarhaddi |  | 100% | 12 |  |  | 100% | 100% | 100% | 100% | 100% | 75% | 100% | 100% | 125% | 100% | 100% | 100% |  | 100%
Nayyer Jafari |  |  | 0
Parya Ardalani |  |  | 47
Amin Mohabbat | 120.5% | 110.6% | 40 | 51.9167 | 57.25 | 100% | 100% | 100% | 137.5% | 100% | 150% | 150% | 100% | 100% | 100% | 100% | 100% |  | 100%
3 last sprint performance | 88.3% | 119% | 21.5 | 45.25 | 45.25 | 95% |  |  | 175% |  | 150% | 175% |  |  | 150% |  |  | 150% | 50%
Mahsa Amiri |  | 150% | 19 | [7 empty] | 150% |  |  |  | 150%
Javad Zaki |  |  | 7
Komeyl Mohebbian | 76.6% | 150% | 47 | 41.5 | 41.5 | [5 empty] | 150% |  |  |  | 150% |  |  | 150%
Alireza Ebrahimzadeh |  | 116.7% | 12 |  |  | 100% |  |  | 200% | [9 empty] | 50%
Maziar Gholami |  | 75% | 19 |  |  | 75%
Farzaneh Sadeghi |  | 100% | 12 |  |  | 100%
Vahid Sarhaddi |  | 100% | 12 |  |  | 100%
Nayyer Jafari |  |  | 0
Parya Ardalani |  |  | 47
Amin Mohabbat | 100% | 141.7% | 40 | 49 | 49 | 100% |  |  | 150% |  |  | 175%
Helper row | 69 |  | 91 |  |  | G | H | I | J | K | L | M | N | O | P | Q | R | S | T
Dec 29 - January 9 | Sprint nr: | 1
Mahsa Amiri |  | 112.5% |  |  |  | 100% H: As expected; 150% J: As expected; 150% K: As expected; 150% L: Very well; 175% M: As expected; 175% O: As expected; 175% P: As expected; 175% T: As expected | Farzaneh: Communication ¦ Ontime follow ups
Javad Zaki |  | 100% |  |  |  | 100% H: As expected; 150% J: As expected; 150% K: As expected; 150% L: As expected; 175% M: As expected; 175% O: As expected; 175% P: As expected; 175% T: As expected
Alireza Ebrahimzadeh |  | 120% |  | 58 |  |  | As expected |  | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected |  |  | Excellent | Mahsa: Scrum poker ¦ He spent quality time on adding ACs and added useful ACs
Amin Mohabbat |  | 120% |  | 40 |  |  | As expected |  | As expected | As expected | Very well | Very well | As expected | As expected | As expected | As expected |  |  | As expected | Mahsa: Communication ¦ On time communication and heads up when something did not go well, or he was requested to do something else Mahsa: Core values ¦ He worked at the weekend, when he understood there is the risk of not finishing the sprint tasks Alireza: Communication ¦ constructive brainstorming before going futher in every topics
Maziar Gholami |  | 112.5% |  |  |  | 100% H: As expected; 150% J: Very well; 150% K: As expected; 150% L: As expected; 175% M: As expected; 175% O: As expected; 175% P: As expected; 175% T: As expected | Mahsa: Teamwork ¦ Being pro-active, offering ideas and trying to suggest solutions based on team's need
Farzaneh Sadeghi |  | 100% |  |  |  | 100% H: As expected; 150% J: As expected; 150% K: As expected; 150% L: As expected; 175% M: As expected; 175% O: As expected; 175% P: As expected; 175% T: As expected
Vahid Sarhaddi |  | 100% |  |  |  | 100% H: As expected; 150% J: As expected; 150% K: As expected; 150% L: Below par; 175% M: As expected; 175% O: Very well; 175% P: As expected; 175% T: As expected | Farzaneh: Knowledge sharing ¦ Vahid is actively trying to share his experince Alireza: weak reaching out channels
Jan 12 - Jan23 | Sprint nr: | 2
Mahsa Amiri |  | 100% |  |  |  | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected
Maziar Gholami |  | 100% |  |  |  | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected
Amin Mohabbat | 0% | 115.4% |  | 63 | 63 | As expected | As expected | As expected | Very well | As expected | Very well | As expected | As expected | As expected | As expected | As expected | As expected |  | As expected | Mahsa: Communication ¦ He constantly keeps me updated and communicate problems on time Alireza: Teamwork ¦ He is happy with Amin's helping him while he was stuck in tasks
Alireza Ebrahimzadeh | 0% | 92.31% |  | 66.5 | 66.5 | As expected | As expected | Below par | As expected | Very well | Below par | As expected | As expected | As expected | As expected | As expected | As expected |  | As expected | Mahsa: Testing ¦ The tasks that were ready to test were not testable on the server. I was blocked in the very early stage. Javad : Communication ¦ Alireza, to help us stay ahead of any challenges, it would be beneficial if you could focus on proactively managing your tasks and identifying any potential risks earlier in the sprint. This will allow us more time to address them effectively and ensure a smooth and successful sprint completion. Mahsa: Being a leader ¦ He is proactive and is helping with offering solutions
Farzaneh Sadeghi |  | 100% |  |  |  | As expected | As expected |  | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected
Vahid Sarhaddi |  | 100% |  |  |  | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected | As expected
Jan 26 - Feb 6 | Sprint nr: | 3
Mahsa Amiri |  | 0% |  |  |  | 100% G: Below par | Komeyl: User stories lacked clarity and proper assets
Maziar Gholami |  | #DIV/0!
Amin Mohabbat |  | 200% |  |  |  | 150% J: Very well | Komeyl: I was very happy with Amin's follow ups and help
Alireza Ebrahimzadeh |  | 100% |  |  |  | 150% J: Very well; 175% N: Below par | Javad : Workreport > He submits work reports late or sometimes without sufficient and clear information. Amin: Alireza helped me so much for checkout
Farzaneh Sadeghi |  | #DIV/0!
Komeyl Mohebbian | [5 empty] | 150% J: Very well | Amin: Komeil was trying to follow up implemented APIs & aks any questions that had frequently
Feb 9 - Feb 20 | Sprint nr: | 4
Mahsa Amiri |  |  | 19 |  |  | 175% P: Very well | Alireza: As we had a messy sprint for me this time she could manage evethg wel to have a great confident in Supermarty, urbansofa and Complizy
Maziar Gholami |  |  | 19 |  |  | 100% G: Below par | Komeyl ¦ Work quality: Design spacing and sizing were not consistent. Some of the meal details were missing in single page.
Amin Mohabbat |  | 200% | 49 | 42.5 |  | 175% M: Very well | Alireza: As I couldn't participate too actively in this sprint Amin covered as mush as he could greatly by himself | 8
Alireza Ebrahimzadeh | 0% | 150% | 12 | 7 | 7 | 150% J: Excellent; 175% T: Below par | Javad ¦ Sprint Planning : ACs weren’t added on time, affecting estimation—timely updates and responsiveness to critical decisions are essential. Mahsa ¦ Teamwork: He is always here to help. Great supportiveness | 4
Komeyl Mohebbian |  | 200% | 41.5 | 30 | 30 | 175% S: Very well | Mahsa ¦ Sprint demo: He is proficient and good lecturer Amin ¦ Patience :D | -15
Farzaneh Sadeghi |  |  | 12
Vahid Sarhaddi |  |  | 12
Feb 23 - March 6 | Sprint nr: | 5
Mahsa Amiri | [5 empty] | 150% L: Very well; 175% P: Very well | We had effective communication about conflicts
Komeyl Mohebbian |  |  |  | 47 | 47 | 150% L: Very well; 175% P: Very well | We had effective communication about conflicts | 0
Amin Mohabbat |  |  |  | 56 | 56 | 150% J: Very well | Komeyl: Helped with seting up ngRok when server was down. Checked up to make sure everything works fine | -45
Maziar Gholami
Farzaneh Sadeghi
Vahid Sarhaddi
March 9 - 18 | Sprint nr: | 6
Mahsa Amiri
Komeyl Mohebbian |  |  |  | 36 | 36 | [15 empty] | -1
Amin Mohabbat |  |  |  | 42 | 42 | [15 empty] | 1
Vahid Sarhaddi
Maziar Gholami
Nayyer Jafari
April 6 - 17 | Sprint nr: | 7
Mahsa Amiri
Komeyl Mohebbian |  |  |  | 0 | 0 | [15 empty] | 0
Amin Mohabbat |  |  |  | 68 | 68 | 175% M: Excellent | Mahsa: Core values ¦ He truly is a team player. Dedicated and commited | 0
Maziar Gholami
Vahid Sarhaddi
Nayyer Jafari

## Initial roadmap
SuperMarty project - Roadmap MVP
User story / task | User story description | Project manager | Backend development | Frontend development | UI/UX design | Backend auto. testing | Frontend auto. testing | Technical (code) review | Performance testing | Security testing | Technical documentation | Total time | MVP | Backend auto. testing | Frontend auto. testing | Technical (code) review | Performance testing | Security testing | Technical documentation | Total Time | MMP | Backend auto. testing | Frontend auto. testing | Technical (code) review | Performance testing | Security testing | Technical documentation | Total Time | MLP | Backend auto. testing | Frontend auto. testing | Technical (code) review | Performance testing | Security testing | Technical documentation | Total Time | MAP | Estimated duriation | Backend req. delivery | Frontend req. delivery | Backend est. delivery | Frontend est. delivery | Estimated delivery date | Actual duration | Actual delivered date | Comment
Team communication & management activities
| Daily Stand Up - Scrum Poker - Retrospective - Sprint Demos, Other meetings 20% | [10 empty] | 483.39 | [7 empty] | 449.112 | [7 empty] | 419.99 | [7 empty] | 445.644 |  | 483.39 | [5 empty] | 48.62
Epic 1: Database and related services
Data gathering and database
Chore | Implement and update AlbertHeijn API scraper + fetching nutritional information | 0 | 32 | 1 | 0 | 0 | 0 | 3.96 | 0.33 | 0 | 0.66 | 37.95 | TRUE |  |  | 0.99 |  |  | 1.32 | 38.61 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 37.95 | 2025-05-03 23:29 | 2025-04-30 04:56 | 2025-05-08 03:46 | 2025-04-30 08:17 | 2025-05-08 03:46
Chore | Implement and update Picnic API scraper + fetching nutritional information | 0 | 32 | 0 | 0 | 0 | 0 | 3.84 | 0.32 | 0 | 0.64 | 36.8 | TRUE |  |  | 0.96 |  |  | 1.28 | 37.44 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 36.8 | 2025-05-07 22:58 | 2025-04-30 04:56 | 2025-05-16 07:31 | 2025-04-30 08:17 | 2025-05-16 07:31
Chore | Implement and update Jumbo web scraper + fetching nutritional information | 0 | 32 | 0 | 0 | 0 | 0 | 3.84 | 0.32 | 0 | 0.64 | 36.8 | TRUE |  |  | 0.96 |  |  | 1.28 | 37.44 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 36.8 | 2025-05-11 22:27 | 2025-04-30 04:56 | 2025-05-24 11:17 | 2025-04-30 08:17 | 2025-05-24 11:17
Chore | Implement and update plus web scraper + fetching nutritional information | 0 | 32 | 0 | 0 | 0 | 0 | 3.84 | 0.32 | 0 | 0.64 | 36.8 | TRUE |  |  | 0.96 |  |  | 1.28 | 37.44 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 36.8 | 2025-05-15 21:56 | 2025-04-30 04:56 | 2025-06-01 15:03 | 2025-04-30 08:17 | 2025-06-01 15:03
Chore | Implementing the infrastructure of scrapers (Python scrapers as a single service) | 0 | 12 | 0 | 0 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 13.8 | TRUE | 1.2 | 0 | 0.36 | 0.24 | 0.12 | 0.48 | 15.6 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 13.8 | 2025-05-17 09:44 | 2025-04-30 04:56 | 2025-06-04 16:27 | 2025-04-30 08:17 | 2025-06-04 16:27
Chore | Implementing database service to fetch and update products | 0 | 16 | 0 | 0 | 0 | 0 | 1.92 | 0.16 | 0 | 0.32 | 18.4 | TRUE | 1.6 | 0 | 0.48 | 0.32 | 0.16 | 0.64 | 20.8 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 18.4 | 2025-05-19 09:29 | 2025-04-30 04:56 | 2025-06-08 18:20 | 2025-04-30 08:17 | 2025-06-08 18:20
Chore | Implement an scraping service for fetching recipes from AH | 0 | 12 | 0 | 0 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 13.8 | FALSE | 1.2 | 0 | 0.36 | 0.24 | 0.12 | 0.48 | 15.6 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 13.8 | 2025-05-20 21:17 | 2025-04-30 04:56 | 2025-06-11 19:45 | 2025-04-30 08:17 | 2025-06-11 19:45
Chore | Database structure of recipes and meals | 0 | 8 | 0 | 0 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 9.2 | FALSE | 0.8 | 0 | 0.24 | 0.16 | 0.08 | 0.32 | 10.4 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 9.2 | 2025-05-21 21:09 | 2025-04-30 04:56 | 2025-06-13 20:41 | 2025-04-30 08:17 | 2025-06-13 20:41
Chore | Scraping servies to fetch and update recipes from AH | 0 | 8 | 0 | 0 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 9.2 | FALSE | 0.8 | 0 | 0.24 | 0.16 | 0.08 | 0.32 | 10.4 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 9.2 | 2025-05-22 21:02 | 2025-04-30 04:56 | 2025-06-15 21:38 | 2025-04-30 08:17 | 2025-06-15 21:38
Chore | Database structure to connect recipes to its related products | 0 | 5 | 0 | 0 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 5.75 | FALSE | 0.5 | 0 | 0.15 | 0.1 | 0.05 | 0.2 | 6.5 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 5.75 | 2025-05-23 11:57 | 2025-04-30 04:56 | 2025-06-17 04:13 | 2025-04-30 08:17 | 2025-06-17 04:13
Chore | Implement a service to merge same products in dataset | 0 | 24 | 0 | 0 | 0 | 0 | 2.88 | 0.24 | 0 | 0.48 | 27.6 | TRUE | 2.4 | 0 | 0.72 | 0.48 | 0.24 | 0.96 | 31.2 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 27.6 | 2025-05-26 11:33 | 2025-04-30 04:56 | 2025-06-23 07:02 | 2025-04-30 08:17 | 2025-06-23 07:02
Chore | Design the database of supermarket products | 0 | 24 | 0 | 0 | 0 | 0 | 2.88 | 0.24 | 0 | 0.48 | 27.6 | TRUE |  |  | 0.72 |  |  | 0.96 | 28.08 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 27.6 | 2025-05-29 11:10 | 2025-04-30 04:56 | 2025-06-29 09:51 | 2025-04-30 08:17 | 2025-06-29 09:51
Chore | Database migrations of backend application | 0 | 12 | 0 | 0 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 13.8 | TRUE | 1.2 | 0 | 0.36 | 0.24 | 0.12 | 0.48 | 15.6 | FALSE |  |  | 0.52 |  |  | 0.78 | 15.6 | FALSE |  |  | 0.65 |  |  | 1.04 | 15.99 | FALSE | 13.8 | 2025-05-30 22:59 | 2025-04-30 04:56 | 2025-07-02 11:16 | 2025-04-30 08:17 | 2025-07-02 11:16
Epic 2: Admin panel - Users
Authentication, authorization and profile
Chore | Implement admin dashboard basic structure | 0 | 0 | 8 | 0 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 9.2 | TRUE | 0 | 0.8 | 0.24 | 0.16 | 0.08 | 0.32 | 10.4 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 9.2 | 2025-05-30 22:59 | 2025-05-01 20:25 | 2025-07-02 11:16 | 2025-05-03 02:31 | 2025-07-02 11:16
Feature | Login as an admin | 1.4 | 3 | 4 | 0.6 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.05 | TRUE | 0.3 | 0.4 | 0.21 | 0.14 | 0.07 | 0.28 | 10.1 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 10.05 | 2025-05-31 07:56 | 2025-05-02 16:09 | 2025-07-03 05:37 | 2025-05-04 11:39 | 2025-07-03 05:37
Feature | Set password (for the first login or reset password) | 1.4 | 4 | 3 | 0.45 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 9.9 | TRUE | 0.4 | 0.3 | 0.21 | 0.14 | 0.07 | 0.28 | 9.85 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 9.9 | 2025-05-31 19:52 | 2025-05-03 06:57 | 2025-07-04 06:06 | 2025-05-05 12:29 | 2025-07-04 06:06
Feature | Forgot password | 1.2 | 3 | 3 | 0.45 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.55 | TRUE | 0.3 | 0.3 | 0.18 | 0.12 | 0.06 | 0.24 | 8.55 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 8.55 | 2025-06-01 04:49 | 2025-05-03 21:46 | 2025-07-05 00:27 | 2025-05-06 13:20 | 2025-07-05 00:27
Chore | Welcome and reset password emails | 0 | 4 | 0 | 0 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 4.6 | TRUE | 0.4 | 0 | 0.12 | 0.08 | 0.04 | 0.16 | 5.2 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 4.6 | 2025-06-01 16:45 | 2025-05-03 21:46 | 2025-07-06 00:55 | 2025-05-06 13:20 | 2025-07-06 00:55
Chore | Refresh tokens | 0 | 2 | 2 | 0 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 4.6 | TRUE | 0.2 | 0.2 | 0.12 | 0.08 | 0.04 | 0.16 | 5.2 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 4.6 | 2025-06-01 22:43 | 2025-05-04 07:38 | 2025-07-06 13:09 | 2025-05-07 05:53 | 2025-07-06 13:09
Feature | Update user profile | 2.6 | 5 | 8 | 1.2 | 0 | 0 | 1.56 | 0.13 | 0 | 0.26 | 18.75 | FALSE | 0.5 | 0.8 | 0.39 | 0.26 | 0.13 | 0.52 | 18.9 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 18.75 | 2025-06-02 13:38 | 2025-05-05 23:07 | 2025-07-07 19:44 | 2025-05-10 00:08 | 2025-07-07 19:44
Feature | Logout | 1.2 | 3 | 3 | 0.45 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.55 | TRUE | 0.3 | 0.3 | 0.18 | 0.12 | 0.06 | 0.24 | 8.55 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 8.55 | 2025-06-02 22:35 | 2025-05-06 13:55 | 2025-07-08 14:05 | 2025-05-11 00:59 | 2025-07-08 14:05
Feature | Two factor authentication | 2 | 5 | 5 | 0.75 | 0 | 0 | 1.2 | 0.1 | 0 | 0.2 | 14.25 | FALSE | 0.5 | 0.5 | 0.3 | 0.2 | 0.1 | 0.4 | 14.25 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 14.25 | 2025-06-03 13:30 | 2025-05-07 14:35 | 2025-07-09 20:41 | 2025-05-12 18:23 | 2025-07-09 20:41
Chore | Authorization for admin users with different roles | 0 | 8 | 5 | 0 | 0 | 0 | 1.56 | 0.13 | 0 | 0.26 | 14.95 | FALSE | 0.8 | 0.5 | 0.39 | 0.26 | 0.13 | 0.52 | 16.9 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 14.95 | 2025-06-04 13:23 | 2025-05-08 15:16 | 2025-07-11 21:37 | 2025-05-14 11:47 | 2025-07-11 21:37
Feature | Admin dashboard header and layout | 1 | 0 | 5 | 0.75 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 7.5 | TRUE | 0 | 0.5 | 0.15 | 0.1 | 0.05 | 0.2 | 7.75 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 7.5 | 2025-06-04 13:23 | 2025-05-09 15:56 | 2025-07-11 21:37 | 2025-05-16 05:11 | 2025-07-11 21:37
Users management
Feature | Users overview (role, name and other information) | 1.8 | 4 | 5 | 0.75 | 0 | 0 | 1.08 | 0.09 | 0 | 0.18 | 12.9 | TRUE | 0.4 | 0.5 | 0.27 | 0.18 | 0.09 | 0.36 | 12.95 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 12.9 | 2025-06-05 01:19 | 2025-05-10 16:37 | 2025-07-12 22:05 | 2025-05-17 22:35 | 2025-07-12 22:05
Feature | Search, sort and filter users | 1.4 | 4 | 3 | 0.45 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 9.9 | TRUE | 0.4 | 0.3 | 0.21 | 0.14 | 0.07 | 0.28 | 9.85 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 9.9 | 2025-06-05 13:15 | 2025-05-11 07:25 | 2025-07-13 22:33 | 2025-05-18 23:26 | 2025-07-13 22:33
Feature | Add a new user | 2.4 | 6 | 6 | 0.9 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 17.1 | TRUE | 0.6 | 0.6 | 0.36 | 0.24 | 0.12 | 0.48 | 17.1 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 17.1 | 2025-06-06 07:09 | 2025-05-12 13:02 | 2025-07-15 11:16 | 2025-05-21 01:07 | 2025-07-15 11:16
Feature | Edit a user and change role | 1.2 | 3 | 3 | 0.45 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.55 | TRUE | 0.3 | 0.3 | 0.18 | 0.12 | 0.06 | 0.24 | 8.55 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 8.55 | 2025-06-06 16:06 | 2025-05-13 03:50 | 2025-07-16 05:37 | 2025-05-22 01:57 | 2025-07-16 05:37
Feature | View a user (user activity, liked bags, preferences and ...) | 4 | 8 | 12 | 1.8 | 0 | 0 | 2.4 | 0.2 | 0 | 0.4 | 28.8 | TRUE | 0.8 | 1.2 | 0.6 | 0.4 | 0.2 | 0.8 | 29 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 28.8 | 2025-06-07 15:58 | 2025-05-15 15:03 | 2025-07-18 06:33 | 2025-05-26 05:19 | 2025-07-18 06:33
Feature | User roles overview | 1.4 | 3 | 4 | 0.6 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.05 | FALSE | 0.3 | 0.4 | 0.21 | 0.14 | 0.07 | 0.28 | 10.1 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 10.05 | 2025-06-08 00:55 | 2025-05-16 10:47 | 2025-07-19 00:55 | 2025-05-27 14:26 | 2025-07-19 00:55
Feature | Define a custom role | 1.8 | 4 | 5 | 0.75 | 0 | 0 | 1.08 | 0.09 | 0 | 0.18 | 12.9 | FALSE | 0.4 | 0.5 | 0.27 | 0.18 | 0.09 | 0.36 | 12.95 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 12.9 | 2025-06-08 12:52 | 2025-05-17 11:28 | 2025-07-20 01:23 | 2025-05-29 07:51 | 2025-07-20 01:23
Feature | View and edit role | 1 | 2 | 3 | 0.45 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 7.2 | FALSE | 0.2 | 0.3 | 0.15 | 0.1 | 0.05 | 0.2 | 7.25 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 7.2 | 2025-06-08 18:50 | 2025-05-18 02:16 | 2025-07-20 13:37 | 2025-05-30 08:41 | 2025-07-20 13:37
Feature | Implementation of feedback and change requests | 6.4 | 16 | 16 | 2.4 | 0 | 0 | 3.84 | 0.32 | 0 | 0.64 | 45.6 | TRUE | 1.6 | 1.6 | 0.96 | 0.64 | 0.32 | 1.28 | 45.6 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 45.6 | 2025-06-10 18:34 | 2025-05-21 09:13 | 2025-07-24 15:30 | 2025-06-04 21:10 | 2025-07-24 15:30
Epic 3: Admin panel - Products, supermarkets and categories
Products management
Feature | Implementing grid component structure | 1 | 0 | 5 | 0.75 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 7.5 | TRUE | 0 | 0.5 | 0.15 | 0.1 | 0.05 | 0.2 | 7.75 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 7.5 | 2025-06-10 18:34 | 2025-05-22 09:54 | 2025-07-24 15:30 | 2025-06-06 14:34 | 2025-07-24 15:30
Feature | Products overview | 1.6 | 0 | 8 | 1.2 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 12 | TRUE | 0 | 0.8 | 0.24 | 0.16 | 0.08 | 0.32 | 12.4 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 12 | 2025-06-10 18:34 | 2025-05-24 01:23 | 2025-07-24 15:30 | 2025-06-09 08:49 | 2025-07-24 15:30
Feature | Products search, sort and filter | 1.4 | 3 | 4 | 0.6 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.05 | TRUE | 0.3 | 0.4 | 0.21 | 0.14 | 0.07 | 0.28 | 10.1 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 10.05 | 2025-06-11 03:31 | 2025-05-24 21:07 | 2025-07-25 09:51 | 2025-06-10 17:56 | 2025-07-25 09:51
Feature | Edit a product (change categories, uploud image and ...) | 1.4 | 4 | 3 | 0.45 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 9.9 | TRUE | 0.4 | 0.3 | 0.21 | 0.14 | 0.07 | 0.28 | 9.85 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 9.9 | 2025-06-11 15:27 | 2025-05-25 11:55 | 2025-07-26 10:19 | 2025-06-11 18:47 | 2025-07-26 10:19
Feature | Publish and unpublish a product | 1.2 | 3 | 3 | 0.45 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.55 | TRUE | 0.3 | 0.3 | 0.18 | 0.12 | 0.06 | 0.24 | 8.55 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 8.55 | 2025-06-12 00:24 | 2025-05-26 02:43 | 2025-07-27 04:40 | 2025-06-12 19:37 | 2025-07-27 04:40
Feature | View a product details (nutri-score, categories, images and ..) | 0.8 | 4 | 0 | 0 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 5.4 | TRUE | 0.4 | 0 | 0.12 | 0.08 | 0.04 | 0.16 | 5.2 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 5.4 | 2025-06-12 12:21 | 2025-05-26 02:43 | 2025-07-28 05:08 | 2025-06-12 19:37 | 2025-07-28 05:08
Supermarkets management
Feature | Supermarkets overview | 1.8 | 4 | 5 | 0.75 | 0 | 0 | 1.08 | 0.09 | 0 | 0.18 | 12.9 | FALSE | 0.4 | 0.5 | 0.27 | 0.18 | 0.09 | 0.36 | 12.95 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 12.9 | 2025-06-13 00:17 | 2025-05-27 03:24 | 2025-07-29 05:37 | 2025-06-14 13:01 | 2025-07-29 05:37
Feature | Search, sort and filter supermarkets | 1.4 | 4 | 3 | 0.45 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 9.9 | FALSE | 0.4 | 0.3 | 0.21 | 0.14 | 0.07 | 0.28 | 9.85 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 9.9 | 2025-06-13 12:13 | 2025-05-27 18:12 | 2025-07-30 06:05 | 2025-06-15 13:52 | 2025-07-30 06:05
Feature | Add a new supermarket | 2 | 4 | 6 | 0.9 | 0 | 0 | 1.2 | 0.1 | 0 | 0.2 | 14.4 | FALSE | 0.4 | 0.6 | 0.3 | 0.2 | 0.1 | 0.4 | 14.5 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 14.4 | 2025-06-14 00:09 | 2025-05-28 23:49 | 2025-07-31 06:33 | 2025-06-17 15:33 | 2025-07-31 06:33
Feature | View and edit a supermarket (address and geolocation on map) | 2.4 | 4 | 8 | 1.2 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 17.4 | FALSE | 0.4 | 0.8 | 0.36 | 0.24 | 0.12 | 0.48 | 17.6 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 17.4 | 2025-06-14 12:05 | 2025-05-30 15:17 | 2025-08-01 07:01 | 2025-06-20 09:48 | 2025-08-01 07:01
Feature | Import supermarkets via CSV file | 2.6 | 8 | 5 | 0.75 | 0 | 0 | 1.56 | 0.13 | 0 | 0.26 | 18.3 | FALSE | 0.8 | 0.5 | 0.39 | 0.26 | 0.13 | 0.52 | 18.15 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 18.3 | 2025-06-15 11:57 | 2025-05-31 15:58 | 2025-08-03 07:58 | 2025-06-22 03:12 | 2025-08-03 07:58
Category management
Feature | Category overview (life styles, diets, product categories and ...) | 1.8 | 3 | 6 | 0.9 | 0 | 0 | 1.08 | 0.09 | 0 | 0.18 | 13.05 | TRUE | 0.3 | 0.6 | 0.27 | 0.18 | 0.09 | 0.36 | 13.2 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 13.05 | 2025-06-15 20:54 | 2025-06-01 21:34 | 2025-08-04 02:19 | 2025-06-24 04:53 | 2025-08-04 02:19
Feature | Search, sort and filter user categories | 1.6 | 4 | 4 | 0.6 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.4 | TRUE | 0.4 | 0.4 | 0.24 | 0.16 | 0.08 | 0.32 | 11.4 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 11.4 | 2025-06-16 08:50 | 2025-06-02 17:19 | 2025-08-05 02:47 | 2025-06-25 14:00 | 2025-08-05 02:47
Feature | Add a new category | 2 | 4 | 6 | 0.9 | 0 | 0 | 1.2 | 0.1 | 0 | 0.2 | 14.4 | TRUE | 0.4 | 0.6 | 0.3 | 0.2 | 0.1 | 0.4 | 14.5 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 14.4 | 2025-06-16 20:47 | 2025-06-03 22:55 | 2025-08-06 03:15 | 2025-06-27 15:41 | 2025-08-06 03:15
Feature | View and edit a category (upload image, edit name and ...) | 2.4 | 4 | 8 | 1.2 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 17.4 | TRUE | 0.4 | 0.8 | 0.36 | 0.24 | 0.12 | 0.48 | 17.6 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 17.4 | 2025-06-17 08:43 | 2025-06-05 14:24 | 2025-08-07 03:44 | 2025-06-30 09:56 | 2025-08-07 03:44
Feature | Remove a category and assign to another category | 1.4 | 3 | 4 | 0.6 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.05 | TRUE | 0.3 | 0.4 | 0.21 | 0.14 | 0.07 | 0.28 | 10.1 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 10.05 | 2025-06-17 17:40 | 2025-06-06 10:08 | 2025-08-07 22:05 | 2025-07-01 19:03 | 2025-08-07 22:05
Feature | Implementation of feedback and change requests | 6.4 | 16 | 16 | 2.4 | 0 | 0 | 3.84 | 0.32 | 0 | 0.64 | 45.6 | TRUE | 1.6 | 1.6 | 0.96 | 0.64 | 0.32 | 1.28 | 45.6 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 45.6 | 2025-06-19 17:24 | 2025-06-09 17:06 | 2025-08-11 23:58 | 2025-07-07 07:32 | 2025-08-11 23:58
Epic 4: Admin panel - Recipes, shopping bags and labels
Meal (recipe) management
Feature | Meals overview + implementing tabs | 1.8 | 3 | 6 | 0.9 | 0 | 0 | 1.08 | 0.09 | 0 | 0.18 | 13.05 | TRUE | 0.3 | 0.6 | 0.27 | 0.18 | 0.09 | 0.36 | 13.2 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 13.05 | 2025-06-20 02:21 | 2025-06-10 22:42 | 2025-08-12 18:19 | 2025-07-09 09:13 | 2025-08-12 18:19
Feature | Meals search, sort and filter | 1.6 | 4 | 4 | 0.6 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.4 | TRUE | 0.4 | 0.4 | 0.24 | 0.16 | 0.08 | 0.32 | 11.4 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 11.4 | 2025-06-20 14:18 | 2025-06-11 18:27 | 2025-08-13 18:47 | 2025-07-10 18:21 | 2025-08-13 18:47
Feature | Add a new meal by existing products | 3.2 | 8 | 8 | 1.2 | 0 | 0 | 1.92 | 0.16 | 0 | 0.32 | 22.8 | TRUE | 0.8 | 0.8 | 0.48 | 0.32 | 0.16 | 0.64 | 22.8 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 22.8 | 2025-06-21 14:10 | 2025-06-13 09:55 | 2025-08-15 19:43 | 2025-07-13 12:35 | 2025-08-15 19:43
Feature | Edit and remove a meal | 1.4 | 3 | 4 | 0.6 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.05 | TRUE | 0.3 | 0.4 | 0.21 | 0.14 | 0.07 | 0.28 | 10.1 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 10.05 | 2025-06-21 23:07 | 2025-06-14 05:40 | 2025-08-16 14:04 | 2025-07-14 21:42 | 2025-08-16 14:04
Feature | View a meal and its nutritinal information (+ calculate total calorie of a meal) | 2.6 | 8 | 5 | 0.75 | 0 | 0 | 1.56 | 0.13 | 0 | 0.26 | 18.3 | TRUE | 0.8 | 0.5 | 0.39 | 0.26 | 0.13 | 0.52 | 18.15 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 18.3 | 2025-06-22 22:59 | 2025-06-15 06:20 | 2025-08-18 15:01 | 2025-07-16 15:07 | 2025-08-18 15:01
Feature | Adding label and categories to a meal | 1.2 | 3 | 3 | 0.45 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.55 | TRUE | 0.3 | 0.3 | 0.18 | 0.12 | 0.06 | 0.24 | 8.55 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 8.55 | 2025-06-23 07:56 | 2025-06-15 21:09 | 2025-08-19 09:22 | 2025-07-17 15:57 | 2025-08-19 09:22
Feature | Define a new label or category in update meal form | 1.4 | 3 | 4 | 0.6 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.05 | TRUE | 0.3 | 0.4 | 0.21 | 0.14 | 0.07 | 0.28 | 10.1 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 10.05 | 2025-06-23 16:53 | 2025-06-16 16:53 | 2025-08-20 03:43 | 2025-07-19 01:04 | 2025-08-20 03:43
Shopping bags
Feature | Shopping bags overview | 1.8 | 3 | 6 | 0.9 | 0 | 0 | 1.08 | 0.09 | 0 | 0.18 | 13.05 | TRUE | 0.3 | 0.6 | 0.27 | 0.18 | 0.09 | 0.36 | 13.2 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 13.05 | 2025-06-24 01:50 | 2025-06-17 22:29 | 2025-08-20 22:04 | 2025-07-21 02:45 | 2025-08-20 22:04
Feature | Bags search, sort and filter | 1.6 | 4 | 4 | 0.6 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.4 | TRUE | 0.4 | 0.4 | 0.24 | 0.16 | 0.08 | 0.32 | 11.4 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 11.4 | 2025-06-24 13:46 | 2025-06-18 18:14 | 2025-08-21 22:33 | 2025-07-22 11:53 | 2025-08-21 22:33
Feature | Add a new shopping bag by existing products | 3.2 | 8 | 8 | 1.2 | 0 | 0 | 1.92 | 0.16 | 0 | 0.32 | 22.8 | TRUE | 0.8 | 0.8 | 0.48 | 0.32 | 0.16 | 0.64 | 22.8 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 22.8 | 2025-06-25 13:39 | 2025-06-20 09:43 | 2025-08-23 23:29 | 2025-07-25 06:07 | 2025-08-23 23:29
Feature | Edit and remove a shopping bag | 1.4 | 3 | 4 | 0.6 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.05 | TRUE | 0.3 | 0.4 | 0.21 | 0.14 | 0.07 | 0.28 | 10.1 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 10.05 | 2025-06-25 22:36 | 2025-06-21 05:27 | 2025-08-24 17:50 | 2025-07-26 15:15 | 2025-08-24 17:50
Feature | View a bag and its nutritinal information (+ calculate total calorie of a bag) | 2.6 | 8 | 5 | 0.75 | 0 | 0 | 1.56 | 0.13 | 0 | 0.26 | 18.3 | TRUE | 0.8 | 0.5 | 0.39 | 0.26 | 0.13 | 0.52 | 18.15 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 18.3 | 2025-06-26 22:28 | 2025-06-22 06:07 | 2025-08-26 18:47 | 2025-07-28 08:39 | 2025-08-26 18:47
Feature | Adding label and categories to a shopping bag | 1.2 | 3 | 3 | 0.45 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.55 | TRUE | 0.3 | 0.3 | 0.18 | 0.12 | 0.06 | 0.24 | 8.55 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 8.55 | 2025-06-27 07:25 | 2025-06-22 20:56 | 2025-08-27 13:08 | 2025-07-29 09:29 | 2025-08-27 13:08
Feature | Define a new label or category in update shopping bag form | 1.4 | 3 | 4 | 0.6 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.05 | TRUE | 0.3 | 0.4 | 0.21 | 0.14 | 0.07 | 0.28 | 10.1 | FALSE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | FALSE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | FALSE | 10.05 | 2025-06-27 16:22 | 2025-06-23 16:40 | 2025-08-28 07:29 | 2025-07-30 18:37 | 2025-08-28 07:29
MVP launch
Epic 5: Mobile app main functionalities
Sign up end users
Chore | Implement mobile application basic UI elements | 0 | 0 | 8 | 0 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 9.2 | FALSE | 0 | 0.8 | 0.24 | 0.16 | 0.08 | 0.32 | 10.4 | TRUE | 0 | 1.2 | 0.32 | 0.24 | 0.16 | 0.48 | 11.2 | TRUE | 0 | 1.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12 | TRUE | 9.2 | 2025-04-30 | 2025-05-01 15:29 | 2025-04-30 | 2025-05-02 18:15 | 2025-05-02 18:15
Chore | Sign up pages layout | 0 | 0 | 6 | 0 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 6.9 | FALSE | 0 | 0.6 | 0.18 | 0.12 | 0.06 | 0.24 | 9.3 | TRUE | 0 | 0.9 | 0.24 | 0.18 | 0.12 | 0.36 | 9.9 | TRUE | 0 | 1.2 | 0.3 | 0.24 | 0.18 | 0.48 | 10.5 | TRUE | 6.9 | 2025-04-30 | 2025-05-02 21:05 | 2025-04-30 | 2025-05-04 19:56 | 2025-05-04 19:56
Feature | Getting name, last name and email in first page | 1.8 | 3 | 6 | 0.9 | 0 | 0 | 1.08 | 0.09 | 0 | 0.18 | 13.05 | FALSE | 0.3 | 0.6 | 0.27 | 0.18 | 0.09 | 0.36 | 13.2 | TRUE | 0.45 | 0.9 | 0.36 | 0.27 | 0.18 | 0.54 | 14.1 | TRUE | 0.6 | 1.2 | 0.45 | 0.36 | 0.27 | 0.72 | 15 | TRUE | 13.05 | 2025-04-30 08:57 | 2025-05-04 02:42 | 2025-04-30 18:21 | 2025-05-06 21:37 | 2025-05-06 21:37
Feature | Getting user gender | 1.2 | 2 | 4 | 0.6 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.7 | FALSE | 0.2 | 0.4 | 0.18 | 0.12 | 0.06 | 0.24 | 8.8 | TRUE | 0.3 | 0.6 | 0.24 | 0.18 | 0.12 | 0.36 | 9.4 | TRUE | 0.4 | 0.8 | 0.3 | 0.24 | 0.18 | 0.48 | 10 | TRUE | 8.7 | 2025-04-30 14:55 | 2025-05-04 22:26 | 2025-05-01 06:35 | 2025-05-08 06:44 | 2025-05-08 06:44
Feature | Getting user interests (Healthy life, Gym life ...) | 2.4 | 6 | 6 | 0.9 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 17.1 | FALSE | 0.6 | 0.6 | 0.36 | 0.24 | 0.12 | 0.48 | 17.1 | TRUE | 0.9 | 0.9 | 0.48 | 0.36 | 0.24 | 0.72 | 18.3 | TRUE | 1.2 | 1.2 | 0.6 | 0.48 | 0.36 | 0.96 | 19.5 | TRUE | 17.1 | 2025-05-01 08:49 | 2025-05-06 04:03 | 2025-05-02 19:18 | 2025-05-10 08:25 | 2025-05-10 08:25
Feature | Getting user diet | 2.2 | 5 | 6 | 0.9 | 0 | 0 | 1.32 | 0.11 | 0 | 0.22 | 15.75 | FALSE | 0.5 | 0.6 | 0.33 | 0.22 | 0.11 | 0.44 | 15.8 | TRUE | 0.75 | 0.9 | 0.44 | 0.33 | 0.22 | 0.66 | 16.9 | TRUE | 1 | 1.2 | 0.55 | 0.44 | 0.33 | 0.88 | 18 | TRUE | 15.75 | 2025-05-01 23:44 | 2025-05-07 09:39 | 2025-05-04 01:53 | 2025-05-12 10:06 | 2025-05-12 10:06
Feature | Getting user order size (Just one person or selecting family size) | 1.2 | 2 | 4 | 0.6 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.7 | FALSE | 0.2 | 0.4 | 0.18 | 0.12 | 0.06 | 0.24 | 8.8 | TRUE | 0.3 | 0.6 | 0.24 | 0.18 | 0.12 | 0.36 | 9.4 | TRUE | 0.4 | 0.8 | 0.3 | 0.24 | 0.18 | 0.48 | 10 | TRUE | 8.7 | 2025-05-02 05:43 | 2025-05-08 05:24 | 2025-05-04 14:07 | 2025-05-13 19:13 | 2025-05-13 19:13
Feature | User prefered schedule | 1.2 | 2 | 4 | 0.6 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.7 | FALSE | 0.2 | 0.4 | 0.18 | 0.12 | 0.06 | 0.24 | 8.8 | TRUE | 0.3 | 0.6 | 0.24 | 0.18 | 0.12 | 0.36 | 9.4 | TRUE | 0.4 | 0.8 | 0.3 | 0.24 | 0.18 | 0.48 | 10 | TRUE | 8.7 | 2025-05-02 11:41 | 2025-05-09 01:08 | 2025-05-05 02:21 | 2025-05-15 04:20 | 2025-05-15 04:20
Feature | Getting user intolerance page | 1.6 | 4 | 4 | 0.6 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.4 | TRUE | 0.4 | 0.4 | 0.24 | 0.16 | 0.08 | 0.32 | 11.4 | TRUE | 0.6 | 0.6 | 0.32 | 0.24 | 0.16 | 0.48 | 12.2 | TRUE | 0.8 | 0.8 | 0.4 | 0.32 | 0.24 | 0.64 | 13 | TRUE | 11.4 | 2025-05-02 23:37 | 2025-05-09 20:52 | 2025-05-06 02:49 | 2025-05-16 13:28 | 2025-05-16 13:28
Feature | Welcome screen before discover pages | 0.8 | 0 | 4 | 0.6 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 6 | TRUE | 0 | 0.4 | 0.12 | 0.08 | 0.04 | 0.16 | 6.2 | TRUE | 0 | 0.6 | 0.16 | 0.12 | 0.08 | 0.24 | 6.6 | TRUE | 0 | 0.8 | 0.2 | 0.16 | 0.12 | 0.32 | 7 | TRUE | 6 | 2025-05-02 23:37 | 2025-05-10 16:37 | 2025-05-06 02:49 | 2025-05-17 22:35 | 2025-05-17 22:35
Authentication and profile
Chore | Implementing a SMS service using a third party | 0 | 20 | 0 | 0 | 0 | 0 | 2.4 | 0.2 | 0 | 0.4 | 23 | TRUE | 2 | 0 | 0.6 | 0.4 | 0.2 | 0.8 | 26 | TRUE | 3 | 0 | 0.8 | 0.6 | 0.4 | 1.2 | 28 | TRUE | 4 | 0 | 1 | 0.8 | 0.6 | 1.6 | 30 | TRUE | 23 | 2025-05-05 11:17 | 2025-05-10 16:37 | 2025-05-11 05:10 | 2025-05-17 22:35 | 2025-05-17 22:35
Feature | Login as an end user | 1.6 | 3 | 5 | 0.75 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.55 | TRUE | 0.3 | 0.5 | 0.24 | 0.16 | 0.08 | 0.32 | 11.65 | TRUE | 0.45 | 0.75 | 0.32 | 0.24 | 0.16 | 0.48 | 12.45 | TRUE | 0.6 | 1 | 0.4 | 0.32 | 0.24 | 0.64 | 13.25 | TRUE | 11.55 | 2025-05-05 20:14 | 2025-05-11 17:17 | 2025-05-11 23:31 | 2025-05-19 15:59 | 2025-05-19 15:59
Feature | Send a verification code for login (first login on a new device) | 1.6 | 5 | 3 | 0.45 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.25 | TRUE | 0.5 | 0.3 | 0.24 | 0.16 | 0.08 | 0.32 | 11.15 | TRUE | 0.75 | 0.45 | 0.32 | 0.24 | 0.16 | 0.48 | 11.95 | TRUE | 1 | 0.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12.75 | TRUE | 11.25 | 2025-05-06 11:10 | 2025-05-12 08:05 | 2025-05-13 06:07 | 2025-05-20 16:50 | 2025-05-20 16:50
Feature | Set password (for the first login or reset password) | 1.2 | 3 | 3 | 0.45 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.55 | TRUE | 0.3 | 0.3 | 0.18 | 0.12 | 0.06 | 0.24 | 8.55 | TRUE | 0.45 | 0.45 | 0.24 | 0.18 | 0.12 | 0.36 | 9.15 | TRUE | 0.6 | 0.6 | 0.3 | 0.24 | 0.18 | 0.48 | 9.75 | TRUE | 8.55 | 2025-05-06 20:07 | 2025-05-12 22:54 | 2025-05-14 00:28 | 2025-05-21 17:40 | 2025-05-21 17:40
Feature | Send a verification code for sign up | 1.6 | 5 | 3 | 0.45 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.25 | TRUE | 0.5 | 0.3 | 0.24 | 0.16 | 0.08 | 0.32 | 11.15 | TRUE | 0.75 | 0.45 | 0.32 | 0.24 | 0.16 | 0.48 | 11.95 | TRUE | 1 | 0.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12.75 | TRUE | 11.25 | 2025-05-07 11:02 | 2025-05-13 13:42 | 2025-05-15 07:03 | 2025-05-22 18:31 | 2025-05-22 18:31
Feature | Forgot password | 1.2 | 3 | 3 | 0.45 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.55 | TRUE | 0.3 | 0.3 | 0.18 | 0.12 | 0.06 | 0.24 | 8.55 | TRUE | 0.45 | 0.45 | 0.24 | 0.18 | 0.12 | 0.36 | 9.15 | TRUE | 0.6 | 0.6 | 0.3 | 0.24 | 0.18 | 0.48 | 9.75 | TRUE | 8.55 | 2025-05-07 19:59 | 2025-05-14 04:30 | 2025-05-16 01:24 | 2025-05-23 19:21 | 2025-05-23 19:21
Feature | Welcome and reset password notification (email or sms) | 1.2 | 6 | 0 | 0 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.1 | TRUE | 0.6 | 0 | 0.18 | 0.12 | 0.06 | 0.24 | 7.8 | TRUE | 0.9 | 0 | 0.24 | 0.18 | 0.12 | 0.36 | 8.4 | TRUE | 1.2 | 0 | 0.3 | 0.24 | 0.18 | 0.48 | 9 | TRUE | 8.1 | 2025-05-08 13:53 | 2025-05-14 04:30 | 2025-05-17 14:07 | 2025-05-23 19:21 | 2025-05-23 19:21
Feature | Refresh tokens | 0.8 | 2 | 2 | 0.3 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 5.7 | TRUE | 0.2 | 0.2 | 0.12 | 0.08 | 0.04 | 0.16 | 5.7 | TRUE | 0.3 | 0.3 | 0.16 | 0.12 | 0.08 | 0.24 | 6.1 | TRUE | 0.4 | 0.4 | 0.2 | 0.16 | 0.12 | 0.32 | 6.5 | TRUE | 5.7 | 2025-05-08 19:51 | 2025-05-14 14:22 | 2025-05-18 02:21 | 2025-05-24 11:55 | 2025-05-24 11:55
Feature | Update user profile | 2.6 | 5 | 8 | 1.2 | 0 | 0 | 1.56 | 0.13 | 0 | 0.26 | 18.75 | TRUE | 0.5 | 0.8 | 0.39 | 0.26 | 0.13 | 0.52 | 18.9 | TRUE | 0.75 | 1.2 | 0.52 | 0.39 | 0.26 | 0.78 | 20.2 | TRUE | 1 | 1.6 | 0.65 | 0.52 | 0.39 | 1.04 | 21.5 | TRUE | 18.75 | 2025-05-09 10:46 | 2025-05-16 05:51 | 2025-05-19 08:56 | 2025-05-27 06:10 | 2025-05-27 06:10
Feature | Logout | 1.2 | 3 | 3 | 0.45 | 0 | 0 | 0.72 | 0.06 | 0 | 0.12 | 8.55 | TRUE | 0.3 | 0.3 | 0.18 | 0.12 | 0.06 | 0.24 | 8.55 | TRUE | 0.45 | 0.45 | 0.24 | 0.18 | 0.12 | 0.36 | 9.15 | TRUE | 0.6 | 0.6 | 0.3 | 0.24 | 0.18 | 0.48 | 9.75 | TRUE | 8.55 | 2025-05-09 19:43 | 2025-05-16 20:39 | 2025-05-20 03:17 | 2025-05-28 07:00 | 2025-05-28 07:00
Feature | Delete account and remove all data after a while | 3.4 | 12 | 5 | 0.75 | 0 | 0 | 2.04 | 0.17 | 0 | 0.34 | 23.7 | TRUE | 1.2 | 0.5 | 0.51 | 0.34 | 0.17 | 0.68 | 23.35 | TRUE | 1.8 | 0.75 | 0.68 | 0.51 | 0.34 | 1.02 | 25.05 | TRUE | 2.4 | 1 | 0.85 | 0.68 | 0.51 | 1.36 | 26.75 | TRUE | 23.7 | 2025-05-11 07:32 | 2025-05-17 21:20 | 2025-05-23 04:42 | 2025-05-30 00:24 | 2025-05-30 00:24
Feature | Implementation of feedback and change requests | 6.4 | 16 | 16 | 2.4 | 0 | 0 | 3.84 | 0.32 | 0 | 0.64 | 45.6 | TRUE | 1.6 | 1.6 | 0.96 | 0.64 | 0.32 | 1.28 | 45.6 | TRUE | 2.4 | 2.4 | 1.28 | 0.96 | 0.64 | 1.92 | 48.8 | TRUE | 3.2 | 3.2 | 1.6 | 1.28 | 0.96 | 2.56 | 52 | TRUE | 45.6 | 2025-05-13 07:16 | 2025-05-21 04:17 | 2025-05-27 06:35 | 2025-06-04 12:53 | 2025-06-04 12:53
Epic 6: Mobile app - Discover and category pages
Discover page
Feature | Search in proucts, meals, bags and categories | 4.8 | 12 | 12 | 1.8 | 0 | 0 | 2.88 | 0.24 | 0 | 0.48 | 34.2 | TRUE | 1.2 | 1.2 | 0.72 | 0.48 | 0.24 | 0.96 | 34.2 | TRUE | 1.8 | 1.8 | 0.96 | 0.72 | 0.48 | 1.44 | 36.6 | TRUE | 2.4 | 2.4 | 1.2 | 0.96 | 0.72 | 1.92 | 39 | TRUE | 34.2 | 2025-05-14 19:05 | 2025-05-23 15:30 | 2025-05-30 07:59 | 2025-06-08 16:15 | 2025-06-08 16:15
Feature | Discover bags block | 3.2 | 4 | 12 | 1.8 | 0 | 0 | 1.92 | 0.16 | 0 | 0.32 | 23.4 | TRUE | 0.4 | 1.2 | 0.48 | 0.32 | 0.16 | 0.64 | 23.8 | TRUE | 0.6 | 1.8 | 0.64 | 0.48 | 0.32 | 0.96 | 25.4 | TRUE | 0.8 | 2.4 | 0.8 | 0.64 | 0.48 | 1.28 | 27 | TRUE | 23.4 | 2025-05-15 07:01 | 2025-05-26 02:43 | 2025-05-31 08:27 | 2025-06-12 19:37 | 2025-06-12 19:37
Feature | Popular recipes | 3.2 | 4 | 12 | 1.8 | 0 | 0 | 1.92 | 0.16 | 0 | 0.32 | 23.4 | TRUE | 0.4 | 1.2 | 0.48 | 0.32 | 0.16 | 0.64 | 23.8 | TRUE | 0.6 | 1.8 | 0.64 | 0.48 | 0.32 | 0.96 | 25.4 | TRUE | 0.8 | 2.4 | 0.8 | 0.64 | 0.48 | 1.28 | 27 | TRUE | 23.4 | 2025-05-15 18:57 | 2025-05-28 13:57 | 2025-06-01 08:56 | 2025-06-16 22:59 | 2025-06-16 22:59
Feature | Recipe categories | 3.2 | 4 | 12 | 1.8 | 0 | 0 | 1.92 | 0.16 | 0 | 0.32 | 23.4 | TRUE | 0.4 | 1.2 | 0.48 | 0.32 | 0.16 | 0.64 | 23.8 | TRUE | 0.6 | 1.8 | 0.64 | 0.48 | 0.32 | 0.96 | 25.4 | TRUE | 0.8 | 2.4 | 0.8 | 0.64 | 0.48 | 1.28 | 27 | TRUE | 23.4 | 2025-05-16 06:53 | 2025-05-31 01:10 | 2025-06-02 09:24 | 2025-06-21 02:21 | 2025-06-21 02:21
Feature | Grocery categories list | 3.2 | 4 | 12 | 1.8 | 0 | 0 | 1.92 | 0.16 | 0 | 0.32 | 23.4 | TRUE | 0.4 | 1.2 | 0.48 | 0.32 | 0.16 | 0.64 | 23.8 | TRUE | 0.6 | 1.8 | 0.64 | 0.48 | 0.32 | 0.96 | 25.4 | TRUE | 0.8 | 2.4 | 0.8 | 0.64 | 0.48 | 1.28 | 27 | TRUE | 23.4 | 2025-05-16 18:49 | 2025-06-02 12:23 | 2025-06-03 09:52 | 2025-06-25 05:43 | 2025-06-25 05:43
Feature | None-grocery categories list | 2.2 | 3 | 8 | 1.2 | 0 | 0 | 1.32 | 0.11 | 0 | 0.22 | 16.05 | FALSE | 0.3 | 0.8 | 0.33 | 0.22 | 0.11 | 0.44 | 16.3 | TRUE | 0.45 | 1.2 | 0.44 | 0.33 | 0.22 | 0.66 | 17.4 | TRUE | 0.6 | 1.6 | 0.55 | 0.44 | 0.33 | 0.88 | 18.5 | TRUE | 16.05 | 2025-05-17 03:46 | 2025-06-04 03:51 | 2025-06-04 04:13 | 2025-06-27 23:58 | 2025-06-27 23:58
Product category detail page
Feature | Category header and title | 1.4 | 2 | 5 | 0.75 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.2 | TRUE | 0.2 | 0.5 | 0.21 | 0.14 | 0.07 | 0.28 | 10.35 | TRUE | 0.3 | 0.75 | 0.28 | 0.21 | 0.14 | 0.42 | 11.05 | TRUE | 0.4 | 1 | 0.35 | 0.28 | 0.21 | 0.56 | 11.75 | TRUE | 10.2 | 2025-05-17 09:44 | 2025-06-05 04:32 | 2025-06-04 16:27 | 2025-06-29 17:22 | 2025-06-29 17:22
Feature | Sub-categories list | 1.4 | 2 | 5 | 0.75 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.2 | TRUE | 0.2 | 0.5 | 0.21 | 0.14 | 0.07 | 0.28 | 10.35 | TRUE | 0.3 | 0.75 | 0.28 | 0.21 | 0.14 | 0.42 | 11.05 | TRUE | 0.4 | 1 | 0.35 | 0.28 | 0.21 | 0.56 | 11.75 | TRUE | 10.2 | 2025-05-17 15:42 | 2025-06-06 05:12 | 2025-06-05 04:41 | 2025-07-01 10:46 | 2025-07-01 10:46
Feature | List of related recipes of selected category | 1.6 | 3 | 5 | 0.75 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.55 | FALSE | 0.3 | 0.5 | 0.24 | 0.16 | 0.08 | 0.32 | 11.65 | TRUE | 0.45 | 0.75 | 0.32 | 0.24 | 0.16 | 0.48 | 12.45 | TRUE | 0.6 | 1 | 0.4 | 0.32 | 0.24 | 0.64 | 13.25 | TRUE | 11.55 | 2025-05-18 00:39 | 2025-06-07 05:53 | 2025-06-05 23:03 | 2025-07-03 04:10 | 2025-07-03 04:10
Feature | List of products in selected category (lazy load) | 2.6 | 5 | 8 | 1.2 | 0 | 0 | 1.56 | 0.13 | 0 | 0.26 | 18.75 | TRUE | 0.5 | 0.8 | 0.39 | 0.26 | 0.13 | 0.52 | 18.9 | TRUE | 0.75 | 1.2 | 0.52 | 0.39 | 0.26 | 0.78 | 20.2 | TRUE | 1 | 1.6 | 0.65 | 0.52 | 0.39 | 1.04 | 21.5 | TRUE | 18.75 | 2025-05-18 15:35 | 2025-06-08 21:22 | 2025-06-07 05:38 | 2025-07-05 22:25 | 2025-07-05 22:25
Feature | Filter items based on labels and food type | 2.6 | 5 | 8 | 1.2 | 0 | 0 | 1.56 | 0.13 | 0 | 0.26 | 18.75 | TRUE | 0.5 | 0.8 | 0.39 | 0.26 | 0.13 | 0.52 | 18.9 | TRUE | 0.75 | 1.2 | 0.52 | 0.39 | 0.26 | 0.78 | 20.2 | TRUE | 1 | 1.6 | 0.65 | 0.52 | 0.39 | 1.04 | 21.5 | TRUE | 18.75 | 2025-05-19 06:30 | 2025-06-10 12:50 | 2025-06-08 12:13 | 2025-07-08 16:40 | 2025-07-08 16:40
Bags category detail page
Feature | Bag category header and title | 1.4 | 2 | 5 | 0.75 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.2 | TRUE | 0.2 | 0.5 | 0.21 | 0.14 | 0.07 | 0.28 | 10.35 | TRUE | 0.3 | 0.75 | 0.28 | 0.21 | 0.14 | 0.42 | 11.05 | TRUE | 0.4 | 1 | 0.35 | 0.28 | 0.21 | 0.56 | 11.75 | TRUE | 10.2 | 2025-05-19 12:28 | 2025-06-11 13:31 | 2025-06-09 00:27 | 2025-07-10 10:04 | 2025-07-10 10:04
Feature | Available bags in selected category | 1.4 | 2 | 5 | 0.75 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.2 | TRUE | 0.2 | 0.5 | 0.21 | 0.14 | 0.07 | 0.28 | 10.35 | TRUE | 0.3 | 0.75 | 0.28 | 0.21 | 0.14 | 0.42 | 11.05 | TRUE | 0.4 | 1 | 0.35 | 0.28 | 0.21 | 0.56 | 11.75 | TRUE | 10.2 | 2025-05-19 18:26 | 2025-06-12 14:11 | 2025-06-09 12:41 | 2025-07-12 03:28 | 2025-07-12 03:28
Feature | List of related recipes of selected bag category | 1.6 | 3 | 5 | 0.75 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.55 | FALSE | 0.3 | 0.5 | 0.24 | 0.16 | 0.08 | 0.32 | 11.65 | TRUE | 0.45 | 0.75 | 0.32 | 0.24 | 0.16 | 0.48 | 12.45 | TRUE | 0.6 | 1 | 0.4 | 0.32 | 0.24 | 0.64 | 13.25 | TRUE | 11.55 | 2025-05-20 03:23 | 2025-06-13 14:52 | 2025-06-10 07:03 | 2025-07-13 20:52 | 2025-07-13 20:52
Recipe category detail page
Feature | Recipe category header and title | 1.4 | 2 | 5 | 0.75 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.2 | TRUE | 0.2 | 0.5 | 0.21 | 0.14 | 0.07 | 0.28 | 10.35 | TRUE | 0.3 | 0.75 | 0.28 | 0.21 | 0.14 | 0.42 | 11.05 | TRUE | 0.4 | 1 | 0.35 | 0.28 | 0.21 | 0.56 | 11.75 | TRUE | 10.2 | 2025-05-20 09:21 | 2025-06-14 15:32 | 2025-06-10 19:17 | 2025-07-15 14:16 | 2025-07-15 14:16
Feature | Available recipes in selected category | 2 | 2 | 8 | 1.2 | 0 | 0 | 1.2 | 0.1 | 0 | 0.2 | 14.7 | TRUE | 0.2 | 0.8 | 0.3 | 0.2 | 0.1 | 0.4 | 15 | TRUE | 0.3 | 1.2 | 0.4 | 0.3 | 0.2 | 0.6 | 16 | TRUE | 0.4 | 1.6 | 0.5 | 0.4 | 0.3 | 0.8 | 17 | TRUE | 14.7 | 2025-05-20 15:19 | 2025-06-16 07:01 | 2025-06-11 07:31 | 2025-07-18 08:31 | 2025-07-18 08:31
Feature | Implementation of feedback and change requests | 6.4 | 16 | 16 | 2.4 | 0 | 0 | 3.84 | 0.32 | 0 | 0.64 | 45.6 | TRUE | 1.6 | 1.6 | 0.96 | 0.64 | 0.32 | 1.28 | 45.6 | TRUE | 2.4 | 2.4 | 1.28 | 0.96 | 0.64 | 1.92 | 48.8 | TRUE | 3.2 | 3.2 | 1.6 | 1.28 | 0.96 | 2.56 | 52 | TRUE | 45.6 | 2025-05-22 15:03 | 2025-06-19 13:58 | 2025-06-15 09:24 | 2025-07-23 21:00 | 2025-07-23 21:00
Epic 7: Mobile app - Product, bag and meal views
Single product page
Feature | Single product header | 0.8 | 1 | 3 | 0.45 | 0 | 0 | 0.48 | 0.04 | 0 | 0.08 | 5.85 | TRUE | 0.1 | 0.3 | 0.12 | 0.08 | 0.04 | 0.16 | 5.95 | TRUE | 0.15 | 0.45 | 0.16 | 0.12 | 0.08 | 0.24 | 6.35 | TRUE | 0.2 | 0.6 | 0.2 | 0.16 | 0.12 | 0.32 | 6.75 | TRUE | 5.85 | 2025-05-22 18:03 | 2025-06-20 04:46 | 2025-06-15 15:31 | 2025-07-24 21:51 | 2025-07-24 21:51
Feature | Title, description and price of a product | 1 | 1 | 4 | 0.6 | 0 | 0 | 0.6 | 0.05 | 0 | 0.1 | 7.35 | TRUE | 0.1 | 0.4 | 0.15 | 0.1 | 0.05 | 0.2 | 7.5 | TRUE | 0.15 | 0.6 | 0.2 | 0.15 | 0.1 | 0.3 | 8 | TRUE | 0.2 | 0.8 | 0.25 | 0.2 | 0.15 | 0.4 | 8.5 | TRUE | 7.35 | 2025-05-22 21:02 | 2025-06-21 00:31 | 2025-06-15 21:38 | 2025-07-26 06:58 | 2025-07-26 06:58
Feature | Nutri-score and labels of product | 1.4 | 1 | 6 | 0.9 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.35 | TRUE | 0.1 | 0.6 | 0.21 | 0.14 | 0.07 | 0.28 | 10.6 | TRUE | 0.15 | 0.9 | 0.28 | 0.21 | 0.14 | 0.42 | 11.3 | TRUE | 0.2 | 1.2 | 0.35 | 0.28 | 0.21 | 0.56 | 12 | TRUE | 10.35 | 2025-05-23 00:01 | 2025-06-22 06:07 | 2025-06-16 03:45 | 2025-07-28 08:39 | 2025-07-28 08:39
Feature | Different supermarket prices + add to card | 2.6 | 5 | 8 | 1.2 | 0 | 0 | 1.56 | 0.13 | 0 | 0.26 | 18.75 | TRUE | 0.5 | 0.8 | 0.39 | 0.26 | 0.13 | 0.52 | 18.9 | TRUE | 0.75 | 1.2 | 0.52 | 0.39 | 0.26 | 0.78 | 20.2 | TRUE | 1 | 1.6 | 0.65 | 0.52 | 0.39 | 1.04 | 21.5 | TRUE | 18.75 | 2025-05-23 14:56 | 2025-06-23 21:36 | 2025-06-17 10:20 | 2025-07-31 02:53 | 2025-07-31 02:53
Feature | Nutrional information of product | 2.4 | 4 | 8 | 1.2 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 17.4 | TRUE | 0.4 | 0.8 | 0.36 | 0.24 | 0.12 | 0.48 | 17.6 | TRUE | 0.6 | 1.2 | 0.48 | 0.36 | 0.24 | 0.72 | 18.8 | TRUE | 0.8 | 1.6 | 0.6 | 0.48 | 0.36 | 0.96 | 20 | TRUE | 17.4 | 2025-05-24 02:52 | 2025-06-25 13:05 | 2025-06-18 10:48 | 2025-08-02 21:08 | 2025-08-02 21:08
Feature | Similar products list | 2.4 | 4 | 8 | 1.2 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 17.4 | TRUE | 0.4 | 0.8 | 0.36 | 0.24 | 0.12 | 0.48 | 17.6 | TRUE | 0.6 | 1.2 | 0.48 | 0.36 | 0.24 | 0.72 | 18.8 | TRUE | 0.8 | 1.6 | 0.6 | 0.48 | 0.36 | 0.96 | 20 | TRUE | 17.4 | 2025-05-24 14:48 | 2025-06-27 04:34 | 2025-06-19 11:16 | 2025-08-05 15:23 | 2025-08-05 15:23
Feature | Meals that contain product | 2.4 | 4 | 8 | 1.2 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 17.4 | TRUE | 0.4 | 0.8 | 0.36 | 0.24 | 0.12 | 0.48 | 17.6 | TRUE | 0.6 | 1.2 | 0.48 | 0.36 | 0.24 | 0.72 | 18.8 | TRUE | 0.8 | 1.6 | 0.6 | 0.48 | 0.36 | 0.96 | 20 | TRUE | 17.4 | 2025-05-25 02:44 | 2025-06-28 20:02 | 2025-06-20 11:45 | 2025-08-08 09:37 | 2025-08-08 09:37
Meal page
Feature | Meal image and title block | 0.6 | 0 | 3 | 0.45 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.5 | TRUE | 0 | 0.3 | 0.09 | 0.06 | 0.03 | 0.12 | 4.65 | TRUE | 0 | 0.45 | 0.12 | 0.09 | 0.06 | 0.18 | 4.95 | TRUE | 0 | 0.6 | 0.15 | 0.12 | 0.09 | 0.24 | 5.25 | TRUE | 4.5 | 2025-05-25 02:44 | 2025-06-29 10:51 | 2025-06-20 11:45 | 2025-08-09 10:28 | 2025-08-09 10:28
Feature | Meal description, labels and nutri-score | 1.6 | 2 | 6 | 0.9 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.7 | TRUE | 0.2 | 0.6 | 0.24 | 0.16 | 0.08 | 0.32 | 11.9 | TRUE | 0.3 | 0.9 | 0.32 | 0.24 | 0.16 | 0.48 | 12.7 | TRUE | 0.4 | 1.2 | 0.4 | 0.32 | 0.24 | 0.64 | 13.5 | TRUE | 11.7 | 2025-05-25 08:42 | 2025-06-30 16:27 | 2025-06-20 23:59 | 2025-08-11 12:09 | 2025-08-11 12:09
Feature | Grocery items in meal | 1.4 | 2 | 5 | 0.75 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.2 | TRUE | 0.2 | 0.5 | 0.21 | 0.14 | 0.07 | 0.28 | 10.35 | TRUE | 0.3 | 0.75 | 0.28 | 0.21 | 0.14 | 0.42 | 11.05 | TRUE | 0.4 | 1 | 0.35 | 0.28 | 0.21 | 0.56 | 11.75 | TRUE | 10.2 | 2025-05-25 14:40 | 2025-07-01 17:08 | 2025-06-21 12:13 | 2025-08-13 05:33 | 2025-08-13 05:33
Feature | Nutritional information of meal | 2.8 | 8 | 6 | 0.9 | 0 | 0 | 1.68 | 0.14 | 0 | 0.28 | 19.8 | TRUE | 0.8 | 0.6 | 0.42 | 0.28 | 0.14 | 0.56 | 19.7 | TRUE | 1.2 | 0.9 | 0.56 | 0.42 | 0.28 | 0.84 | 21.1 | TRUE | 1.6 | 1.2 | 0.7 | 0.56 | 0.42 | 1.12 | 22.5 | TRUE | 19.8 | 2025-05-26 14:32 | 2025-07-02 22:44 | 2025-06-23 13:09 | 2025-08-15 07:14 | 2025-08-15 07:14
Feature | Other market total price | 1.8 | 5 | 4 | 0.6 | 0 | 0 | 1.08 | 0.09 | 0 | 0.18 | 12.75 | TRUE | 0.5 | 0.4 | 0.27 | 0.18 | 0.09 | 0.36 | 12.7 | TRUE | 0.75 | 0.6 | 0.36 | 0.27 | 0.18 | 0.54 | 13.6 | TRUE | 1 | 0.8 | 0.45 | 0.36 | 0.27 | 0.72 | 14.5 | TRUE | 12.75 | 2025-05-27 05:28 | 2025-07-03 18:28 | 2025-06-24 19:45 | 2025-08-16 16:21 | 2025-08-16 16:21
Feature | Similar meals | 2 | 4 | 6 | 0.9 | 0 | 0 | 1.2 | 0.1 | 0 | 0.2 | 14.4 | TRUE | 0.4 | 0.6 | 0.3 | 0.2 | 0.1 | 0.4 | 14.5 | TRUE | 0.6 | 0.9 | 0.4 | 0.3 | 0.2 | 0.6 | 15.5 | TRUE | 0.8 | 1.2 | 0.5 | 0.4 | 0.3 | 0.8 | 16.5 | TRUE | 14.4 | 2025-05-27 17:24 | 2025-07-05 00:05 | 2025-06-25 20:13 | 2025-08-18 18:02 | 2025-08-18 18:02
Bag detail page
Feature | Bag image and title block | 0.6 | 0 | 3 | 0.45 | 0 | 0 | 0.36 | 0.03 | 0 | 0.06 | 4.5 | TRUE | 0 | 0.3 | 0.09 | 0.06 | 0.03 | 0.12 | 4.65 | TRUE | 0 | 0.45 | 0.12 | 0.09 | 0.06 | 0.18 | 4.95 | TRUE | 0 | 0.6 | 0.15 | 0.12 | 0.09 | 0.24 | 5.25 | TRUE | 4.5 | 2025-05-27 17:24 | 2025-07-05 14:53 | 2025-06-25 20:13 | 2025-08-19 18:53 | 2025-08-19 18:53
Feature | Bag description, labels and nutri-score | 1.6 | 2 | 6 | 0.9 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.7 | TRUE | 0.2 | 0.6 | 0.24 | 0.16 | 0.08 | 0.32 | 11.9 | TRUE | 0.3 | 0.9 | 0.32 | 0.24 | 0.16 | 0.48 | 12.7 | TRUE | 0.4 | 1.2 | 0.4 | 0.32 | 0.24 | 0.64 | 13.5 | TRUE | 11.7 | 2025-05-27 23:22 | 2025-07-06 20:30 | 2025-06-26 08:27 | 2025-08-21 20:34 | 2025-08-21 20:34
Feature | Grocery items in bag | 1.4 | 2 | 5 | 0.75 | 0 | 0 | 0.84 | 0.07 | 0 | 0.14 | 10.2 | TRUE | 0.2 | 0.5 | 0.21 | 0.14 | 0.07 | 0.28 | 10.35 | TRUE | 0.3 | 0.75 | 0.28 | 0.21 | 0.14 | 0.42 | 11.05 | TRUE | 0.4 | 1 | 0.35 | 0.28 | 0.21 | 0.56 | 11.75 | TRUE | 10.2 | 2025-05-28 05:20 | 2025-07-07 21:10 | 2025-06-26 20:41 | 2025-08-23 13:58 | 2025-08-23 13:58
Feature | Other market total price | 1.8 | 5 | 4 | 0.6 | 0 | 0 | 1.08 | 0.09 | 0 | 0.18 | 12.75 | TRUE | 0.5 | 0.4 | 0.27 | 0.18 | 0.09 | 0.36 | 12.7 | TRUE | 0.75 | 0.6 | 0.36 | 0.27 | 0.18 | 0.54 | 13.6 | TRUE | 1 | 0.8 | 0.45 | 0.36 | 0.27 | 0.72 | 14.5 | TRUE | 12.75 | 2025-05-28 20:15 | 2025-07-08 16:55 | 2025-06-28 03:16 | 2025-08-24 23:05 | 2025-08-24 23:05
Feature | Nutritional information of bag | 2.8 | 8 | 6 | 0.9 | 0 | 0 | 1.68 | 0.14 | 0 | 0.28 | 19.8 | TRUE | 0.8 | 0.6 | 0.42 | 0.28 | 0.14 | 0.56 | 19.7 | TRUE | 1.2 | 0.9 | 0.56 | 0.42 | 0.28 | 0.84 | 21.1 | TRUE | 1.6 | 1.2 | 0.7 | 0.56 | 0.42 | 1.12 | 22.5 | TRUE | 19.8 | 2025-05-29 20:07 | 2025-07-09 22:31 | 2025-06-30 04:13 | 2025-08-27 00:46 | 2025-08-27 00:46
Feature | Meal recipes with selected bag | 3.2 | 8 | 8 | 1.2 | 0 | 0 | 1.92 | 0.16 | 0 | 0.32 | 22.8 | TRUE | 0.8 | 0.8 | 0.48 | 0.32 | 0.16 | 0.64 | 22.8 | TRUE | 1.2 | 1.2 | 0.64 | 0.48 | 0.32 | 0.96 | 24.4 | TRUE | 1.6 | 1.6 | 0.8 | 0.64 | 0.48 | 1.28 | 26 | TRUE | 22.8 | 2025-05-30 19:59 | 2025-07-11 14:00 | 2025-07-02 05:09 | 2025-08-29 19:01 | 2025-08-29 19:01
Feature | Similar bags | 2 | 4 | 6 | 0.9 | 0 | 0 | 1.2 | 0.1 | 0 | 0.2 | 14.4 | TRUE | 0.4 | 0.6 | 0.3 | 0.2 | 0.1 | 0.4 | 14.5 | TRUE | 0.6 | 0.9 | 0.4 | 0.3 | 0.2 | 0.6 | 15.5 | TRUE | 0.8 | 1.2 | 0.5 | 0.4 | 0.3 | 0.8 | 16.5 | TRUE | 14.4 | 2025-05-31 07:56 | 2025-07-12 19:36 | 2025-07-03 05:37 | 2025-08-31 20:42 | 2025-08-31 20:42
Feature | Implementation of feedback and change requests | 6.4 | 16 | 16 | 2.4 | 0 | 0 | 3.84 | 0.32 | 0 | 0.64 | 45.6 | TRUE | 1.6 | 1.6 | 0.96 | 0.64 | 0.32 | 1.28 | 45.6 | TRUE | 2.4 | 2.4 | 1.28 | 0.96 | 0.64 | 1.92 | 48.8 | TRUE | 3.2 | 3.2 | 1.6 | 1.28 | 0.96 | 2.56 | 52 | TRUE | 45.6 | 2025-06-02 07:40 | 2025-07-16 02:34 | 2025-07-07 07:30 | 2025-09-06 09:11 | 2025-09-06 09:11
Epic 8: Shoping proceess and release of platform
Shopping list page
Feature | Shopping list items and total price | 2 | 4 | 6 | 0.9 | 0 | 0 | 1.2 | 0.1 | 0 | 0.2 | 14.4 | TRUE | 0.4 | 0.6 | 0.3 | 0.2 | 0.1 | 0.4 | 14.5 | TRUE | 0.6 | 0.9 | 0.4 | 0.3 | 0.2 | 0.6 | 15.5 | TRUE | 0.8 | 1.2 | 0.5 | 0.4 | 0.3 | 0.8 | 16.5 | TRUE | 14.4 | 2025-06-02 19:36 | 2025-07-17 08:10 | 2025-07-08 07:58 | 2025-09-08 10:52 | 2025-09-08 10:52
Feature | Other markets with total price | 2.8 | 8 | 6 | 0.9 | 0 | 0 | 1.68 | 0.14 | 0 | 0.28 | 19.8 | TRUE | 0.8 | 0.6 | 0.42 | 0.28 | 0.14 | 0.56 | 19.7 | TRUE | 1.2 | 0.9 | 0.56 | 0.42 | 0.28 | 0.84 | 21.1 | TRUE | 1.6 | 1.2 | 0.7 | 0.56 | 0.42 | 1.12 | 22.5 | TRUE | 19.8 | 2025-06-03 19:28 | 2025-07-18 13:47 | 2025-07-10 08:55 | 2025-09-10 12:33 | 2025-09-10 12:33
Feature | Nutri-score and labels of shopping list | 2.8 | 8 | 6 | 0.9 | 0 | 0 | 1.68 | 0.14 | 0 | 0.28 | 19.8 | TRUE | 0.8 | 0.6 | 0.42 | 0.28 | 0.14 | 0.56 | 19.7 | TRUE | 1.2 | 0.9 | 0.56 | 0.42 | 0.28 | 0.84 | 21.1 | TRUE | 1.6 | 1.2 | 0.7 | 0.56 | 0.42 | 1.12 | 22.5 | TRUE | 19.8 | 2025-06-04 19:21 | 2025-07-19 19:23 | 2025-07-12 09:51 | 2025-09-12 14:14 | 2025-09-12 14:14
Feature | Nutritional information table | 2.2 | 5 | 6 | 0.9 | 0 | 0 | 1.32 | 0.11 | 0 | 0.22 | 15.75 | TRUE | 0.5 | 0.6 | 0.33 | 0.22 | 0.11 | 0.44 | 15.8 | TRUE | 0.75 | 0.9 | 0.44 | 0.33 | 0.22 | 0.66 | 16.9 | TRUE | 1 | 1.2 | 0.55 | 0.44 | 0.33 | 0.88 | 18 | TRUE | 15.75 | 2025-06-05 10:16 | 2025-07-21 01:00 | 2025-07-13 16:26 | 2025-09-14 15:55 | 2025-09-14 15:55
Feature | Filter supermarkets based on preferences | 2.2 | 5 | 6 | 0.9 | 0 | 0 | 1.32 | 0.11 | 0 | 0.22 | 15.75 | TRUE | 0.5 | 0.6 | 0.33 | 0.22 | 0.11 | 0.44 | 15.8 | TRUE | 0.75 | 0.9 | 0.44 | 0.33 | 0.22 | 0.66 | 16.9 | TRUE | 1 | 1.2 | 0.55 | 0.44 | 0.33 | 0.88 | 18 | TRUE | 15.75 | 2025-06-06 01:11 | 2025-07-22 06:37 | 2025-07-14 23:02 | 2025-09-16 17:36 | 2025-09-16 17:36
Feature | Filter supermarkets based on location and custom preferences | 2.2 | 5 | 6 | 0.9 | 0 | 0 | 1.32 | 0.11 | 0 | 0.22 | 15.75 | FALSE | 0.5 | 0.6 | 0.33 | 0.22 | 0.11 | 0.44 | 15.8 | FALSE | 0.75 | 0.9 | 0.44 | 0.33 | 0.22 | 0.66 | 16.9 | FALSE | 1 | 1.2 | 0.55 | 0.44 | 0.33 | 0.88 | 18 | TRUE | 15.75 | 2025-06-06 16:06 | 2025-07-23 12:13 | 2025-07-16 05:37 | 2025-09-18 19:17 | 2025-09-18 19:17
Feature | Suggest nearest supermarket based on user location | 2.8 | 8 | 6 | 0.9 | 0 | 0 | 1.68 | 0.14 | 0 | 0.28 | 19.8 | FALSE | 0.8 | 0.6 | 0.42 | 0.28 | 0.14 | 0.56 | 19.7 | FALSE | 1.2 | 0.9 | 0.56 | 0.42 | 0.28 | 0.84 | 21.1 | FALSE | 1.6 | 1.2 | 0.7 | 0.56 | 0.42 | 1.12 | 22.5 | TRUE | 19.8 | 2025-06-07 15:58 | 2025-07-24 17:50 | 2025-07-18 06:33 | 2025-09-20 20:58 | 2025-09-20 20:58
Feature | Redirect shopping list to AlbertHeijn web store | 1.6 | 5 | 3 | 0.45 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.25 | TRUE | 0.5 | 0.3 | 0.24 | 0.16 | 0.08 | 0.32 | 11.15 | TRUE | 0.75 | 0.45 | 0.32 | 0.24 | 0.16 | 0.48 | 11.95 | TRUE | 1 | 0.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12.75 | TRUE | 11.25 | 2025-06-08 06:54 | 2025-07-25 08:38 | 2025-07-19 13:09 | 2025-09-21 21:48 | 2025-09-21 21:48
Feature | Redirect shopping list to Jumbo web store | 1.6 | 5 | 3 | 0.45 | 0 | 0 | 0.96 | 0.08 | 0 | 0.16 | 11.25 | TRUE | 0.5 | 0.3 | 0.24 | 0.16 | 0.08 | 0.32 | 11.15 | TRUE | 0.75 | 0.45 | 0.32 | 0.24 | 0.16 | 0.48 | 11.95 | TRUE | 1 | 0.6 | 0.4 | 0.32 | 0.24 | 0.64 | 12.75 | TRUE | 11.25 | 2025-06-08 21:49 | 2025-07-25 23:26 | 2025-07-20 19:44 | 2025-09-22 22:39 | 2025-09-22 22:39
Feature | Implementation of feedback and change requests | 6.4 | 16 | 16 | 2.4 | 0 | 0 | 3.84 | 0.32 | 0 | 0.64 | 45.6 | TRUE | 1.6 | 1.6 | 0.96 | 0.64 | 0.32 | 1.28 | 45.6 | TRUE | 2.4 | 2.4 | 1.28 | 0.96 | 0.64 | 1.92 | 48.8 | TRUE | 3.2 | 3.2 | 1.6 | 1.28 | 0.96 | 2.56 | 52 | TRUE | 45.6 | 2025-06-10 21:33 | 2025-07-29 06:24 | 2025-07-24 21:37 | 2025-09-28 11:08 | 2025-09-28 11:08
Epic 9: Data broker (rough estimation)
Shopping list page
Feature | Universal language | 2 | 4 | 6 | 0.9 | 0 | 0 | 1.2 | 0.1 | 0 | 0.2 | 14.4 | FALSE | 0.4 | 0.6 | 0.3 | 0.2 | 0.1 | 0.4 | 14.5 | FALSE | 0.6 | 0.9 | 0.4 | 0.3 | 0.2 | 0.6 | 15.5 | FALSE | 0.8 | 1.2 | 0.5 | 0.4 | 0.3 | 0.8 | 16.5 | TRUE | 14.4 | 2025-06-11 09:29 | 2025-07-30 12:00 | 2025-07-25 22:05 | 2025-09-30 12:49 | 2025-09-30 12:49
Feature | Other markets with total price | 32 | 80 | 80 | 12 | 0 | 0 | 19.2 | 1.6 | 0 | 3.2 | 228 | FALSE | 0.8 | 0.6 | 0.42 | 0.28 | 0.14 | 0.56 | 19.7 | FALSE | 1.2 | 0.9 | 0.56 | 0.42 | 0.28 | 0.84 | 21.1 | FALSE | 1.6 | 1.2 | 0.7 | 0.56 | 0.42 | 1.12 | 22.5 | TRUE | 228 | 2025-06-21 08:12 | 2025-08-15 22:47 | 2025-08-15 07:29 | 2025-10-28 03:15 | 2025-10-28 03:15
Release of the Platform
Chore | Setup and configure live server | 0 | 12 | 12 | 0 | 0 | 0 | 2.88 | 0.24 | 0 | 0.48 | 27.6 | TRUE |  |  | 0.72 | 0.48 | 0.24 |  | 27.84 | TRUE |  |  | 0.96 | 0.72 | 0.48 |  | 28.56 | TRUE |  |  | 1.2 | 0.96 | 0.72 |  | 29.28 | TRUE | 27.6 | 2025-06-22 20:00 | 2025-08-18 10:00 | 2025-08-18 08:54 | 2025-11-01 06:37 | 2025-11-01 06:37
Chore | Setup application | 0 | 32 | 0 | 0 | 0 | 0 | 3.84 | 0.32 | 0 | 0.64 | 36.8 | TRUE |  |  | 0.96 | 0.64 | 0.32 |  | 37.12 | TRUE |  |  | 1.28 | 0.96 | 0.64 |  | 38.08 | TRUE |  |  | 1.6 | 1.28 | 0.96 |  | 39.04 | TRUE | 36.8 | 2025-06-26 19:29 | 2025-08-18 10:00 | 2025-08-26 12:40 | 2025-11-01 06:37 | 2025-11-01 06:37
Chore | Insert the base data | 0 | 12 | 0 | 0 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 13.8 | TRUE |  |  | 0.36 | 0.24 | 0.12 |  | 13.92 | TRUE |  |  | 0.48 | 0.36 | 0.24 |  | 14.28 | TRUE |  |  | 0.6 | 0.48 | 0.36 |  | 14.64 | TRUE | 13.8 | 2025-06-28 07:17 | 2025-08-18 10:00 | 2025-08-29 14:04 | 2025-11-01 06:37 | 2025-11-01 06:37
Chore | configure the monitoring and backup | 0 | 12 | 0 | 0 | 0 | 0 | 1.44 | 0.12 | 0 | 0.24 | 13.8 | TRUE |  |  | 0.36 | 0.24 | 0.12 |  | 13.92 | TRUE |  |  | 0.48 | 0.36 | 0.24 |  | 14.28 | TRUE |  |  | 0.6 | 0.48 | 0.36 |  | 14.64 | TRUE | 13.8 | 2025-06-29 19:06 | 2025-08-18 10:00 | 2025-09-01 15:29 | 2025-11-01 06:37 | 2025-11-01 06:37
| Total estimated time + risk margin of 15% | 315.33 | 1105.15 | 923.45 | 131.2725 | 0 | 0 | 243.432 | 20.286 | 0 | 40.572 | 3335.391 | 2652.1185 | 76.935 | 82.34 | 55.821 | 33.695 | 16.8475 | 70.748 | 3098.8728 | 1866.4063 | 60.2025 | 148.1775 | 67.022 | 44.436 | 29.624 | 95.013 | 2897.931 | 1922.041 | 80.27 | 197.57 | 83.7775 | 59.248 | 44.436 | 126.684 | 3074.9436 | 2132.0931 | 3335.391 | 2025-07-08 07:38 | 2025-09-03 22:46 | 2025-09-19 02:50 | 2025-11-29 00:23 | 2025-11-29 00:23 | 48.62
| Total remaining time | 315.33 | 1105.15 | 923.45 | 131.2725 | 0 | 0 | 243.432 | 20.286 | 0 | 40.572 | 3335.391 | 2652.1185 | 76.935 | 82.34 | 55.821 | 33.695 | 16.8475 | 70.748 | 3098.8728 | 1866.4063 | 60.2025 | 148.1775 | 67.022 | 44.436 | 29.624 | 95.013 | 2897.931 | 1922.041 | 80.27 | 197.57 | 83.7775 | 59.248 | 44.436 | 126.684 | 3074.9436 | 2132.0931 | 3335.391 |  |  |  |  | 213

## Meetings
SuperMarty project - Meetings
State | Meeting items | Comments
21 October 2024 - Kick-Off Meeting
TRUE | Introduction
TRUE | Responsibilities and representatives: Managing one of the items: Budget, scope, deadline
TRUE | Official start of the project - Pre-development phase
TRUE | Approval on designs, flows, and roadmap (MVP scope) | Mahsa will send the MVP scope to Amir for final approval
TRUE | Agile contract and invoicing structure
TRUE | Agile management methodologies
TRUE | Support system
TRUE | Q&A | Amir: Contracts and legal process should be started - Source code's should be delivered to us ¦ Mahsa: I will provide you with the answer by the end of the day.
11 November 2024 - Agile management methodology
TRUE | What is Agile: Scrum - Epic - Sprint
TRUE | What steps we will take during the project
TRUE | I will be a guardian to your budget
TRUE | We are dependent on you
TRUE | Q&A
2 December 2024 - Update and Question
TRUE | Let's keep in touch. We need your cooperation
TRUE | 2 times in week to be avaiable | Wednesday: 12:00 to 13:00 - Thursday 12:00 to 13:00
TRUE | We do not recommend a native mobile app | Web app
TRUE | Low code portals for admin panel | Agreed
TRUE | Payments and invoices | Amir give me a deadline today (December 2)
TRUE | Q&A | Scapper launched a new apps
9 December 2024 - Update and Question
TRUE | What categories do you want have? | We need to have as detailed tags as possible (Zuivel, eieren, boterMelkHalfvolle melk) - The admin should be able to change the suggested products manually
TRUE | How many users do you estimate to use the application? | Amir is going to send it to me by December 10
TRUE | Can we crawl the recepies from the markets? | I will let you know by December 12
16 December 2024 - Update and Question
TRUE | Should meals include fields for a name, description, and preparation instructions? | Yes
TRUE | Which product categories from the supermarkets do you want to include in the system (e.g., Meat, Vegetables, Beverages)? | Same as Albert hein
TRUE | What information should be used to define a bag or meal? For example: price, weight, calories, nutritional breakdown, etc. | Amir will send the list to me
TRUE | Should out-of-stock products be displayed in suggestions, or should they be excluded? | Nothing for now
TRUE | What are the key factors for end-users to discover bags and meals? For example: price, nutritional value, category, popularity, or user preferences. | If the user has not chosen any filter or preference, show the bags and meals randomly but other than this, it should be based on the user's preference and the tags that the admin had added to the bags and meals: like Diet, helal, low carb, high protein
TRUE | For the matching algorithm: -Should the system aim for exact matches (same product across all supermarkets)? -Or should it suggest close matches (similar products with slight differences)? -How should the system handle scenarios where a product does not exist in one or more supermarkets? | 6.1- the admin should be able to change the product of a market if the exact match was not found 6.2- the category should stay the same, but the amounts, weigh, and things like this can be different 6.3- Show a warning to the admin to search for an alternative but for the shopping cart that user creates, show all the markets, and show a warning next to the market that does not have all the products
TRUE | How should the system handle packaged or pre-offered products, like predefined bags or meal kits available directly from supermarkets? | unclear question
TRUE | After a bag or meal is finalized, where should the user be redirected? - Would you prefer to show links to each item in the bag/meal individually? Risks and blockers for MVP : supermarket account registrations or blockers | check out page of that market - they need to have an account- We need to put a notif there that the users have to have accounts on those markets
TRUE | Should a meal function purely as an instructional recipe, or should it specify exact products sourced from the four supermarkets? | specific products
TRUE | Do end-users have any roles in the system? Why? | Not for MVP but in the future there are going to have hierarchy in the system eg trainer, normal user
TRUE | Should the system store user activities, preferences, or liked bags/meals in the MVP version? Why? | yes preference: yes like: it means adding it to the favorites list user activity: we didn't get what does it mean
TRUE | Amir: I would like to have an AI as a food assistance in the application | It is a good idea, but not for MVP
23 December 2024 - Update and Question
TRUE | Concern regarding the payment transparency | Amir understood the concerns we had and
TRUE | Javad : Is it necessary to include Picnic supermarket in the MVP, or would you recommend starting with another supermarket due to data aggregation challenges? | Amir: We can skip Picnic for the MVP but keep in mind we eventually need that in the later versions
TRUE | Javad : Is it essential to include categories like laundries in the product categories? | Amir: Include everything in the categories
TRUE | Javad : How should the system handle packaged or pre-offered products, like predefined bags or meal kits available directly from supermarkets? | Amir: Show them one on one
TRUE | Vahid: We can devide the system into 3 parts: 1- users 2- Admin 3- Aggregation of data from super markets | Amir: It is ok
TRUE | Vahid: We want to to focus on the admin side first, what are the fields needed for the meals and bags and products | we have 3 levels: 1- bags, 2-meals, 3- products= Nutritional info for all levels. Description field for bags and meals
TRUE | Vahid: Why do you need to have products in the admin panel | Amir: If I want to create a mean, I need to create a bag first, and for bag I need to have access to bags
TRUE | Amir: I want to reuse the created meals to create new ones without being have to making it from scratch | Mahsa: We can have a feature like duplicate
TRUE | Javad: Do users see the total calleries or it should be based on the product? | Amir: It should be top down, first total callery of the bag, then meal, then product
TRUE | Vahid: Filter supermarket products with some fields and related them to our product | Amir: It's a good idea but have some challenging products like chilly powder for find in all supermarkets with same filter because same product have some types in different supermarkets and with different prices
TRUE | Vahid: In client side there is a challenge in purchase shopping list in supermarkets | Amir: It's exist some solution for example in albert heighn can share the shopping list link and other just click on it and use that shopping list Javad: we can thinking more future for this challenge and find solution
30 December 2024- Update and Question
TRUE | Reviewing action points of the previous meeting
TRUE | Reviewing the budget spent so far
TRUE | Approval on the epic and its features
TRUE | Available in [name supermarkets] field in add product page | It was a misunderstanding and we can show this value for the admins
TRUE | How to manage Nutritional values on products? | For the products with standard units (kg, Li) it is ok. For the ones that are being sold in peices but the nutitional values are per grams, we will provide their list to Amir so he can tell us the standard nutritional values. We will send the list to Amir by the end of January
TRUE | Q&A | Amir: I would like to see how we are going to show the nutritional values in user side. ¦ Mahsa: We already have samples. We can demonstrate them to you next week
06 January 2025- Update and Question
TRUE | Reviewing action points of the previous meeting
TRUE | Reviewing the budget spent so far | Admin panel: On track - Aggregator: Off track. At the end of the sprint, We might need to remove someof the less-important features to cover it up
TRUE | Product fields | Amir has checked the fields that we need to store - He will highlight the fields that he doesn't understand what they mean
TRUE | Approval on epic 2's features | Amir will review and provide us with a resonse by the end of the day
TRUE | Approval on the payment at the end of January | Amir will let me know by the end of the day
TRUE | Lack of response to the emails and its consequences on us | Amir said he will try to respond to ny emails in 24 hours
TRUE | Nutritional value design samples | By the end of tomorrow Amir will send a compelete list of nutritional values - For the first version, we will use the table design
TRUE | Q&A
16 January 2025- Update and Question
TRUE | Next steps
TRUE | Payment terms | Amir will talk to Jacky and inform us by Jan 17
TRUE | Q&A
20 January 2025- Update and Question
TRUE | Reviewing action points of the previous meeting
TRUE | Reviewing the budget spent so far
TRUE | Epic 2 designs
TRUE | Demonstrating Sprint 1
TRUE | Finalizing payment terms
TRUE | Q&A
17 February 2025- Update and Question
TRUE | Reviewing action points of the previous meeting | Amir will send it after the meeting
TRUE | Reviewing the budget spent so far | Mahsa should share the credentials of stage by Feb 20
TRUE | Company set up, and official invoices | Amir will talk to Jacky and let me know about the result
TRUE | Logo of the Super Marty project | Amir will share the files after the meeting
TRUE | Language of the application- We need Dutch translation | Mahsa will provide Amir with a clean Figma file by Feb 20, Amir will translate and add comments, no deadline for this
TRUE | Q&A
24 February 2025- Update and Question
TRUE | Meet our team members
TRUE | Reviewing action points of the previous meeting
TRUE | Reviewing the budget spent so far
TRUE | Discover page design
TRUE | Demonstration of epic 1 and 2
TRUE | Searching within products, price or amount | Internally solved
TRUE | Q&A
5 March 2025- Update and Question
TRUE | Reviewing action points of the previous meeting
TRUE | Reviewing the budget spent so far
TRUE | Checking epic 1 and 2
TRUE | Q&A
10 March 2025- Update and Question
TRUE | Reviewing action points of the previous meeting
TRUE | Reviewing the budget spent so far
TRUE | Demonstrating recent features
TRUE | Product and group product
TRUE | Q&A
17 March 2025- Update and Question
TRUE | Reviewing action points of the previous meeting
TRUE | Reviewing the budget spent so far
TRUE | Reviewing your feedback document
TRUE | Check out and redirection to the destination super market
TRUE | Charactristics of the products
TRUE | Q&A
8 April 2025- Update and Question
TRUE | Reviewing the invoices
TRUE | Confiusion about the project budget
8 April 2025- Update and Question - Afternoon
TRUE | Reviewing action points of the previous meeting
TRUE | Reviewing the budget spent so far
TRUE | A short demo of selecting market products for product groups
TRUE | Deeper discussion about charactristics
TRUE | Q&A
9 April 2025- Update and Question
TRUE | October 21 - Project discovery files including roadmap were sent via email
TRUE | November 10 - Total hours and rate per hour were sent via email
TRUE | How far have we proceeded so far according to the initial roadmap
TRUE | What next? Are we limitted to the 100K? If yes, we need to plan how to use the remaining time
TRUE | Retro: Emails should be checked carefully and replied
TRUE | Q&A
10 April 2025 - Roadmap review meeting
TRUE | Reviewing the roadmap and listing the remaining to-dos
15 April 2025- Update and Question
TRUE | What is the budget?
TRUE | The payment planning
22 April 2025- Update and Question
TRUE | Reviewing action points of the previous meeting
TRUE | Reviewing the budget spent so far
TRUE | Let's go live! | Server: a VM for now. Duration: 3 months Storage: 100GB Mail provider: Mailgun SSL: Comodo Domain
TRUE | Demonstration of the new features
TRUE | Q&A
29 April 2025- Update and Question
FALSE | Reviewing action points of the previous meeting
FALSE | Reviewing the budget spent so far
FALSE | Demonstration of the new features
FALSE | Q&A
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Action points
SuperMarty project - Action points
State | Action points | Responsible | Deadline | Comment | Formulas
01 January 2023 - Kick-Off Meeting
FALSE |  |  |  |  | 0
FALSE
FALSE
FALSE
FALSE
FALSE
Formulas:
Formulas = COUNTIF([Deadline]:D9, "<" & TODAY())

## Q&A
SuperMarty project - Questions & Answers
State | Question | Requester | Request date | Responsible | Answer | Formulas
FALSE | aya in shopping haii ke azashon data migirm be ma api mostaghim midan ke data ro fetch konim ya na ? | Arash |  |  |  | 0
FALSE | pishbinimon az mizan user ya marketing rooye in app cheghadre baraye v1 ? | Arash
FALSE | aya ma mostaghim mitoonim emkane order ro be user bedim yani oon order rooye bag haye app ma bezane ? | Arash
FALSE | rate taghiir data cheghadre ? minute ? hour ? daily ? or per change from source ? | Arash
FALSE | mikhaim pishnahad bedim rooye filter ke masaln healthy hast ya na ? aya harkodom az product ha ke az site haye thirdparty dige hast item hashon mesle mizane kalori , enerzhi, suger va... yeki hast ? | Arash
FALSE | mobile app ke mikhaim aya besoorate nasbi bashe va baraye ios ya android ? ya WPA ham bashe okeye ? | Arash
FALSE | aya producti ke too AlbertHeijn hast daghighan ham esmesh tooye jumbo hast ? yani mishe inaro match kard ? va melakemon baraye matching product chie ? barcode ? name ? chon mikhaim price haro baham compare konim baayad product ro ba ye item baham match konim | Arash |  |  |  | 0
FALSE | ma niaz darim baraye hamchin app i algoritm haii ke estefade mishe va nahve tasmim giri system ro dashte bashim va bedoonim app ma bar che asas kar mikone , aya darim hamchin chizi ? | Arash
FALSE | faghat data ro az in 4 ta online shop migirim ? va dar ayande niaz nist bishatar beshe ? | Arash
FALSE | feature search va filter product ha tu app cheghadr ahamiat dare? | Vahid
FALSE | What is the value proposition of the product? What makes it different from the competitors? | Mahsa |  |  |  | 0
FALSE | Who is the target audiance of the product for V1? | Mahsa
FALSE | How the initial products will be added to the admin panel? via crawling? adding manually? | Mahsa |  |  |  | 0
FALSE | Are the items in each bag belong to 1 market? (As an admin I have created a bag, and the cheapest option belongs to Albert heijn) | Mahsa
FALSE | Where do we get the nutritions? | Mahsa |  |  |  | 0
FALSE | What information will we get for creating the account? | Mahsa
FALSE
FALSE | If the data crawling of these websites is going to be handled on our end, have the IP limitations been considered? We would need a significant number of IPs to avoid being restricted by those websites, as they will likely block us. | Alireza
FALSE | Approximately how many products are we expected to have in the system overall? | Alireza
FALSE | Let’s assume that cucumbers are one of the products. My main question is, on what basis are we going to determine that the cucumbers from Store A and Store B are related? Is it possible to use artificial intelligence in our system for product categorization and linking? | Alireza
FALSE | Considering that stores usually have a large variety of packaging or supplier options for a single product with different prices, which products should we display? Should we consider only the common products among these four stores or include all the products? | Alireza
FALSE | if the crawling of these websites is handled on our end, how are we going to manage the structural changes of these websites? Will these changes come to us as a bug that we need to update, or is the plan to design the system in a way that such cases can be managed by the admin without needing a developer? | Alireza
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Formulas:
Formulas = COUNTIF([Request date]:D8, "<" & TODAY())
Formulas = COUNTIF([Request date]:[Request date, row below], "<" & TODAY())

## Resources
SuperMarty project - Resources
Team members | Personnel nr | Status | Role | Technical coach | Seniority multiplier | Actual output | Working hours p/w | Project team meetings deduction | [7 empty] | Personal time (non project related) |  |  | Company meetings (non project related) |  |  |  |  | Other project permanent commitment | Commited time | Actual task time p/w | Expected task output p/w | Actual velocity | Last checked and verified | Comment
[8 empty] | Project retro | Technical meetings | Weekly planning | Unplanned communication | Sprint demo | Sprint demo rehearsal | Scrum poker | Daily stand up's p/w | Time off in hours p/w | Holidays in hours p/w | IDP and R&D | Company week retro | Chapter retro | Company management | Interviews | Assessments
Mahsa Amiri |  | TRUE | Project manager | FALSE | 1 | 6 - Normal | 40 | 0.25 | 0 | 1.6875 | 2.5312 | 0.5 | 0 | 0 | 1.25 | 2.5 | 1.8169 | 1.6875 | 0.28125 | 0.14062 | 0.14062 | 0 | 0 | 17.5 | 15.9331 | 9.7144 | 9.7144 |  | 2025-02-11
Javad Zaki |  | TRUE |  | FALSE | 1 | 6 - Normal | 40 | 0 | 0 | 0.0625 | 0.09375 | 0 | 0 | 0 | 0 | 0.55556 | 0.40375 | 0.375 | 0.0625 | 0.03125 | 0 | 0 | 0 | 35 | 3.5719 | 3.4157 | 3.4157 |  | 2025-02-11
Komeyl Mohebbian |  | TRUE | Frontend development | FALSE | 1 | 6 - Normal | 40 | 0.25 | 1 | 0.5 | 0.75 | 0.5 | 0 | 1 | 1.25 | 4.4444 | 3.23 | 3 | 0.5 | 0.25 | 0 | 0 | 0 | 0 | 28.5756 | 23.3256 | 23.3256 |  | 2025-02-11
Alireza Ebrahimzadeh |  | TRUE | Backend development | FALSE | 1 | 6 - Normal | 40 | 0 | 0.5 | 0.125 | 0.1875 | 0 | 0 | 0 | 0.5 | 1.1111 | 0.8075 | 0.75 | 0.125 | 0.0625 | 0 | 0 | 0 | 30 | 7.1439 | 5.8314 | 5.8314 |  | 2025-02-11
Maziar Gholami |  | TRUE | UI/UX design | FALSE | 1 | 6 - Normal | 40 | 0 | 0 | 0.1875 | 0.28125 | 0 | 0 | 0 | 0.5 | 1.6667 | 1.2112 | 1.125 | 0.1875 | 0.09375 | 0 | 0 | 0 | 25 | 10.7158 | 9.7471 | 9.7471 |  | 2025-02-11
Farzaneh Sadeghi |  | TRUE | Dev Ops development | FALSE | 1 | 6 - Normal | 40 | 0 | 0.5 | 0.125 | 0.1875 | 0 | 0 | 0 | 0.5 | 1.1111 | 0.8075 | 0.75 | 0.125 | 0.0625 | 0 | 0 | 0 | 30 | 7.1439 | 5.8314 | 5.8314 |  | 2025-02-11
Vahid Sarhaddi |  | TRUE | Technical (code) review | FALSE | 1 | 6 - Normal | 40 | 0 | 0.5 | 0.125 | 0.1875 | 0 | 0 | 0 | 0.5 | 1.1111 | 0.8075 | 0.75 | 0.125 | 0.0625 | 0 | 0 | 0 | 30 | 7.1439 | 5.8314 | 5.8314 |  | 2025-02-11
Nayyer Jafari |  | TRUE | Technical (code) review | FALSE | 1 | 6 - Normal | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 |  | 2025-02-11
Parya Ardalani |  | TRUE |  | FALSE | 1 | 6 - Normal | 40 | 0.25 | 1 | 0.5 | 0.75 | 0.5 | 0 | 1 | 1.25 | 4.4444 | 3.23 | 3 | 0.5 | 0.25 | 0 | 0 | 0 | 0 | 28.5756 | 23.3256 | 23.3256 |  | 2025-02-11
Amin Mohabbat |  | TRUE | Backend development | FALSE | 1 | 6 - Normal | 40 | 0.25 | 1 | 0.4375 | 0.65625 | 0.5 | 0 | 1 | 1.25 | 3.8889 | 2.8262 | 2.625 | 0.4375 | 0.21875 | 0 | 0 | 0 | 5 | 25.0036 | 19.9099 | 19.9099 |  | 2025-02-11
|  | FALSE |  | FALSE |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FALSE |  | FALSE |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FALSE |  | FALSE |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FALSE |  | FALSE |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FALSE |  | FALSE
|  | FALSE |  | FALSE
|  | FALSE |  | FALSE
|  | FALSE |  | FALSE
|  | FALSE |  | FALSE
|  | FALSE |  | FALSE
| Extra ordinary events impacting team members working hours | [22 empty] | Comment
Team members | Type | Start date |  | End date |  | Deviation in hours p/d | Total deviation
Nayyer Jafari | [5 empty] | 0
Parya Ardalani | [5 empty] | -8
Amin Mohabbat | [5 empty] | -7
| Project velocity estimation per week | [5 empty] | Resources deficit |  | Roadmap hours |  |  |  | Remaining work in weeks |  | Additional data | [14 empty] | Comment
Role | Ideal output p/w |  | Current roles output p/w | Required rebalanced output p/w |  |  | Deficit p/w | Main roles def. p/w | Total hours | Back remaining | Front remaini. | Total remaining | Ideal | Current | Ideal out. total
Project manager | 8.6932 |  | 9.7144 | 8.6932 |  |  | -1.0212 | -1.0212 | 140.76 |  |  | 72.68 | 8.3606 | 8.3606
Full stack development | 0 |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0
Backend development | 45.1852 |  | 31.5726 | 27.462 |  |  | 13.6126 | 16.3517 | 774.525 | 377.775 |  | 377.775 | 8.3606 | 13.7563 | 56.3034
Frontend development | 20.2887 |  | 23.3256 | 20.2887 |  |  | -3.0369 | -1.807 | 284.625 |  | 169.625 | 169.625 | 8.3606 | 8.3606 | 34.0437
UI/UX design | 3.6692 |  | 9.7471 | 3.6692 |  |  | -6.0779 |  | 40.6812 |  |  | 30.6762 | 8.3606 | 8.3606
Backend auto. testing | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
Frontend auto. testing | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
Technical (code) review | 7.8404 |  | 5.8314 | 5.718 |  |  | 2.009 |  | 126.96 | 45.2378 | 20.3122 | 65.55 | 8.3606 | 11.4637
Performance testing | 0.65336 |  | 0 | 0.4765 |  |  | 0.65336 |  | 10.58 | 3.7698 | 1.6927 | 5.4625 | 8.3606 | 11.4637
Security testing | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Technical documentation | 1.3067 |  | 0 | 0.95301 |  |  | 1.3067 |  | 21.16 | 7.5396 | 3.3854 | 10.925 | 8.3606 | 11.4637
Dev Ops development | 0 |  | 5.8314 | 0 |  |  | -5.8314
Formulas:
Personnel nr = IF('Roadmap setting'!$B8>TODAY(),[Sprint demo]/ROUNDUP(('Roadmap setting'!$B8-TODAY())/7),[Sprint demo]/MIN(O55:O56))
Daily stand up's p/w = IF(ISDATE('Roadmap setting'!$B7)&'Roadmap setting'!$B7<TODAY(),[Technical meetings]/ROUNDUP(('Roadmap setting'!$B8-'Roadmap setting'!$B7)/7),[Technical meetings]/[Scrum poker])
Daily stand up's p/w = IF('Roadmap setting'!$B8>TODAY(),[Technical meetings]/ROUNDUP(('Roadmap setting'!$B8-TODAY())/7),[Technical meetings]/[Scrum poker])

## Roadmap setting
SuperMarty project - Roadmap settings
Project settings |  |  |  |  | Comment
Project name | SuperMarty project
Company name | SuperMarty
Company website url
Project status | In progress
Project start date | 2024-11-04
Project deadline (optional)
Stakeholder chosen plan | Minimum viable product - MVP
Sprint cycle in weeks | 2
Project focus | Budget based |  | Risk margin | 15%
Roadmap calculation config | MVP | MMR | MLP | MAP
Project manager | 20% | 20% | 20% | 20% | user story writing, management, reporting and accept / rejecting
UI/UX design | 15% | Prototyping | 10% | FALSE
Backend auto. testing | 0% | 10% | 10% | 10%
Frontend auto. testing | 0% | 10% | 10% | 10%
Technical (code) review | 12% | 3% | 3% | 3%
Performance testing | 1% | 2% | 2% | 2% | Speed, scalability and stability testing
Security testing | 0% | 2% | 2% | 2%
Technical documentation | 2% | 4% | 4% | 4%
Communication | 20% | 20% | 20% | 20% | Daily stand Ups, scrum poker, retrospectives, sprint demos, brainstorming, support, meetings, meeting reports, emails, chats, phone conversations, etc.

## Budget
Reports | [10 empty] | Metrics
Approved Budget (h) | 1670
Estimated duriation Road map (h) | 1398.6588 |  | 296.73
Total |  |  | 2507.3 | 1373.27 | [6 empty] | Mahsa.a |  |  | Alireza.e |  |  | Komeyl.m |  |  | Javad.z |  |  | Amin.m |  |  | Farzaneh.s |  |  | Nayyer.j |  |  | Vahid.s |  |  | Parya |  |  | Maziar.g |  |  | Arash.g
Name | Start | End | Total Budgeted Cost (h) | Total Actual Cost (h) | Total Budget Variance (%) | Billable Amount (h) | Billing Variance (%) | Earned Value (h) | Planned Value (h) | Schedule Variance | Budgeted Cost (h) | Actual Cost (h) | Budget Variance (%) | Budgeted Cost (h) | Actual Cost (h) | Budget Variance (%) | Budgeted Cost (h) | Actual Cost (h) | Budget Variance (%) | Budgeted Cost (h) | Actual Cost (h) | Budget Variance (%) | Budgeted Cost (h) | Actual Cost (h) | Budget Variance (%) | Budgeted Cost (h) | Actual Cost (h) | Budget Variance (%) | Budgeted Cost (h) | Actual Cost (h) | Budget Variance (%) | Budgeted Cost (h) | Actual Cost (h) | Budget Variance (%) | Budgeted Cost (h) | Actual Cost (h) | Budget Variance (%) | Budgeted Cost (h) | Actual Cost (h) | Budget Variance (%) | Budgeted Cost (h) | Actual Cost (h) | Budget Variance (%)
November | 2024-11-03 | 2024-11-28 | 318.3 | 79.21 | 75.11% | 0 | 100% | 0 | 298.3 | 0% | 50.75 | 20.25 | 39.9% | 35.75 | 6 | 16.78% | 35.75 | 9 | 25.17% | 50.05 | 3 | 5.994% | 0 | 2.83 | 0 | 28 | 0 | 0% | 30 | 6 | 20% | 30 | 15.98 | 53.27% | 15 | 0 | 0% | 23 | 0 | 0% | 20 | 16.15 | 80.75%
December | 2024-12-01 | 2024-12-31 | 402 | 191.74 | 52.3% | 0 | 100% | 0 | 385 | 0% | 70 | 44.46 | 63.51% | 110 | 23.94 | 21.76% | 110 | 0 | 0% | 40 | 34.56 | 86.4% | 0 | 17.44 | 0 | 16 | 3.81 | 23.81% | 12 | 4.99 | 41.58% | 12 | 41.98 | 349.8% | 12 | 3.97 | 33.08% | 15 | 8.66 | 57.73% | 5 | 7.93 | 158.6%
January | 2025-01-01 | 2025-01-31 | 415 | 403.98 | 2.655% | 403.98 | 0% | 0 | 0 | 0% | 90 | 53.25 | 59.17% | 105 | 96.58 | 91.98% | 0 | 24.25 | 0% | 20 | 11.88 | 59.4% | 100 | 129.68 | 129.7% | 16 | 12 | 75% | 12 | 10.25 | 85.42% | 40 | 26.8 | 67% | 12 | 5 | 41.67% | 15 | 32.39 | 215.9% | 5 | 1.9 | 38%
February | 2025-02-01 | 2025-02-28 | 515 | 304.87 | 40.8% | 304.42 | 0.1476% | 262 | 0 | 100% | 90 | 44.75 | 49.72% | 105 | 28.45 | 27.1% | 100 | 94.9 | 0% | 20 | 3.5 | 17.5% | 100 | 107.85 | 107.8% | 16 | 1.34 | 8.375% | 12 | 0.66 | 5.5% | 40 | 8.23 | 20.57% | 12 | 5.45 | 45.42% | 15 | 9.74 | 64.93% | 5 | 0 | 0%
March | 2025-03-01 | 2025-03-31 | 556 | 194.07 | 65.1% | 194.07 | 0% | 210 | 229.43 | -9.252% | 60 | 33.95 | 56.58% | 100 | 1.17 | 1.17% | 100 | 63.88 | 0% | 10 | 3.09 | 30.9% | 100 | 76.6 | 76.6% | 16 | 1.4 | 8.75% | 12 | 2.47 | 20.58% | 30 | 3.95 | 13.17% | 5 | 1.4 | 28% | 30 | 2.16 | 7.2% | 5 | 4 | 80%
April | 2025-04-06 | 2025-04-30 | 301 | 199.4 | 33.75% | 0 | 100% | 0 | 250 | 0% | 55 | 49.93 | 90.78% | 0 | 0 | #DIV/0! | 100 | 30.25 | 0% | 5 | 2.9 | 58% | 100 | 101.79 | 101.8% | 4 | 0 | 0% | 2 | 1.63 | 81.5% | 15 | 2.91 | 19.4% | 5 | 2.49 | 49.8% | 10 | 7.5 | 75% | 5 | 0 | 0%
May | 2025-05-01 | 2025-05-31 | 451 | 0 | 100% | 0 | 0% | 0 | 350 | 0% | 55 |  | 0% | 110 |  | 0% | 110 | 0 | 0% | 5 |  | 0% | 130 | 0 | 0% | 4 | 0 | 0% | 2 | 0 | 0% | 15 | 0 | 0% | 5 | 0 | 0% | 10 | 0 | 0% | 5 | 0 | 0%
Total up to April 30 |  |  |  | 1373.27

## Change log
SuperMarty project - Document change log
Version | Date | Author | Type | Comment
v0.00.01 | 2024-07-08 | Amir Zaghari | Other | First version created
v0.00.02 | 2024-10-29 | Mahsa Amiri |  | Resources were added - Prepration Phase, Epic 1 time estimation are added to the Budgeting tab

## Error Log
SuperMarty project - Error Log
Error Title | Error | Warning | Formula bar | Description | Status | Last Check
Roadmap Checks
Roadmap MVP-MMR columns not correctly deleted | True |  |  | This error will count the numbers of columns in tab "Roadmap" , you need to choose from one of plans - MVP,MMR,MLP,MAP - and then you have to delete all of the columns that not related to your plan , this error will notice you that if you didn't delete the columns correctly , This cell will show "Yes" text. | TRUE | 2023-10-26
Not entered actual delivered date deadlines | 91 |  |  | This error will count the number of actual delivered date deadlines in "Roadmap" tab . It goes to the roadmap tab and if there were empty cells in the column "Actual delivered date" , will count them and shows the number of empty cells. | TRUE | 2023-11-06
Overdue deadlines | 8 | 22 |  | This formula will count the numbers of overdue deadlines in tab "Roadmap" . We got 2 columns in roadmap tab named "Estimated delivery date" and "Actual delivered date" . This formula goes and compares the diffrence between 2 columns aand if actual delivered date was passed the estimated delivery date for 2 weeks , you'll see the count of overdue deadlines in warning column , and if the actual delivered date was passed the estimated delivery date for 4 weeks , you'll see the count of overdue deadlines in Error column in here. | TRUE | 2023-10-26
Project deadline in risk with current resources |  |  |  | This formula will work on overdue deadline of the project. We have a section in "Roadmap settings" tab named "Project deadline" . If you entered some date in it , this formula will record it and compare it with the final estimated deadline in column AP:AP tab "Roadmap" . If the diffrence between two dates were 2 weeks or less than 2 weeks , you'll see the "Yes" word on warning column , But if the diffrence were more than 2 weeks , you'll see the word "Yes" on error column. If you don't enter any deadlines in "Roadmap settings" tab , you'll see nothing. | TRUE | 2023-10-26
Team Performance Checks
Roadmap hours estimation is not accurate (If actual speed is much higher or lower than expected). | 5 | 7 |  | This error will count the numbers of unexpected high or low rates of performance output . We have a tab named "Team Performance" , In this tab there is a column named "Performance Output " B:B column . If someone performance were more than 150% or less than 50% , this formula will show you the numbers of unexpected rates of rows in "Error" column , and if someones performance was more than 125% or less than 75% , it will count the errors in "Warning" column. | TRUE | 2023-10-26
Teammember(s) has low work quality |  | 2 |  | This error will count the numbers of low work quality for you. In the "Team performance" tab , we have a column named "Work quality" G:G , If there were some data with "Bad" text , they'll count on "Error" column , and if there were some data with "Below par" text , they'll be shown on "Warning" column. | TRUE | 2023-10-26
Teammember(s) has low testing quality (high rejection rate) |  | 1 |  | This error will count the numbers of low testing quality for you. In the "Team performance" tab , we have a column named "Testing" I:I , If there were some data with "Bad" text , they'll count on "Error" column , and if there were some data with "Below par" text , they'll be shown on "Warning" column. | TRUE | 2023-10-26
Teammember(s) has low teamwork quality |  |  |  | This error will count the numbers of low teamwork quality for you. In the "Team performance" tab , we have a column named "Teamwork" J:J , If there were some data with "Bad" text , they'll count on "Error" column , and if there were some data with "Below par" text , they'll be shown on "Warning" column. | TRUE | 2023-10-26
Teammember(s) has low core values quality |  |  |  | This error will count the numbers of low core values quality for you. In the "Team performance" tab , we have a column named "Core values" M:M , If there were some data with "Bad" text , they'll count on "Error" column , and if there were some data with "Below par" text , they'll be shown on "Warning" column. | TRUE | 2023-10-26
Teammember(s) has low conflict management quality |  |  |  | This error will count the numbers of low conflict management quality for you. In the "Team performance" tab , we have a column named "Conflict Management" P:P , If there were some data with "Bad" text , they'll count on "Error" column , and if there were some data with "Below par" text , they'll be shown on "Warning" column. | TRUE | 2023-10-26
Meetings Checks
Project is in progress but no sprint meetings are recorded. | Yes | Yes |  | In this formula , you can check for the meetings dates and their relignment with project status and sprint cycle. In the tab "Roadmap settings" we got 2 section , project status and sprint cycle. If the project status was on "On progress" and the sprint cycle was on "Weekly" this formula will work 2 models. The first one is it will go on "Meetings" tab and searches thorugh meetings dates , if there were meetings that set for last 7 days from today , it will show nothing , other wise you should see "Yes" word in warning column , and The second is if some meetings were set for last 14 days from today , it will show nothing , otherwise you'll see "Yes" as an error message at error column. The other sprint cycle is "Every 2 weeks" , if you choose this sprint cycle , the formula will search for last 14 days from today and if there were some meetings , you see nothing , but if there were no meeting , you'll see "Yes" at warning column . In addition , if you choose "Every 2 weeks" as your sprint cycle , the formula will also search for 28 days from today meetings and if there were nothing , you will see "Yes" at error column. | TRUE | 2023-10-26
Project is in maintanance but no monthly progress is recorded. | Project not in maintenance | Project not in maintenance |  | In this formula , you can check for the meetings dates and their relignment with project status and sprint cycle. In the tab "Roadmap settings" we got 2 section , project status and sprint cycle. If the project status was on "In maintenance" and the sprint cycle was on "Weekly" this formula will work 2 models. The first one is it will go on "Meetings" tab and searches thorugh meetings dates , if there were meetings that set for last 14 days from today , it will show nothing , other wise you should see "Yes" word in warning column , and The second is if some meetings were set for last 28 days from today , it will show nothing , otherwise you'll see "Yes" as an error message at error column. The other sprint cycle is "Every 2 weeks" , if you choose this sprint cycle , the formula will search for last 28 days from today and if there were some meetings , you see nothing , but if there were no meeting , you'll see "Yes" at warning column . In addition , if you choose "Every 2 weeks" as your sprint cycle , the formula will also search for 56 days from today meetings and if there were nothing , you will see "Yes" at error column. | TRUE | 2023-10-26
Action points Checks
Overdue action points and checkboxes | 6 |  |  | In the tab of "Action points" we have a column named "Deadline" - Column D . This formula goes thorugh that column and compares that deadlines with the date of Today , If some deadlines were before today , will count and show you the number of overdue deadlines. In addition , this formula will also count the unfilled checkboxes in A:A column at "Action points" tab. | TRUE | 2023-10-26
Sprint cycle is chosen but no action points are recorded. |  |  |  | In this formula , you can check for the action points deadlines and their relignment with sprint cycle. In the tab "Roadmap settings" we got 1 section , sprint cycle. If the sprint cycle was on "Weekly" this formula will work 2 models. The first one is it will go on "Action points" tab and searches thorugh deadlines, if there were deadlines that set for last 14 days from today , it will show nothing , other wise you should see "Yes" word in warning column , and The second is if some deadlines were set for last 28 days from today , it will show nothing , otherwise you'll see "Yes" as an error message at error column. The other sprint cycle is "Every 2 weeks" , if you choose this sprint cycle , the formula will search for last 28 days from today and if there were some deadlines, you see nothing , but if there were no deadlines, you'll see "Yes" at warning column . In addition , if you choose "Every 2 weeks" as your sprint cycle , the formula will also search for 56 days from today deadlines and if there were nothing , you will see "Yes" at error column. | TRUE | 2023-10-26
Resources Checks
Resources deficit errors | 1 |  |  | In the tab "Resources" on column I:I we have some data named "Main roles def. p/w". If the amount of the deficit were between 1 to 8 , You'll see the count of them at warning column , but if they were more than 8 , you'll see the count of them at error column. | TRUE | 2023-10-26
Project deadline in risk with current resources | Yes |  |  | If the recent item "Deficit errors" were not equal to "0" , this formula will show you "Yes" , which means that with the resources that you have right now , your deadline is in the risk. | TRUE | 2023-10-26
Project epics and sprints not correctly set based on resources expected output | Yes |  |  | This part is working by script on , for reaching to the code , follow this steps: go to the tab bar choose "Extensions" - Apps script - code name is : Epic Dyas.gs . This script is goes to the "Roadmap" tab , searches for diffrent epics and their estimated dates deadlines at column AP, If the dates diffrences were between 20 to 40 days , you'll see "Yes" word at warning column , but if they were less than 20 days and more than 40 days , you'll see "Yes" word at error column. | TRUE | 2023-11-06
Resources are spending to much time on non development related activities. |  | Yes |  | In the tab "Resources" we have 2 columns named "Working hours p/ w" and "Committed time". This formula will go and sum the working hours and then compares the half of it with the sum of committed time , If teammembers were spending too much time on non development tasks , You'll see "Yes" word here at warning column , and if the sum of comittetd time was less than 1/3 working hours , you'll see "Yes" word at error column. | TRUE | 2023-10-26
Developers seniority is not a good match |  |  |  | In the tab of "Resources" , we got some roles as :Full stack development-Backend development-Frontend development-Backend auto. testing-Frontend auto. testing-Technical (code) review and some seniorities as Senior A to Senior D . This formula will Sum of thecommitted times of roles that mentioned before with senioroties that mentioned before , with the roles but with diffrent senioroties (anything but not the seniors of A to D ) ,If the sum committed time of technical members with seniors A to D , was less than 20% of technical members with other senioroties , It will show you "Yes" word in error column , and also if the Sum of the committed time of technical members with Seniors of A to D was more than 40% of the sum of committed time of technical members with other senioroties , you'll see "Yes" word at warning column. | TRUE | 2023-10-30
PO's assigned or commited time is not a good match | Yes |  |  | In the tab of "Resources" , we got a role as "Product Owner" and some other rules , this formula will go on resources tab and sum of the all of committed times of product owners and compares them with sum of the any other roles except product owners , if the sum of committed time of product owners was less than 20 % of sum of committed times of other roles , you'll see the word "Yes" at error column , and if the committed time of produt owners were more than 40% of sum of committed times of other rules , you'll see the word "Yes" at warning column. | TRUE | 2023-10-30
Technical coach assigneded or commited time is not a good match |  |  |  |  | FALSE
Epic 0 and release of the platform epic should not have any UI/UX design or automated testing. |  |  |  | This part is being done by data validation, The way it works is you can't enter any number (or formulas can't enter any numbers) except 0 into related cells. | TRUE | 2023-10-30
Alert when someone's seniority is not correctly set(output is more or less than expected). |  |  |  |  | FALSE
Count of resources last check that they weren't updated in last 2 weeks | 10 | 10 |  | This formula goes thorugh "Resources" tab in the column "Last checked and verified" and searches for the dates that they're in 2 last weeks, if the rows were being updated in last 2 weeks , there are no errors , but If they have been updated later than this time,you'll see the count of erros at Error column.If they were updated in last week (last 7 days) ,you won't see anything in warning column but if they weren't , you'll see the count of them in warning column. | TRUE | 2023-10-26
Check if personnel first name and lastname is entered (based on space and @ before the name). | 1 |  |  | The way how this formula works it we have a column named "Team members" in the tab "Resources" that contains the name of team members that work on the project , this formula goes and checks if firstname and lastname is entered in a correct way with an space , and if some name was entered without an space , this item will show the numbers of errors. Also the names shoud be written with an @ before , otherwise it'll count as errors. | TRUE | 2023-10-26
Check if Resources do not contain duplicate names or personnel id's. | 3 |  |  | If there were duplicate data in column "Team members" in the tab "Resources" , this section will show you the count of duplicates , otherwise shows nothing. | TRUE | 2023-10-26
Resource deficits and overflows more than the project risk margin should be checked for each role. |  |  |  |  | FALSE
Roadmap setting Checks
Project settings errors | 1 |  |  | In the tab of "Roadmap setting" there is a section named "Project settings" which include the parts of " prject name - company name - company website URL - project status - project start date - project deadline - stakeholder chosen plan - sprint cycle and project focus . This formula goes through these items and if some item were empty or missed , will count the empty cells and show them as errors. The note is that the item "Project deadline" is optional and this error won't count that cell if it was empty or filled, and also the empty cells will show with the red background in the related tab. | TRUE | 2023-10-26
Stakeholder not chosen plan |  |  |  | In the tab of "Roadmap setting" there is a section named "Stakeholder Chosen Plan" that if this cell was empty , it will show the error message of "Yes" , and It was chosen , this cell will be empty. | TRUE | 2023-10-26
Project name is not filled in |  |  |  | In the tab of "Roadmap setting" there is a section named "Project name" that if this cell was empty , It will show the error message of "Yes" , and It was chosen , this cell will be empty. | TRUE | 2023-10-26
Project deadline is sooner than project start date |  |  |  | In this section , we have a formula which is if the project deadline was sooner than project start date , show "Yes" message , but if any of these cells were empty or even one of them were empty , shows nothing. | TRUE | 2023-10-26
project plans formula's are changed in a unrealistic way |  |  |  |  | FALSE
Project status is incorrect(paused/ cancelled but work is done or in progress but no work is done). |  |  |  |  | FALSE
Release report sorting is incorrect (latest release should be on top. |  |  |  |  | FALSE
Change Log Checks
Project versioning (filename) not in line with changelog | Yes |  | Bugloos Roadmap template v2.06.00 ¦ 06-07-2024 | This item include a formula and a script that is in extensions - apps script named "file name" . The way that this script works is in column "D" which is hidden , we have a formula bar and a formla that is =getfilename , this script goes thorugh the file and reads the file name and show it by this "=getfilename" formula , after that we have a formula in cell "B45" which is compare the versioning part of file name with the table of change log in tab change log , if the last row of that table was the same with the version part of file name , it will show nothing , but if they were diffrent , it will show "Yes" | TRUE | 2023-10-26
Project roadmap rows updated but changelog is not changed. |  |  |  |  | FALSE
Format Checks
Non company font's are used |  |  |  | This part is working by script on , for reaching to the code , follow this steps: go to the tab bar choose "Extensions" - Apps script - code name is : fontcheck .This script goes through all of the tabs and checks all of the items (including dates - texts - numbers ) for "Fira Sans" font , If entered data were something except fira sans , you'll see the count of the mistakes in here , if mistakes were less than 20 items , you'll see the count of them at warning column , but if they were more than 20 items , you'll see the count of them at error column. | TRUE | 2023-11-13
Non company font sizes are used |  |  |  | This section is focusing on font sizes with code script , for reaching to the code , follow this steps: go to the tab bar choose "Extensions" - Apps script - code name is : fontsizecheck . This script is searching for all of the font sizes on all the tabs , and checks for any cells in there except the first row , if there were any cells that contains data that font sizes were more than 14 , it will count them as errors . If the count of mistakes were less than 20 , it will show them on warning column , but if they were more than 20 items , you'll see the count of them on error column. | TRUE | 2023-11-16
Non company font colors are used. |  |  |  |  | FALSE
Spreadsheet has more than 2 editors (all team members and stakeholders should be viewers). |  |  |  | This item is working by script code too. For reaching to the code , follow this steps: go to the tab bar choose "Extensions" - Apps script - code name is : editorscheck. The way how it works is checks for the number of people are have editor access on the file . The standard number of editors should be 2, If it was between 2 to 4 , you'll see "Yes" on warning column , If it was more than 4 , You'll see "Yes" on error column. | TRUE | 2023-11-16
Error Log Checks
No last check dates entered | 8 |  |  | This formula is check for the "Last Check" column in tab "Error log" . Each item should have a last check date and if any items were empty from date , this formula will go and count the empty ones. | TRUE | 2023-10-26
Last Check not being updated by last three months | 35 |  |  | The "Last Check" Column in the "Error Log" tab shoud contain date data with a maximum of last 3 months. This formula will go through that column and searches for the dates that not updated in the last 3 months and count the errors. | TRUE | 2023-10-26
Not entered formulas for error logs items | 8 |  |  | This formula is check for the formulas of items in error log tab , when you enter a formula for some item , you should fill the check box , this formula goes and counts the number of unchecked check boxes and shou you the number of them in here at Error column. | TRUE | 2023-10-26